## Program Summary 202202
| Report Generated | 04/12/2022 09:02:23 AM
[14 empty] | Month To Date | [9 empty] | Inception To Date | [6 empty] | At Complete |  |  |  |  | At Complete Analysis | [5 empty] | Schedule Analytics |  | Predictive Triggers | [6 empty] | Over Target Baseline
functions | Mission Area | Major Program | Program Code | Description | Duration | Program Type | Primary Contract Type | Primary APEX Contract Phase | Primary EAC Classification | Status | Tag | Responsible | Release Status | MTD BCWS | MTD BCWS HOURS | MTD BCWP | MTD BCWP HOURS | MTD ACWP | MTD ACWP HOURS | MTD SV | MTD CV | MTD SPI | MTD CPI | ITD BCWS | ITD BCWP | ITD ACWP | ITD SV | ITD CV | ITD SPI | ITD CPI | TCPI | BAC excl UB | LRE | BCWR | VAC (LRE) | % COMP | % SPENT | Prev Period BAC excl UB | Prev Period LRE | IEAC MIN | IEAC MAX | BEI | CEI | MTD SPI | MTD CPI | TCPI | VAC (LRE) | Staffing Delta | Comments | User Notes | OTB BCWS | OTB BCWP | OTB ACWP | OTB SV | OTB CV | OTB SPI | OTB CPI
| Strategic Missile Defense | MISSILE DEFENSE | 0EPV | Next Generation Interceptor | 64 | Development |  |  |  | Deteriorating | Active | Finance: Andrea Huerta,Finance: Andrea Huerta,Finance: Katherine Beckum,Finance: Katherine Beckum,Finance: Rodolfo Gallego,Finance: Rodolfo Gallego,PM: Timothy Soeder,PM: Timothy Soeder,Planner: ANTOINETTE AGUILAR,Planner: ANTOINETTE AGUILAR,Planner: DeAnna Stapler,Planner: DeAnna Stapler,Planner: Maria Brusati,Planner: Maria Brusati,Planner: Seth Van Norman,Planner: Seth Van Norman,Planner: ZACHARY SHAW,Planner: ZACHARY SHAW | FINAL | 26402.6287 | 47534.74 | 24573.5465 | 42731.632 | 25618.1883 | 60928.768 | -1829.0822 | -1044.6418 | 0.93072 | 0.95922 | 142048.39 | 133980.5703 | 137586.4548 | -8067.8197 | -3605.8845 | 0.9432 | 0.97379 | 0.96636 | 1143798.9595 | 1182556.221 | 1009818.3893 | -38757.2615 | 12% | 12.03% | 1143096.7753 | 1173519.9145 | 1174582.5794 | 1237026.6916 | 0.92978 | 0.59649 |  | 0.95922 | 0.96636 | -38757.2615 | 68449069.51 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | SM3 IIA | 0E2Y | SM3 IIA RDTE | 51 | Production |  |  |  | Deteriorating | Active | Finance: DERRICK TAFT,Finance: DERRICK TAFT,Finance: Jessica DONOVAN,Finance: Jessica DONOVAN,PM: ANDREW HUTCHINS,PM: ANDREW HUTCHINS,PM: CEDRIC MACADANGDANG,PM: CEDRIC MACADANGDANG,PM: Erick Elkins,PM: Erick Elkins,PM: HADRIAN KIM,PM: HADRIAN KIM,PM: John Melichar,PM: John Melichar,PM: Michael Allison,PM: Michael Allison,PM: Sharon Walk,PM: Sharon Walk,Planner: Alvin Neff,Planner: Alvin Neff,Planner: CHARLES KENNA,Planner: CHARLES KENNA,Planner: Erik Hammer,Planner: Erik Hammer,Planner: Helen Trujillo,Planner: Helen Trujillo,Planner: Janet Sword,Planner: Janet Sword,Planner: Luis Contreras,Planner: Luis Contreras,Planner: Melissa Elliott,Planner: Melissa Elliott,Planner: Sara Wilson,Planner: Sara Wilson | FINAL | 32334.0485 | 46703.19 | 21971.174 | 26238.215 | 29209.1797 | 40191.868 | -10362.8745 | -7238.0057 | 0.67951 | 0.7522 | 1129241.9354 | 1191693.4566 | 1245559.5935 | 62451.5212 | -53866.1369 | 1.0553 | 0.95675 | 0.9877 | 2076816.5322 | 2141704.7484 | 885123.0755 | -64888.2162 | 57% | 59.97% | 2079420.8703 | 2144562.112 | 2122209.241 | 2170691.415 | 1.3491 | 0.27168 | 0.67951 | 0.7522 |  | -64888.2162 |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Strategic Missile Defense | MISSILE DEFENSE | 619Y | KSA THAAD Production Reportable | 6 | Development |  |  |  | Steady | Active | Finance: Adam Muzerall,Finance: Adam Muzerall,Finance: Joseph Chop,Finance: Joseph Chop,Finance: MICHAEL AHLIN,Finance: MICHAEL AHLIN,PM: Joseph DiCesare,PM: Joseph DiCesare,PM: William Lawton,PM: William Lawton,Planner: Catherine Arno,Planner: Catherine Arno,Planner: Jereme Coste,Planner: Jereme Coste,Planner: Michael Mirabile,Planner: Michael Mirabile,Planner: Monica Dwyre-Wortman,Planner: Monica Dwyre-Wortman,Planner: SAMANTHA HATFIELD-COLANGELO,Planner: SAMANTHA HATFIELD-COLANGELO,Planner: SARAH DIXON,Planner: SARAH DIXON,Planner: Thomas Wegerski,Planner: Thomas Wegerski,Planner: ZACHARY SHAW,Planner: ZACHARY SHAW | FINAL | 15944.3089 | 69611.015 | 11486.5736 | 46098.224 | 14536.9282 | 55378.291 | -4457.7353 | -3050.3547 | 0.72042 | 0.79017 | 266962.4892 | 235757.786 | 236850.7442 | -31204.7033 | -1092.9583 | 0.88311 | 0.99539 | 1.0025 | 943108.2063 | 942449.6942 | 707350.4203 | 658.512 | 25% | 25.11% | 882913.4654 | 883610.9632 | 947480.3966 | 1041538.7427 | 0.84737 | - | 0.72042 | 0.79017 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Naval Power | SM-6 | 0EKP | SM6 FY19 23 MY Production | 85 | Production |  |  |  | Steady | Watch Program | Finance: David Henz,Finance: David Henz,Finance: Valerie Quay,Finance: Valerie Quay,PM: AMANDA MUELLER,PM: AMANDA MUELLER,PM: Robert Marsett,PM: Robert Marsett,Planner: BRADFORD KNOX,Planner: BRADFORD KNOX,Planner: Bobbi Mayeux,Planner: Bobbi Mayeux,Planner: Daniel Curtis,Planner: Daniel Curtis,Planner: Kevin Mcvey,Planner: Kevin Mcvey,Planner: Kristin Jiroudek,Planner: Kristin Jiroudek | FINAL | 15809.3614 | 15396.75 | 2800.2381 | 10416.965 | 16675.9593 | 25776.078 | -13009.1233 | -13875.7212 | 0.17713 | 0.16792 | 126249.7855 | 183203.1917 | 234751.7251 | 56953.4063 | -51548.5334 | 1.4511 | 0.78041 | 1.0168 | 864378.2244 | 904701.8777 | 681175.0327 | -40323.6533 | 21% | 27.16% | 864378.2247 | 884056.7711 | 836246.8218 | 1107591.3985 | 0.74843 | 0.26667 | 0.17713 | 0.16792 |  | -40323.6533 | 19037173 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | LWS OTHER | 0EQ1 | Stinger FMS Bundle IDIQ | 55 | Production |  |  |  | Steady | Active | Finance: Christopher Butler,Finance: Christopher Butler,Finance: KENNETH OLISKY,Finance: KENNETH OLISKY,PM: Amanda Pena,PM: Amanda Pena,PM: Andrew Gallerani,PM: Andrew Gallerani,PM: John Lynch,PM: John Lynch,Planner: Nan Gao,Planner: Nan Gao | PRELIMINARY | 3674.5003 | 12864.03 | 2307.2997 | 9957.347 | 2158.5584 | 11142.86 | -1367.2006 | 148.7413 | 0.62792 | 1.0689 | 24873.8599 | 21078.8173 | 22095.3277 | -3795.0426 | -1016.5104 | 0.84743 | 0.95399 | 0.9426 | 270225.4431 | 286413.4736 | 249146.6259 | -16188.0304 | 8% | 8.177% | 270225.4431 | 270889.7386 | 283256.866 | 330276.5428 | 0.80488 | 0.33333 | 0.62792 | 1.0689 | 0.9426 | -16188.0304 |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Internal - Other | Internal - Other | 61HE | 2022 RMD IRAD | 12 | Internal |  |  |  | Steady | Active | PM: KRISTEN STONE,PM: KRISTEN STONE,Planner: CHARLES KENNA,Planner: CHARLES KENNA,Planner: David Lafleur,Planner: David Lafleur,Planner: Marilyn Buckelew,Planner: Marilyn Buckelew | FINAL | 24191.2321 | 119245.33 | 20961.3502 | 108720.927 | 17215.5249 | 101838.129 | -3229.8819 | 3745.8253 | 0.86649 | 1.2176 | 40007.2964 | 35603.9229 | 30368.2315 | -4403.3735 | 5235.6914 | 0.88994 | 1.1724 | -8.5839 | 261945.0902 | 4000.0606 | 226341.1674 | 257945.0297 | 14% | 11.59% | 246782.9422 | 0 | 223425.0747 | 247301.6964 | - | -
| Naval Power | NAVAL RADARS | 60JD | AMDR LRIP | 79 | Production |  |  |  | Steady | Watch Program | Finance: Joshua Stedman,Finance: Joshua Stedman,PM: David Fenn,PM: David Fenn,Planner: Stephen Colwell,Planner: Stephen Colwell | FINAL | 22712.1126 | 40464.53 | 13467.4524 | 35710.693 | 14384.9964 | 39586.558 | -9244.6602 | -917.544 | 0.59296 | 0.93622 | 977116.9782 | 906180.7685 | 1090677.0287 | -70936.2097 | -184496.2602 | 0.9274 | 0.83084 | 0.79083 | 1091010.7769 | 1324393.7101 | 184830.0084 | -233382.9332 | 83% | 99.97% | 1091010.7769 | 1322673.2997 | 1313137.9895 | 1330552.3265 | 0.68627 | 0.27429 | 0.59296 | 0.93622 |  | -233382.9332 | 42105757.05 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | BAHRAIN PROGRAMS | 618T | Bahrain Patriot 2 Lot | 59 | Production |  |  |  | Steady | Active | Finance: Joseph Galli,Finance: Joseph Galli,PM: Kathleen Kapilian,PM: Kathleen Kapilian,PM: Stefanie Chiou,PM: Stefanie Chiou,Planner: Ani Days,Planner: Ani Days,Planner: Jeremy Koen,Planner: Jeremy Koen,Planner: Joaquin Casanova,Planner: Joaquin Casanova,Planner: Lee Brucks,Planner: Lee Brucks,Planner: MATTHEW RONDEAU,Planner: MATTHEW RONDEAU,Planner: Michael Jordan,Planner: Michael Jordan,Planner: Nanette Halliburton,Planner: Nanette Halliburton,Planner: Prashant Navkal,Planner: Prashant Navkal,Planner: Stephen Pike,Planner: Stephen Pike | FINAL | 16812.911 | 45681.85 | 5921.2857 | 34995.268 | 6277.7233 | 22470.001 | -10891.6253 | -356.4375 | 0.35219 | 0.94322 | 322037.8461 | 293749.5701 | 274928.9142 | -28288.276 | 18820.6559 | 0.91216 | 1.0685 | 1.0644 | 450621.4042 | 422309.8345 | 156871.8341 | 28311.5696 | 65% | 61.01% | 450617.0564 | 415507.1907 | 421749.9053 | 435888.8629 | 0.94477 | 0.70732 | 0.35219 | 0.94322 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Strategic Missile Defense | MISSILE DEFENSE | 61BE | CLS FY21 IDIQ | 12 | Development |  |  |  | Steady | Active | PM: Alexander Umansky,PM: Alexander Umansky,PM: Antone Lawrence,PM: Antone Lawrence,PM: CHARLES KENNA,PM: CHARLES KENNA,PM: ELIZABETH SWEENEY,PM: ELIZABETH SWEENEY,PM: Teresa Rudolph,PM: Teresa Rudolph,PM: Thomas Mccarthy,PM: Thomas Mccarthy,Planner: CHRISTINA CORACCIO,Planner: CHRISTINA CORACCIO,Planner: Christopher Shoup,Planner: Christopher Shoup,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Jereme Coste,Planner: Jereme Coste,Planner: SAMANTHA HATFIELD-COLANGELO,Planner: SAMANTHA HATFIELD-COLANGELO | FINAL | 3657.3104 | 6317.79 | 3901.3625 | 6213.808 | 3486.9634 | 8501.021 | 244.0521 | 414.3991 | 1.0667 | 1.1188 | 129213.6524 | 120033.6392 | 115888.2269 | -9180.0131 | 4145.4124 | 0.92895 | 1.0358 | 0.96877 | 229628.4535 | 229016.476 | 109594.8143 | 611.9775 | 52% | 50.47% | 227686.5134 | 226398.7115 | 221698.138 | 229790.3393 | 0.80101 | - | 1.0667 |  | 0.96877 | 611.9775 |  | MTD SPI 5 month average is less than ITD SPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Land Warfare & Air Defense | LTAMDS | 6161 | LTAMDS UMR | 42 | Internal |  |  |  | Steady | Watch Program | Finance: RICHARD PACKER,Finance: RICHARD PACKER,PM: Alan Chon,PM: Alan Chon,PM: Jason Rathbone,PM: Jason Rathbone,Planner: Jessica Vanco,Planner: Jessica Vanco | FINAL | 7480.4565 | 37158.36 | 10221.6314 | 61417.266 | 23747.7312 | 115773.167 | 2741.1749 | -13526.0997 | 1.3664 | 0.43043 | 718939.673 | 658669.4974 | 732500.9988 | -60270.1757 | -73831.5014 | 0.91617 | 0.89921 | 0.59535 | 762986.0256 | 907719.6617 | 104316.5282 | -144733.6361 | 86% | 96% | 762175.3688 | 856917.0154 | 848510.5627 | 859125.7753 | 0.93086 | 0.58333 | 1.3664 | 0.43043 | 0.59535 | -144733.6361 | 16448652 | Engage Immediately. MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | LWS OTHER | 0ERJ | Enduring Indirect Fire Protection Capability | 21 | Internal |  |  |  | Steady | Active | PM: DAVID MASEREDJIAN,PM: DAVID MASEREDJIAN,Planner: Lee Brucks,Planner: Lee Brucks,Planner: Michael Jordan,Planner: Michael Jordan,Planner: Nanette Halliburton,Planner: Nanette Halliburton,Planner: Seth Van Norman,Planner: Seth Van Norman | FINAL | 2209.64 | 12348.37 | 1668.6149 | 9688.882 | 1312.5391 | 11222.338 | -541.0251 | 356.0758 | 0.75515 | 1.2713 | 14829.8606 | 13512.0645 | 13220.7467 | -1317.7961 | 291.3178 | 0.91114 | 1.022 | 0.97703 | 109118.366 | 111074.3475 | 95606.3015 | -1955.9816 | 12% | 12.12% | 109118.6583 | 108841.1474 | 106765.7927 | 115888.9953 | 0.7672 | 0.51351
| Air Power | STORMBREAKER | 0EDS | StormBreaker SDB II iECP | 24 | Development |  |  |  | Steady | Active | Finance: Chris Parzuchowski,Finance: Chris Parzuchowski,Finance: Garrett McGhee,Finance: Garrett McGhee,Finance: John Kelly,Finance: John Kelly,PM: Alison Howlett,PM: Alison Howlett,PM: David Brown,PM: David Brown,PM: Jodi Scott,PM: Jodi Scott,PM: Laurie Skalenda,PM: Laurie Skalenda,PM: Thomas Weneck,PM: Thomas Weneck,Planner: CHLOE CARLSON,Planner: CHLOE CARLSON,Planner: MIGUEL GUZMAN,Planner: MIGUEL GUZMAN | FINAL | 3547.9422 | 9919.59 | 1780.6244 | 8571.875 | 4571.4007 | 17238.977 | -1767.3178 | -2790.7763 | 0.50188 | 0.38951 | 269567.8801 | 255659.6793 | 321250.5711 | -13908.2007 | -65590.8918 | 0.94841 | 0.79583 | 0.67797 | 336761.283 | 440875.3001 | 81101.6037 | -104114.0171 | 76% | 95.39% | 340121.9237 | 441887.0063 | 423159.2357 | 428703.1923 | 0.85874 | - | 0.50188 | 0.38951 | 0.67797 | -104114.0171 | 31303070.25 | Engage Immediately. MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | EUCOM PROGRAMS | 614N | Romania Patriot 3 Lot | 12 | Production |  |  |  | Steady | Active | Finance: JESSICA KING CERNIGLIA,Finance: JESSICA KING CERNIGLIA,Finance: PRESTON CALLANDER,Finance: PRESTON CALLANDER,PM: PRESTON CALLANDER,PM: PRESTON CALLANDER,PM: Patrick Griffin,PM: Patrick Griffin,Planner: Alvin Neff,Planner: Alvin Neff,Planner: Andrea Miller,Planner: Andrea Miller,Planner: Brian Martinez,Planner: Brian Martinez,Planner: Dominique Laplanche,Planner: Dominique Laplanche,Planner: JAMES RICHARD,Planner: JAMES RICHARD,Planner: Joaquin Casanova,Planner: Joaquin Casanova,Planner: Lee Brucks,Planner: Lee Brucks,Planner: Michael Jordan,Planner: Michael Jordan,Planner: Stephen Pike,Planner: Stephen Pike | FINAL | 8306.2534 | 22907.77 | 6572.7971 | 21176.195 | 3738.3382 | 24979.817 | -1733.4563 | 2834.4589 | 0.79131 | 1.7582 | 339376.2244 | 311423.7414 | 296838.8317 | -27952.4831 | 14584.9097 | 0.91764 | 1.0491 | 0.97825 | 392244.5359 | 379456.9502 | 80820.7946 | 12787.5858 | 79% | 75.68% | 392244.5359 | 377395.0345 | 373874.5456 | 380789.0457 | 0.91002 | 0.43333 | 0.79131 |  | 0.97825 | 12787.5858 |  | MTD SPI 5 month average is less than ITD SPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | NAVAL AIR ADVANCED | 0EKH | Maritime Strike Tomahawk IP and T | 55 | Development |  |  |  | Steady | Active | Finance: Brian Prince,Finance: Brian Prince,Finance: Laura Clark,Finance: Laura Clark,PM: Greg Burgess,PM: Greg Burgess,Planner: Gregory Ornella,Planner: Gregory Ornella,Planner: Kaelin Butler,Planner: Kaelin Butler,Planner: Robert Miles,Planner: Robert Miles | FINAL | 4706.4512 | 22554.48 | 4517.1215 | 21861.261 | 6169.0859 | 24934.483 | -189.3297 | -1651.9644 | 0.95977 | 0.73222 | 249635.8625 | 232766.9761 | 265462.2371 | -16868.8864 | -32695.2611 | 0.93243 | 0.87684 | 0.95233 | 304527.3243 | 340814.5039 | 71760.3483 | -36287.1796 | 76% | 87.17% | 304573.7339 | 332006.9549 | 347302.2941 | 353233.3358 | 0.87513 | 0.625 |  | 0.73222 |  | -36287.1796 | 8800423.13 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Advanced Technology | AMS: ADV PROGRAMS | 0EQO | MSDM Phase 2 | 39 | Development |  |  |  | Steady | Active | PM: DONALD BOHNEY,PM: DONALD BOHNEY,PM: Stephen Watters,PM: Stephen Watters,Planner: BROOKS WILTSHIRE,Planner: BROOKS WILTSHIRE,Planner: Derek Prost,Planner: Derek Prost,Planner: Susan Dickens,Planner: Susan Dickens,Planner: Tammy Antunez,Planner: Tammy Antunez,Planner: VIRGINIA WILKINSON,Planner: VIRGINIA WILKINSON | FINAL | 1844.0314 | 2968.5 | 3231.9877 | 10266.615 | 3502.0523 | 15800.849 | 1387.9563 | -270.0645 | 1.7527 | 0.92288 | 54762.4778 | 45248.7819 | 49925.6007 | -9513.6959 | -4676.8188 | 0.82627 | 0.90632 | 1.0299 | 91619.0621 | 94947.6343 | 46370.2803 | -3328.5722 | 49% | 54.49% | 91480.5566 | 95006.5002 | 101088.6155 | 111845.7971 | 0.70646 | 0.38983 | 1.7527 |  | 1.0299 | -3328.5722 | 521479 | MTD SPI 5 month average is less than ITD SPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | TAIWAN PROGRAMS | 617U | Taiwan IDS ISS | 3 | Development |  |  |  | Steady | Active | PM: Edgar Hoak,PM: Edgar Hoak,Planner: Hamon Ashford,Planner: Hamon Ashford,Planner: Timothy Parella,Planner: Timothy Parella | FINAL | 4579.3618 | 12605.14 | 5038.3771 | 18522.258 | 4287.2296 | 14264.829 | 459.0153 | 751.1475 | 1.1002 | 1.1752 | 99666.7755 | 88909.8078 | 88841.0684 | -10756.9677 | 68.7394 | 0.89207 | 1.0008 | 1.3935 | 133045.0077 | 120512.3365 | 44135.1999 | 12532.6712 | 67% | 66.78% | 132854.9231 | 122133.7293 | 132942.1458 | 138277.821 | 0.89564 | 0.4359 | 1.1002 | 1.1752 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Naval Power | TOMAHAWK | 0EOS | FY21 TOMAHAWK CRUISE MISSILES RECERTIFICATION | 10 | Production |  |  |  | Steady | Active | Finance: JENNIFER DESHAZO,Finance: JENNIFER DESHAZO,PM: Desiree Vorel,PM: Desiree Vorel,PM: KELLY COVINGTON,PM: KELLY COVINGTON,PM: MAYA KEMPTON,PM: MAYA KEMPTON,PM: SAMUEL BREAN,PM: SAMUEL BREAN,PM: Sara THOMAS,PM: Sara THOMAS,Planner: David Rowe,Planner: David Rowe,Planner: Robert Miles,Planner: Robert Miles,Planner: Yvette Boessneck,Planner: Yvette Boessneck | FINAL | 4050.9959 | 23269.2 | 4269.8568 | 26065.304 | 3766.6371 | 22778.94 | 218.8609 | 503.2197 | 1.054 | 1.1336 | 25385.1516 | 19872.2826 | 23534.777 | -5512.8689 | -3662.4944 | 0.78283 | 0.84438 | 1.0215 | 62218.3677 | 64989.3318 | 42346.0851 | -2770.964 | 32% | 37.83% | 61814.7008 | 64630.0549 | 73685.3152 | 87597.8258 | 0.80734 | 0.375 | 1.054 |  |  | -2770.964 |  | MTD SPI 5 month average is less than ITD SPI. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | SM-2 | 0EQI | SM2 Block IIIC LRIP | 39 | Production |  |  |  | Deteriorating | Active | PM: AMANDA MUELLER,PM: AMANDA MUELLER,PM: JASON HERRERA,PM: JASON HERRERA,Planner: Charles Green,Planner: Charles Green,Planner: Kristin Jiroudek,Planner: Kristin Jiroudek,Planner: Seth Van Norman,Planner: Seth Van Norman | FINAL | 180.4235 | 781.78 | 119.823 | 705.55 | 110.0798 | 646.324 | -60.6005 | 9.7432 | 0.66412 | 1.0885 | 1014.5982 | 925.6582 | 831.6991 | -88.94 | 93.9591 | 0.91234 | 1.113 | 0.88337 | 37716.7826 | 42480.2233 | 36791.1244 | -4763.4407 | 2% | 2.205% | 37716.7826 | 41654.7451 | 33888.3348 | 37064.5152 | 1 | - | 0.66412 |  | 0.88337 | -4763.4407 |  | MTD SPI 5 month average is less than ITD SPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | ESSM | 0ERF | ESSM Design Agent CY21 25 | 45 | Internal |  |  |  | Steady | Active | Finance: Edward Pajor,Finance: Edward Pajor,PM: David Bujak,PM: David Bujak,PM: SIGVALD WINSTRYG,PM: SIGVALD WINSTRYG,Planner: Charles Green,Planner: Charles Green,Planner: Kristin Jiroudek,Planner: Kristin Jiroudek,Planner: Seth Van Norman,Planner: Seth Van Norman | FINAL | 1113.8364 | 6287.63 | 1280.2012 | 7463.205 | 564.1693 | 3240.83 | 166.3649 | 716.0319 | 1.1494 | 2.2692 | 4621.2731 | 3124.6528 | 2362.3222 | -1496.6203 | 762.3306 | 0.67615 | 1.3227 | 1.0105 | 38520.9345 | 37389.8146 | 35396.2817 | 1131.1199 | 8% | 6.133% | 38521.1492 | 38251.2813 | 29122.8701 | 41940.4159 | 0.56 | 1
| Naval Power | TOMAHAWK | 0ELD | Tomahawk JMEWS EMD | 45 | Development |  |  |  | Steady | Active | Finance: Devyn BARRIER,Finance: Devyn BARRIER,Finance: Tegan Cole,Finance: Tegan Cole,PM: Juliette Haggh,PM: Juliette Haggh,Planner: Erin St. Germain,Planner: Erin St. Germain,Planner: Michael Garcia,Planner: Michael Garcia,Planner: Sam Westmoreland,Planner: Sam Westmoreland,Planner: Yanis ROMERO QUIANES,Planner: Yanis ROMERO QUIANES | FINAL | 2040.6227 | 7109.8 | 1825.9589 | 6947.635 | 2587.0544 | 9461.725 | -214.6639 | -761.0955 | 0.8948 | 0.70581 | 45487.3935 | 44122.4388 | 48509.3276 | -1364.9548 | -4386.8888 | 0.96999 | 0.90957 | 1.0285 | 78960.0534 | 82381.3874 | 34837.6146 | -3421.334 | 56% | 61.44% | 78441.0987 | 81261.2865 | 86810.6841 | 87995.5601 | 0.96255 | 0.425 | 0.8948 | 0.70581 | 1.0285 | -3421.334 | 1832377.92 | Engage Immediately. MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | NAVAL RADARS | 61A4 | EASR Production | 84 | Production |  |  |  | Steady | Watch Program | Finance: ANN LONG,Finance: ANN LONG,Finance: Brian Land,Finance: Brian Land,Finance: Joshua Stedman,Finance: Joshua Stedman,PM: David Fenn,PM: David Fenn,Planner: Byron Chin,Planner: Byron Chin,Planner: Kevin Mcvey,Planner: Kevin Mcvey,Planner: MATTHEW CANFIELD,Planner: MATTHEW CANFIELD,Planner: MICHAEL GILL,Planner: MICHAEL GILL,Planner: Richard Helle,Planner: Richard Helle,Planner: Stephen Colwell,Planner: Stephen Colwell | FINAL | 3964.4969 | 12177.615 | 2000.7438 | 9472.51 | 1353.1656 | 13761.785 | -1963.7531 | 647.5782 | 0.50467 | 1.4786 | 127940.4966 | 111784.6214 | 145679.7939 | -16155.8752 | -33895.1726 | 0.87372 | 0.76733 | 0.59309 | 145148.1671 | 201933.4633 | 33363.5457 | -56785.2962 | 77% | 100.4% | 145018.4131 | 203636.7497 | 189159.7861 | 195443.8109 | 0.41754 | 0.1036 |  |  | 0.59309 | -56785.2962 |  | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | ESSM | 0ERI | ESSM Blk 2 TTFRP | 29 | Internal |  |  |  | Steady | Active | Finance: Edward Pajor,Finance: Edward Pajor,Finance: JOHN FARUOLO,Finance: JOHN FARUOLO,Finance: Jordan McCombs,Finance: Jordan McCombs,PM: Christopher Driscoll,PM: Christopher Driscoll,PM: Dianna Patterson-Williams,PM: Dianna Patterson-Williams,PM: JOHN FARUOLO,PM: JOHN FARUOLO,PM: Jennifer Richardson,PM: Jennifer Richardson,Planner: Brett Muxen,Planner: Brett Muxen,Planner: Kristen Marcum,Planner: Kristen Marcum,Planner: Kristin Jiroudek,Planner: Kristin Jiroudek,Planner: Seth Van Norman,Planner: Seth Van Norman | FINAL | 1251.6015 | 3618.48 | 991.8382 | 5843.879 | 506.7913 | 2127.597 | -259.7633 | 485.0469 | 0.79246 | 1.9571 | 4143.9609 | 3720.6236 | 3155.684 | -423.3373 | 564.9397 | 0.89784 | 1.179 | 1.0066 | 32118.1717 | 31366.99 | 28397.548 | 751.1817 | 12% | 9.825% | 32118.1717 | 31889.9494 | 27241.3471 | 29981.8443 | 0.98214 | - |  |  | 1.0066 |  |  | TCPI 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | RAM | 0EQ5 | RAM GMRP TTP | 49 | DoD - Production and Deployment - LRIP |  |  |  | Steady | Active | PM: William Parten,PM: William Parten,Planner: CHARLES KENNA,Planner: CHARLES KENNA,Planner: Kristin Jiroudek,Planner: Kristin Jiroudek,Planner: Malinda Seagraves,Planner: Malinda Seagraves,Planner: Seth Van Norman,Planner: Seth Van Norman | FINAL | 522.1154 | 2338 | 1286.8908 | 1938.048 | 124.4338 | 1571.536 | 764.7754 | 1162.457 | 2.4648 | 10.342 | 4279.2523 | 3923.1621 | 2436.446 | -356.0903 | 1486.716 | 0.91679 | 1.6102 | 1.0832 | 31992.9043 | 28349.3187 | 28069.7422 | 3643.5856 | 12% | 7.616% | 31992.9063 | 28929.2651 | 19868.9178 | 21451.196 | 0.52 | 0.33333 |  |  | 1.0832 | 3643.5856 |  | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Land Warfare & Air Defense | COOPERATIVE AREA PROTECTION SYSTEMS | 0EPE | Stunner Backup DSWS BLK III | 35 | Development |  |  |  | Steady | Active | Finance: Cynthia Valencia,Finance: Cynthia Valencia,PM: ANDREW KINGRY,PM: ANDREW KINGRY,PM: TYLER KRONE,PM: TYLER KRONE,Planner: Janet Sword,Planner: Janet Sword,Planner: Seth Van Norman,Planner: Seth Van Norman | PRELIMINARY | 1345.3783 | 6275.76 | 673.9434 | 1765.465 | 1762.7108 | 7370.011 | -671.435 | -1088.7674 | 0.50093 | 0.38233 | 32041.0113 | 16576.0354 | 32235.4568 | -15464.9759 | -15659.4214 | 0.51734 | 0.51422 | 2.2551 | 44362.9438 | 44557.3893 | 27786.9084 | -194.4455 | 37% | 72.66% | 28233.7671 | 42008.4661 | 86272.7259 | 136687.9816 | 0.81625 | 0.55
| Air Power | AMRAAM | 0EOV | Lot 31 TE Phase II | 51 | Production |  |  |  | Steady | Active | Finance: Aaron Olson,Finance: Aaron Olson,Finance: Charles Campbell,Finance: Charles Campbell,Finance: Cheryl Biagini,Finance: Cheryl Biagini,Finance: Maribel Baltier,Finance: Maribel Baltier,Finance: Michael Good,Finance: Michael Good,Finance: Sergio Gonzales,Finance: Sergio Gonzales,Finance: Susana Williams,Finance: Susana Williams,PM: Aaron Olson,PM: Aaron Olson,PM: Carlo Pedrazzini,PM: Carlo Pedrazzini,PM: Charles Campbell,PM: Charles Campbell,PM: Cheryl Biagini,PM: Cheryl Biagini,PM: Jesus Velazquez,PM: Jesus Velazquez,PM: Luis Narvaez,PM: Luis Narvaez,PM: Maribel Baltier,PM: Maribel Baltier,PM: Michael Good,PM: Michael Good,PM: Sergio Gonzales,PM: Sergio Gonzales,PM: Susana Williams,PM: Susana Williams,Planner: Carlo Pedrazzini,Planner: Carlo Pedrazzini,Planner: Charles Campbell,Planner: Charles Campbell,Planner: Cheryl Biagini,Planner: Cheryl Biagini,Planner: Evan LAGUNA,Planner: Evan LAGUNA,Planner: Justin Tyner,Planner: Justin Tyner,Planner: Maribel Baltier,Planner: Maribel Baltier,Planner: Sarah Morris,Planner: Sarah Morris,Planner: Sergio Gonzales,Planner: Sergio Gonzales,Planner: Seth Van Norman,Planner: Seth Van Norman,Planner: Susana Williams,Planner: Susana Williams | FINAL | 1281.5713 | 2568.6 | 1031.9294 | 6515.992 | 1051.0168 | 4681.762 | -249.6419 | -19.0874 | 0.80521 | 0.98184 | 21940.2221 | 17648.2127 | 18710.35 | -4292.0095 | -1062.1374 | 0.80438 | 0.94323 | 1.2374 | 42855.2948 | 39081.2299 | 25207.0821 | 3774.0649 | 41% | 43.66% | 43304.0527 | 39451.5677 | 45434.4914 | 51933.7483 | 0.60481 | 0.3 | 0.80521 |  |  |  |  | MTD SPI 5 month average is less than ITD SPI.
| Naval Power | MALD | 0EHW | MALD Navy TMRR and EMD | 23 | Development |  |  |  | Steady | Active | Finance: COREY LANE,Finance: COREY LANE,PM: Ryan Glass,PM: Ryan Glass,Planner: CARLA EGURROLA,Planner: CARLA EGURROLA,Planner: Daniel Duran,Planner: Daniel Duran,Planner: Florence Iyer,Planner: Florence Iyer,Planner: Mark Lew,Planner: Mark Lew,Planner: Michael Gadigian,Planner: Michael Gadigian | FINAL | 2521.7914 | 10574.66 | 2213.7364 | 9302.102 | 3880.1505 | 13935.258 | -308.055 | -1666.4141 | 0.87784 | 0.57053 | 180743.051 | 174615.9716 | 190645.7003 | -6127.0795 | -16029.7287 | 0.9661 | 0.91592 | 0.93849 | 199092.8167 | 216726.9183 | 24476.8452 | -17634.1016 | 88% | 95.76% | 199044.0269 | 212452.4659 | 217369.5174 | 218307.2263 | 0.8487 | 0.27586 |  | 0.57053 |  | -17634.1016 | 0 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 616F | RDC FY20 TO4 | 5 | Development |  |  |  | Steady | Active | Finance: Carrie Schoenholtz,Finance: Carrie Schoenholtz,Finance: David Rourke,Finance: David Rourke,Finance: Jeffrey Lewitzky,Finance: Jeffrey Lewitzky,Finance: Michael Gormley,Finance: Michael Gormley,Finance: Michael Leschinski,Finance: Michael Leschinski,Finance: Stephen Kim,Finance: Stephen Kim,Finance: TIMOTHY HEPWORTH,Finance: TIMOTHY HEPWORTH,PM: CAITLIN MEDEIROS,PM: CAITLIN MEDEIROS,PM: David Rourke,PM: David Rourke,PM: Erin Scheaffer,PM: Erin Scheaffer,PM: Jeffrey Lewitzky,PM: Jeffrey Lewitzky,PM: TYLER STRATTON,PM: TYLER STRATTON,Planner: Paul Bonin,Planner: Paul Bonin,Planner: Timothy Parella,Planner: Timothy Parella | FINAL | 984.9066 | 5279.59 | 997.209 | 5279.862 | 1001.6849 | 5689.197 | 12.3024 | -4.476 | 1.0125 | 0.99553 | 99685.46 | 95633.7217 | 92675.5275 | -4051.7383 | 2958.1943 | 0.95935 | 1.0319 | 0.90853 | 117588.3343 | 116840.5714 | 21954.6126 | 747.7629 | 81% | 78.81% | 117553.2378 | 116725.8678 | 113951.028 | 114852.4126 | 0.93588 | 0.26923 | 1.0125 | 0.99553 | 0.90853 | 747.7629 | 2946672 | Engage Immediately. MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Air Power | COMMAND AND CONTROL | 61BM | Qatar AOC Upgrade Reportable | 0 | Development |  |  |  | Steady | Active | Finance: ERIN LEONARD,Finance: ERIN LEONARD,Finance: JOHN PANETTA,Finance: JOHN PANETTA,Finance: TIFFANY O'KEEFE,Finance: TIFFANY O'KEEFE,PM: GRACIELA Amundsen,PM: GRACIELA Amundsen,PM: Glenn Ouyang,PM: Glenn Ouyang,Planner: CHRISTINA CORACCIO,Planner: CHRISTINA CORACCIO,Planner: David Lafleur,Planner: David Lafleur,Planner: Jackie Hollandsworth,Planner: Jackie Hollandsworth,Planner: KEVIN CRAIG,Planner: KEVIN CRAIG,Planner: TIM MCCORMICK,Planner: TIM MCCORMICK,Planner: William Marcley,Planner: William Marcley | FINAL | 2747.2162 | 8627.82 | 3140.8438 | 9812.554 | 2704.3769 | 10840.4 | 393.6275 | 436.4669 | 1.1433 | 1.1614 | 51599.2924 | 46923.0853 | 42189.707 | -4676.2071 | 4733.3784 | 0.90937 | 1.1122 | 0.84947 | 66373.4536 | 65086.8841 | 19450.3682 | 1286.5695 | 71% | 63.56% | 66037.0922 | 67255.5877 | 59678.0143 | 61420.844 | 0.90955 | 0.6 | 1.1433 |  | 0.84947 |  | 2545478.31 | MTD SPI 5 month average is less than ITD SPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | INTEGRATED MISSION SYSTEMS | 615I | Polar Security Cutter | 3 | Production |  |  |  | Steady | Active | PM: Daniel Salazar,PM: Daniel Salazar,Planner: Aidan Lehrer,Planner: Aidan Lehrer,Planner: Anaizat Hereim,Planner: Anaizat Hereim,Planner: Anthony Muhl,Planner: Anthony Muhl,Planner: David Ponte,Planner: David Ponte,Planner: Deborah Fowler,Planner: Deborah Fowler,Planner: Minh Luong,Planner: Minh Luong,Planner: ROBERT GALLIGANI,Planner: ROBERT GALLIGANI,Planner: Richard Helle,Planner: Richard Helle | FINAL | 650.7463 | 3255.39 | 725.7479 | 3633.389 | 862.4342 | 4885.707 | 75.0016 | -136.6863 | 1.1153 | 0.84151 | 26788.1989 | 22782.4435 | 23448.8723 | -4005.7554 | -666.4288 | 0.85047 | 0.97158 | 1.144 | 41665.6373 | 39954.7747 | 18883.1938 | 1710.8626 | 55% | 56.28% | 41540.3699 | 40286.5775 | 42884.4345 | 46301.7198 | 0.74745 | 0.2 | 1.1153 | 0.84151 | 1.144 | 1710.8626 | 143356 | Engage Immediately. MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | UNDERSEA SYSTEMS (LEGACY) | 617M | LCS VDS Production 5001 6001 8001 | 8 | Development |  |  |  | Steady | Active | PM: Yin-Yu Chen,PM: Yin-Yu Chen,Planner: Geoffrey Johnson,Planner: Geoffrey Johnson,Planner: Kevin Mcvey,Planner: Kevin Mcvey,Planner: Richard Helle,Planner: Richard Helle | PRELIMINARY | 335.6327 | 1062.11 | 968.4365 | -100.242 | -914.1339 | 9255.336 | 632.8039 | 1882.5704 | 2.8854 | -1.0594 | 50122.0693 | 33329.2397 | 43717.11 | -16792.8296 | -10387.8703 | 0.66496 | 0.76238 | 0.74277 | 51186.5882 | 67758.7994 | 17857.3485 | -16572.2112 | 65% | 85.41% | 51186.5882 | 59814.1606 | 67140.1367 | 78941.753 | 0.43116 | 0.098765 |  | -1.0594 | 0.74277 | -16572.2112 | 664962 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Advanced Technology | AMS: ADV PROGRAMS | 0ERO | FUTURE HYPERSONICS PROJECT PHASE 1 | 15 | Internal |  |  |  | Steady |  | Finance: BENJAMIN JAEDECKE,Finance: BENJAMIN JAEDECKE,PM: Bryan Postal,PM: Bryan Postal,PM: Matthew Franklin,PM: Matthew Franklin,Planner: Lisa SILVA,Planner: Lisa SILVA,Planner: Seth Van Norman,Planner: Seth Van Norman | PRELIMINARY | 2891.843 | 12485.52 | 2344.8819 | 9376.909 | 2956.4044 | 13210.182 | -546.9611 | -611.5225 | 0.81086 | 0.79315 | 11321.2163 | 9729.6887 | 14712.6954 | -1591.5276 | -4983.0067 | 0.85942 | 0.66131 | 1.1117 | 25407.2105 | 28815.3797 | 15677.5218 | -3408.1692 | 38% | 57.91% | 18085.9813 | 23001.5662 | 38419.3739 | 42297.1787 | 0.51402 | -
| Naval Power | TOMAHAWK | 0EKC | AGR5 | 47 | Development |  |  |  | Deteriorating | Active | Finance: David Ozaeta,Finance: David Ozaeta,PM: Amber Stadler,PM: Amber Stadler,PM: Erin St. Germain,PM: Erin St. Germain,PM: Juliette Haggh,PM: Juliette Haggh,Planner: Amber Stadler,Planner: Amber Stadler,Planner: Erin St. Germain,Planner: Erin St. Germain,Planner: Michael Garcia,Planner: Michael Garcia | FINAL | 832.5386 | 1520.9 | 740.0078 | 1553.839 | 1400.8996 | 2452.313 | -92.5307 | -660.8917 | 0.88886 | 0.52824 | 34619.8026 | 33777.3893 | 35237.9344 | -842.4133 | -1460.545 | 0.97567 | 0.95855 | 1.042 | 49335.2429 | 50168.4337 | 15557.8536 | -833.1907 | 68% | 71.43% | 49335.2563 | 50015.8105 | 51468.5145 | 51873.3077 | 0.8913 | 0.22222 | 0.88886 | 0.52824 | 1.042 | -833.1907 | 519056.45 | Engage Immediately. MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Advanced Technology | AMS: ADV PROGRAMS | 61F9 | ONR EMPIRE | 36 | Development |  |  |  | Steady | Active | PM: Joanne Attridge,PM: Joanne Attridge,Planner: CARI GHAREEB,Planner: CARI GHAREEB,Planner: Judith Kopeloff,Planner: Judith Kopeloff | FINAL | 477.4244 | 2696.8 | 266.9094 | 1505.839 | 265.3968 | 1507.376 | -210.5151 | 1.5125 | 0.55906 | 1.0057 | 1516.1779 | 992.8828 | 935.8488 | -523.2951 | 57.034 | 0.65486 | 1.0609 | 1.053 | 15232.2844 | 14458.6613 | 14239.4016 | 773.6231 | 7% | 6.144% | 15166.9157 | 14515.2251 | 14357.2989 | 21431.023 | 0.4 | 0.33333
| Naval Power | SM-2 | 0EGY | SM2 Block IIIC EMD V1005090 | 46 | Development |  |  |  | Steady | Active | Finance: David Devery,Finance: David Devery,Finance: Miranda Romero,Finance: Miranda Romero,PM: Aszetta Jordan,PM: Aszetta Jordan,PM: Eric Witherspoon,PM: Eric Witherspoon,PM: Lindy Cote,PM: Lindy Cote,PM: Paul Strangio,PM: Paul Strangio,Planner: Charles Green,Planner: Charles Green,Planner: Kristin Jiroudek,Planner: Kristin Jiroudek | FINAL | 1583.4923 | 8503.42 | 1432.471 | 7837.053 | 1400.5084 | 7934.069 | -151.0213 | 31.9626 | 0.90463 | 1.0228 | 130106.6384 | 128151.5488 | 142681.9577 | -1955.0896 | -14530.4089 | 0.98497 | 0.89816 | 1.5927 | 141577.839 | 151111.6052 | 13426.2902 | -9533.7662 | 91% | 100.8% | 141450.5117 | 151378.2835 | 157630.5821 | 157858.6394 | 0.98517 | 0.28571 |  |  |  | -9533.7662 |  | VAC 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | AIM-9X | 0E4C | AIM 9X System Improvement Program III | 65 | Development |  |  |  | Steady | Active | Finance: Bradley Miller,Finance: Bradley Miller,PM: Anthony Jinks,PM: Anthony Jinks,PM: Mary Alice Kelly,PM: Mary Alice Kelly,Planner: Bruce Mcdaniel,Planner: Bruce Mcdaniel,Planner: Florence Iyer,Planner: Florence Iyer,Planner: Lawrence Brown,Planner: Lawrence Brown,Planner: Lisa Sparks,Planner: Lisa Sparks,Planner: MIGUEL GUZMAN,Planner: MIGUEL GUZMAN | FINAL | 692.0841 | 2885.46 | 1311.6617 | 5334.233 | 2059.0231 | 9703.801 | 619.5776 | -747.3614 | 1.8952 | 0.63703 | 270483.6775 | 268692.512 | 288078.7057 | -1791.1655 | -19386.1937 | 0.99338 | 0.93271 | 0.98494 | 281841.688 | 301429.0016 | 13149.176 | -19587.3136 | 95% | 102.2% | 281757.4698 | 301147.4325 | 302176.5962 | 302270.5759 | 0.98307 | 0.52632 |  | 0.63703 |  | -19587.3136 | 21735355.16 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 613D | RDC ANTPY2 TO3 | 8 | Development |  |  |  | Steady | Active | Finance: Carrie Schoenholtz,Finance: Carrie Schoenholtz,Finance: David Rourke,Finance: David Rourke,Finance: Jeffrey Lewitzky,Finance: Jeffrey Lewitzky,Finance: Michael Gormley,Finance: Michael Gormley,Finance: Michael Leschinski,Finance: Michael Leschinski,Finance: Stephen Kim,Finance: Stephen Kim,Finance: TIMOTHY HEPWORTH,Finance: TIMOTHY HEPWORTH,Finance: Yan Ye,Finance: Yan Ye,PM: CAITLIN MEDEIROS,PM: CAITLIN MEDEIROS,PM: David Rourke,PM: David Rourke,PM: Jeffrey Lewitzky,PM: Jeffrey Lewitzky,PM: TYLER STRATTON,PM: TYLER STRATTON,Planner: CHARLES KENNA,Planner: CHARLES KENNA,Planner: Paul Bonin,Planner: Paul Bonin,Planner: Timothy Parella,Planner: Timothy Parella | FINAL | 1628.7844 | 10187.79 | 844.8972 | 4426.98 | 1175.0781 | 6896.244 | -783.8872 | -330.1809 | 0.51873 | 0.71901 | 61966.6626 | 57943.7338 | 60602.5843 | -4022.9288 | -2658.8505 | 0.93508 | 0.95613 | 0.88679 | 71062.3326 | 75395.996 | 13118.5988 | -4333.6635 | 82% | 85.28% | 71062.3345 | 75359.8519 | 74323.1532 | 75275.7475 | 0.68406 | 0.14423 | 0.51873 | 0.71901 |  | -4333.6635 | 1983285 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | EXCALIBUR | 0EO7 | HTK Rapid Demonstration | 14 | Development |  |  |  | Steady | Active | PM: JUAN BLANCO,PM: JUAN BLANCO,PM: James Thouin,PM: James Thouin,PM: Jennifer Ashley Downs,PM: Jennifer Ashley Downs,Planner: CRISTAL TUCKER,Planner: CRISTAL TUCKER,Planner: Heather Pederson,Planner: Heather Pederson,Planner: John Cooper,Planner: John Cooper,Planner: Pamela Blackowiak,Planner: Pamela Blackowiak,Planner: Susan Dickens,Planner: Susan Dickens | FINAL | 3946.2223 | 16312.28 | 2917.2021 | 12520.339 | 3688.4738 | 19033.756 | -1029.0202 | -771.2717 | 0.73924 | 0.7909 | 38767.7279 | 32161.4082 | 38022.5453 | -6606.3196 | -5861.137 | 0.82959 | 0.84585 | 2.0162 | 44810.5493 | 44296.4079 | 12649.1411 | 514.1414 | 72% | 84.85% | 43713.1759 | 34353.7441 | 52976.8823 | 56048.6735 | 0.77419 | 0.24051 |  | 0.7909 |  |  | 316364 | MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | TAIWAN PROGRAMS | 615V | PRAE | 36 | Development |  |  |  | Deteriorating | Active | Finance: KENNETH OLISKY,Finance: KENNETH OLISKY,Finance: Michelle RACHAL,Finance: Michelle RACHAL,Finance: NICHOLAS BURKE,Finance: NICHOLAS BURKE,PM: BRIAN RICKS,PM: BRIAN RICKS,Planner: Anna Davydan,Planner: Anna Davydan,Planner: MATTHEW RONDEAU,Planner: MATTHEW RONDEAU,Planner: Meghan CARTER,Planner: Meghan CARTER,Planner: Prashant Navkal,Planner: Prashant Navkal | FINAL | 490.9981 | 2379.37 | 180.2425 | 867.07 | 149.0059 | 810.975 | -310.7555 | 31.2366 | 0.36709 | 1.2096 | 13888.1165 | 13269.9753 | 9604.9708 | -618.1413 | 3665.0045 | 0.95549 | 1.3816 | 0.98374 | 24763.6364 | 21288.5798 | 11493.6612 | 3475.0566 | 54% | 38.79% | 24763.6364 | 21288.5798 | 17924.2237 | 18311.7507 | - | - | 0.36709 |  | 0.98374 | 3475.0566 |  | MTD SPI 5 month average is less than ITD SPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. | On Quarterly EV cycle - data potentially skewed
| Land Warfare & Air Defense | EUCOM PROGRAMS | 6185 | Sweden TA | 59 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: JESSICA KING CERNIGLIA,Finance: JESSICA KING CERNIGLIA,PM: David Belliveau,PM: David Belliveau,PM: JESSICA KING CERNIGLIA,PM: JESSICA KING CERNIGLIA,PM: Julie Praino,PM: Julie Praino,Planner: Brian Martinez,Planner: Brian Martinez,Planner: JESSICA KING CERNIGLIA,Planner: JESSICA KING CERNIGLIA | FINAL | 166.3693 | 649.54 | 200.4844 | 595.16 | 124.3159 | 327.622 | 34.1151 | 76.1685 | 1.2051 | 1.6127 | 5062.0973 | 4296.7617 | 2672.0814 | -765.3356 | 1624.6803 | 0.84881 | 1.608 | 1.0773 | 15307.8228 | 12892.8953 | 11011.061 | 2414.9274 | 28% | 17.46% | 15307.8228 | 12966.7783 | 9519.6688 | 10739.3553 | - | - | 1.2051 | 1.6127 | 1.0773 | 2414.9274 |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | ANS | 6197 | DBR J1 PIO Spares | 46 | Production |  |  |  | Deteriorating | Active | Finance: Holly Johnson,Finance: Holly Johnson,Finance: Ralph Ungaro,Finance: Ralph Ungaro,PM: Dale Wainwright,PM: Dale Wainwright,PM: Kim Rohwer,PM: Kim Rohwer,Planner: Colin Faherty,Planner: Colin Faherty,Planner: SHEA BARRON,Planner: SHEA BARRON,Planner: Surya Achalla,Planner: Surya Achalla | FINAL | 413.127 | 1487.39 | -853.9138 | -6486.282 | 203.4451 | 488.048 | -1267.0409 | -1057.3589 | -2.067 | -4.1973 | 5074.1891 | 3744.9362 | 4129.0299 | -1329.2529 | -384.0937 | 0.73804 | 0.90698 | 1.1714 | 14441.7102 | 13260.9035 | 10696.774 | 1180.8067 | 26% | 28.59% | 14383.8742 | 13383.6311 | 15922.9024 | 20109.099 | - | - | -2.067 | -4.1973 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Internal - Other | ENGR: ENG PROJECTS | 0EP3 | Ultra 1x | 24 | DoD - Engineering Manufacturing and Development |  |  |  | Deteriorating | Active | Finance: Laura Dominick,Finance: Laura Dominick,PM: Glenn Davis,PM: Glenn Davis,Planner: AMY JOYCE,Planner: AMY JOYCE,Planner: Jason Jankowski,Planner: Jason Jankowski | FINAL | 1382.4962 | 8291.0119 | 1958.5939 | 3867.4998 | 2095.7162 | 4773.492 | 576.0977 | -137.1223 | 1.4167 | 0.93457 | 77679.2316 | 70408.4924 | 71742.9242 | -7270.7393 | -1334.4318 | 0.9064 | 0.9814 | 0.85401 | 80845.6374 | 83964.2243 | 10437.145 | -3118.5869 | 87% | 88.74% | 80529.4734 | 85099.9078 | 82377.8814 | 83476.1012 | 0.78544 | 0.4375 | 1.4167 | 0.93457 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Land Warfare & Air Defense | AREA DEFENSE SYSTEMS | 61DD | Sentinal IFF Norway Upgrade | 41 | Production |  |  |  | Deteriorating | Active | Finance: Joseph Ferrara,Finance: Joseph Ferrara,PM: Russell Cook,PM: Russell Cook,Planner: Robert Bakke,Planner: Robert Bakke,Planner: TIMOTHY REHFELDT,Planner: TIMOTHY REHFELDT | FINAL | 456.9732 | 964.58 | 268.3094 | 926.052 | 235.0893 | 714.066 | -188.6638 | 33.2201 | 0.58714 | 1.1413 | 4106.0036 | 3665.931 | 3018.8822 | -440.0725 | 647.0489 | 0.89282 | 1.2143 | 0.97595 | 13228.4534 | 12817.0965 | 9562.5223 | 411.3568 | 28% | 22.82% | 13228.4534 | 12856.7488 | 10893.5879 | 11838.898 | 0.94286 | - | 0.58714 | 1.1413 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Naval Power | UNDERSEA SYSTEMS (LEGACY) | 612B | ALFS FY19 Spare STRs DOD and FMS | 7 | Production |  |  |  | Deteriorating | Active | Finance: Mark Purcell,Finance: Mark Purcell,Finance: Stephen Esares,Finance: Stephen Esares,PM: Susan Romano,PM: Susan Romano,Planner: David Ponte,Planner: David Ponte,Planner: Mark Purcell,Planner: Mark Purcell,Planner: Richard Todd,Planner: Richard Todd | FINAL | 728.5457 | 1563.58 | 167.3419 | 884.29 | 141.0391 | 826.247 | -561.2037 | 26.3028 | 0.22969 | 1.1865 | 16671.9424 | 14111.7384 | 11246.9738 | -2560.204 | 2864.7647 | 0.84644 | 1.2547 | 1.465 | 23502.0021 | 17656.6412 | 9390.2636 | 5845.3609 | 60% | 47.86% | 23502.0021 | 18162.2554 | 18730.9595 | 20088.732 | 0.19355 | - | 0.22969 |  |  |  |  | MTD SPI 5 month average is less than ITD SPI.
| Strategic Missile Defense | SM3 IB | 0EQA | SM3 HAWK Period 0 | -3 | Internal |  |  |  | Steady | Active | PM: Marc Lee,PM: Marc Lee,PM: Michael Kalina,PM: Michael Kalina,PM: Michael Van Fleet,PM: Michael Van Fleet,Planner: Erik Hammer,Planner: Erik Hammer,Planner: JULIE SHARPLESS,Planner: JULIE SHARPLESS,Planner: Marilyn Buckelew,Planner: Marilyn Buckelew,Planner: Seth Van Norman,Planner: Seth Van Norman,Planner: VIRGINIA WILKINSON,Planner: VIRGINIA WILKINSON,Planner: ZACHARY SHAW,Planner: ZACHARY SHAW | FINAL | 2835.0436 | 15069.7 | 2494.4021 | 13232.14 | 2762.5424 | 14108.515 | -340.6415 | -268.1403 | 0.87985 | 0.90294 | 8144.4686 | 7468.4789 | 7412.4671 | -675.9897 | 56.0118 | 0.917 | 1.0076 | 0.85887 | 16340.8572 | 17742.7983 | 8872.3783 | -1401.941 | 46% | 45.36% | 16210.5147 | 15088.0439 | 16218.3046 | 17015.3418 | 0.87826 | 0.67442 |  |  | 0.85887 |  |  | TCPI 5 month average is less than the furthest month in the 5 month forecast.
| Land Warfare & Air Defense | AREA DEFENSE SYSTEMS | 619U | KBAR | 2 | Development |  |  |  | Steady | Active | Finance: Christopher Butler,Finance: Christopher Butler,Finance: JOSEPH CHIARELLI,Finance: JOSEPH CHIARELLI,Finance: Jonathan Rutups,Finance: Jonathan Rutups,Finance: Shane Isacco,Finance: Shane Isacco,PM: Andrew Lloyd,PM: Andrew Lloyd,PM: Greg Callison,PM: Greg Callison,Planner: Yoreida Andrieu,Planner: Yoreida Andrieu | FINAL | 572.66 | 3263.5 | 590.2123 | 3361.872 | 1909.7197 | 6139.589 | 17.5523 | -1319.5074 | 1.0307 | 0.30906 | 46606.5307 | 39136.2022 | 46094.934 | -7470.3285 | -6958.7318 | 0.83971 | 0.84903 | 7.026 | 47846.2049 | 47334.6082 | 8710.0027 | 511.5967 | 82% | 96.34% | 47846.2049 | 45997.5485 | 56353.6453 | 58311.8308 | 0.95434 | 1 |  | 0.30906 |  | 511.5967 | 112792 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | TSIS | 61HP | ZUMWALT FY21 Spares | 28 | Internal |  |  |  | Steady | Active | PM: Mark Silveira,PM: Mark Silveira,Planner: Adam Genetti,Planner: Adam Genetti,Planner: Anthony Muhl,Planner: Anthony Muhl | FINAL | 98.8729 | 447.73 | 61.4612 | 349.6 | 26.3635 | 161.64 | -37.4117 | 35.0977 | 0.62162 | 2.3313 | 98.8729 | 61.4612 | 46.2128 | -37.4117 | 15.2484 | 0.62162 | 1.33 | 0.99588 | 8548.2766 | 8568.124 | 8486.8154 | -19.8474 | 1% | 0.5406% | 8548.2766 | 8568.124 | 6427.4674 | 10311.7686 | - | -
| Land Warfare & Air Defense | QATAR PROGRAMS | 60RL | Qatar TA NET Cost Type | 23 | Development |  |  |  | Steady | Active | Finance: LISA WALLACE,Finance: LISA WALLACE,PM: DAVID MCCORMICK,PM: DAVID MCCORMICK,PM: LADI KEHINDE,PM: LADI KEHINDE,Planner: Alvin Neff,Planner: Alvin Neff,Planner: Anna Davydan,Planner: Anna Davydan,Planner: Brian Martinez,Planner: Brian Martinez,Planner: Michael Jordan,Planner: Michael Jordan,Planner: SUSAN MAPLES,Planner: SUSAN MAPLES,Planner: Stephen Pike,Planner: Stephen Pike,Planner: TIM MCCORMICK,Planner: TIM MCCORMICK | FINAL | 1257.7968 | 3132.61 | 1034.4381 | 2820.268 | 569.7901 | 2037.309 | -223.3588 | 464.6479 | 0.82242 | 1.8155 | 38876.0413 | 36191.1847 | 29934.6987 | -2684.8567 | 6256.486 | 0.93094 | 1.209 | 0.84337 | 44648.5982 | 39962.8747 | 8457.4135 | 4685.7236 | 81% | 67.05% | 44648.5982 | 40717.9815 | 36930.0521 | 37449.005 | 0.96082 | 0.4 | 0.82242 | 1.8155 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Naval Power | P73 | 0EJ0 | KP TD7 | 34 | Development |  |  |  | Steady | Active | PM: George Ortiz,PM: George Ortiz,PM: Victor Arnold,PM: Victor Arnold,Planner: Ashlinn Gardner,Planner: Ashlinn Gardner,Planner: Bruce Mcdaniel,Planner: Bruce Mcdaniel,Planner: Daniel Duran,Planner: Daniel Duran,Planner: VIRGINIA WILKINSON,Planner: VIRGINIA WILKINSON | FINAL | 3314.904 | 16887.45 | 0 | 0 | 1226.611 | 6848.872 | -3314.904 | -1226.611 | 0 | 0 | 44334.2376 | 38586.287 | 40571.5957 | -5747.9505 | -1985.3087 | 0.87035 | 0.95107 | 1.1963 | 46984.6347 | 47591.9471 | 8398.3477 | -607.3124 | 82% | 86.35% | 46984.6347 | 47375.5842 | 49402.048 | 50717.4636 | 0.9527 | 0.53333 | 0 | 0 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Land Warfare & Air Defense | AREA DEFENSE SYSTEMS | 61EK | DE MSHORAD | 3 | Development |  |  |  | Steady | Active | PM: Anjani Baswa,PM: Anjani Baswa,PM: Terrance Lee,PM: Terrance Lee,Planner: Yoreida Andrieu,Planner: Yoreida Andrieu | FINAL | 726.9588 | 3931.75 | 968.9934 | 4121.593 | 1033.035 | 3387.378 | 242.0346 | -64.0416 | 1.3329 | 0.93801 | 12357.1606 | 10758.7412 | 10568.9339 | -1598.4194 | 189.8074 | 0.87065 | 1.018 | 1.1765 | 18904.2471 | 17492.6888 | 8145.5059 | 1411.5583 | 57% | 55.91% | 18904.2471 | 18014.8531 | 18570.7355 | 19759.5581 | 0.75652 | 0.73077 |  |  | 1.1765 |  |  | TCPI 5 month average is less than the furthest month in the 5 month forecast.
| Air Power | AMRAAM | 0EJQ | F3R Phase 5 | 15 | Development |  |  |  | Steady | Active | Finance: Clinton Feagins,Finance: Clinton Feagins,Finance: Isaac Albrecht,Finance: Isaac Albrecht,PM: Michael Vela,PM: Michael Vela,PM: Robert Bennett,PM: Robert Bennett,PM: Tracy Milburn,PM: Tracy Milburn,Planner: AMY JOYCE,Planner: AMY JOYCE,Planner: Andrew Uhlig,Planner: Andrew Uhlig,Planner: Angela Tankersley,Planner: Angela Tankersley,Planner: EMILY LETWAK,Planner: EMILY LETWAK,Planner: Kathryn Harris,Planner: Kathryn Harris,Planner: Susan Lansey,Planner: Susan Lansey,Planner: Tracy Milburn,Planner: Tracy Milburn | FINAL | 739.0489 | 3569.46 | 904.7831 | 4822.268 | 3725.0532 | 19935.845 | 165.7341 | -2820.2701 | 1.2243 | 0.24289 | 50263.6793 | 47488.079 | 103080.9007 | -2775.6003 | -55592.8217 | 0.94478 | 0.46069 | 0.35268 | 55098.8033 | 124660.3029 | 7610.7243 | -69561.4996 | 86% | 187.1% | 55252.9956 | 121815.9747 | 119601.2641 | 120566.8522 | 0.89601 | 0.64 |  | 0.24289 |  | -69561.4996 | 685924 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget. |  | 18090.6677 | 15489.6997 | 103080.9007 | -2600.9681 | -87591.2011 | 0.85623 | 0.15027
| Naval Power | TOMAHAWK | 0EIV | GTS Obsolescence | 5 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: Dustyn Holt,Finance: Dustyn Holt,PM: ABRAHAM ERHABOR,PM: ABRAHAM ERHABOR,PM: WILLIAM PAULEY,PM: WILLIAM PAULEY,Planner: Adam Bingle,Planner: Adam Bingle,Planner: James Watson,Planner: James Watson,Planner: Kaelin Butler,Planner: Kaelin Butler,Planner: Robert Miles,Planner: Robert Miles,Planner: Yesenia Ibarra,Planner: Yesenia Ibarra | FINAL | -1076.9362 | -3487.37 | 0 | 0 | 630.9975 | 2002.308 | 1076.9362 | -630.9975 | 0 | 0 | 9608.9918 | 8074.0309 | 10477.6159 | -1534.961 | -2403.5851 | 0.84026 | 0.7706 | 1.322 | 15084.8681 | 15780.7526 | 7010.8372 | -695.8845 | 54% | 69.46% | 14730.0488 | 15320.0838 | 19575.5326 | 21305.1454 | 0.93361 | 0.73913 | 0 | 0 |  |  | 331019 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | C2 OTHER | 61A3 | Jordan IFADS | 36 | Development |  |  |  | Steady | Active | PM: Stephen Bohan,PM: Stephen Bohan,Planner: Dale Principe,Planner: Dale Principe,Planner: Dayle DaSilva,Planner: Dayle DaSilva | FINAL | 1274.4428 | 1505.55 | 1059.3677 | 1766.313 | 402.9874 | 1561.399 | -215.0751 | 656.3803 | 0.83124 | 2.6288 | 19509.3685 | 18549.4247 | 17792.8034 | -959.9438 | 756.6213 | 0.9508 | 1.0425 | 1.0012 | 25403.6427 | 24638.935 | 6854.218 | 764.7077 | 73% | 70.04% | 25346.0941 | 24644.7626 | 24367.4414 | 24707.6829 | 0.9619 | 1 | 0.83124 | 2.6288 |  | 764.7077 | 125947 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | AIM-9X | 0EQP | ESAD Redesign | 36 | Production |  |  |  | Deteriorating | Active | PM: Alice Smith,PM: Alice Smith,Planner: Lawrence Brown,Planner: Lawrence Brown,Planner: Seth Van Norman,Planner: Seth Van Norman | PRELIMINARY | 160.8739 | 216.83 | 9.5784 | 52.35 | 15.2451 | 87.771 | -151.2955 | -5.6667 | 0.05954 | 0.62829 | 535.4895 | 389.5783 | 93.6552 | -145.9112 | 295.923 | 0.72752 | 4.1597 | 1.0698 | 6951.0149 | 6226.7083 | 6561.4366 | 724.3066 | 6% | 1.347% | 6951.0149 | 6376.2234 | 1671.0352 | 2261.8211 | 0.75 | - |  |  | 1.0698 |  | 0 | TCPI 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | NAVAL RADARS | 60GG | AEGIS FMS | 72 | Production |  |  |  | Steady | Active | Finance: JENNA GERBER,Finance: JENNA GERBER,Finance: JONATHAN BAZARIAN,Finance: JONATHAN BAZARIAN,Finance: Jason O'Neil,Finance: Jason O'Neil,PM: Brad Smith,PM: Brad Smith,PM: JENNA GERBER,PM: JENNA GERBER,PM: JONATHAN BAZARIAN,PM: JONATHAN BAZARIAN,PM: Jason O'Neil,PM: Jason O'Neil,PM: Joseph O'Brien,PM: Joseph O'Brien,Planner: JENNA GERBER,Planner: JENNA GERBER,Planner: Lawrence Bernabei,Planner: Lawrence Bernabei,Planner: Richard Todd,Planner: Richard Todd | FINAL | 258.7379 | 81.49 | 240.0114 | 1278.477 | 481.9255 | 1953.258 | -18.7265 | -241.9142 | 0.92762 | 0.49803 | 255677.2539 | 250614.3925 | 270230.5372 | -5062.8614 | -19616.1446 | 0.9802 | 0.92741 | 2.2369 | 257129.3392 | 273142.9701 | 6514.9467 | -16013.6308 | 97% | 105.1% | 257129.3392 | 272428.5351 | 277255.4232 | 277397.3385 | 0.9061 | - |  | 0.49803 |  | -16013.6308 | 0 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Air Power | PERSISTENT AND STRATEGIC SENSORS | 616N | BSU Analysis and Integration | 14 | Production |  |  |  | Deteriorating | Active | Finance: Christa Mixon,Finance: Christa Mixon,Finance: Emerson Laundis,Finance: Emerson Laundis,PM: CAROLINE JACOBSON,PM: CAROLINE JACOBSON,PM: JEREMY HURLEY,PM: JEREMY HURLEY,PM: Tracy Milburn,PM: Tracy Milburn,Planner: Bridget Harrod,Planner: Bridget Harrod,Planner: DAVID DEDONATO,Planner: DAVID DEDONATO,Planner: Jacqueline Walbourne,Planner: Jacqueline Walbourne,Planner: Jason Crane,Planner: Jason Crane,Planner: Paul Bonin,Planner: Paul Bonin,Planner: REEJA MATHEW,Planner: REEJA MATHEW,Planner: Ryan Driscoll,Planner: Ryan Driscoll,Planner: Sean Liddell,Planner: Sean Liddell,Planner: Tracy Milburn,Planner: Tracy Milburn | FINAL | 806.6552 | 1433.97 | 338.4824 | 1533.845 | 381.1841 | 1961.541 | -468.1728 | -42.7017 | 0.41961 | 0.88798 | 9972.0259 | 8881.8444 | 8307.8691 | -1090.1815 | 573.9753 | 0.89068 | 1.0691 | 1.0856 | 15284.1889 | 14205.4569 | 6402.3445 | 1078.732 | 58% | 54.36% | 15344.1338 | 14002.2126 | 14296.4722 | 15031.5294 | 0.79695 | 0.61538 | 0.41961 | 0.88798 |  | 1078.732 | 232084.27 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | MALD | 0EQN | Powered Launch Consideration CLIN | 19 | Development |  |  |  | Steady | Active | PM: Ryan Glass,PM: Ryan Glass,Planner: Florence Iyer,Planner: Florence Iyer,Planner: Michael Gadigian,Planner: Michael Gadigian,Planner: Seth Van Norman,Planner: Seth Van Norman | FINAL | 322.5996 | 1831.83 | 308.5773 | 1743.82 | 232.2431 | 1265.162 | -14.0223 | 76.3342 | 0.95653 | 1.3287 | 3366.0735 | 3049.3108 | 3128.6132 | -316.7627 | -79.3024 | 0.9059 | 0.97465 | 1.0394 | 8571.9835 | 8442.1132 | 5522.6727 | 129.8703 | 36% | 36.5% | 8540.7741 | 8470.8667 | 8794.9121 | 9383.5277 | 0.98305 | 0.8 |  |  | 1.0394 |  |  | TCPI 5 month average is less than the furthest month in the 5 month forecast.
| Land Warfare & Air Defense | CRDP | 0EPH | Autonomous Strike | 12 | Development |  |  |  | Steady | Active | PM: CHARLES STEVENS,PM: CHARLES STEVENS,Planner: Joaquin Casanova,Planner: Joaquin Casanova,Planner: Susan Dickens,Planner: Susan Dickens | FINAL | -814.1602 | 2680.356 | 1411.2629 | 3050.386 | 1167.9619 | 3458.16 | 2225.4231 | 243.3011 | -1.7334 | 1.2083 | 12946.2293 | 10874.602 | 11220.9518 | -2071.6273 | -346.3498 | 0.83998 | 0.96913 | 1.5603 | 16234.8166 | 14656.4074 | 5360.2145 | 1578.4092 | 67% | 69.12% | 15956.9318 | 12250.988 | 16751.8861 | 17805.5369 | 0.76163 | - | -1.7334 | 1.2083 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Naval Power | TOMAHAWK | 0EMH | FY20 TOMAHAWK CRUISE MISSILES RECERTIFICATION | 4 | Production |  |  |  | Steady | Active | Finance: Dustyn Holt,Finance: Dustyn Holt,Finance: JENNIFER DESHAZO,Finance: JENNIFER DESHAZO,PM: Desiree Vorel,PM: Desiree Vorel,PM: KELLY COVINGTON,PM: KELLY COVINGTON,PM: MAYA KEMPTON,PM: MAYA KEMPTON,PM: SAMUEL BREAN,PM: SAMUEL BREAN,PM: Sara THOMAS,PM: Sara THOMAS,Planner: David Rowe,Planner: David Rowe,Planner: MIGUEL GUZMAN,Planner: MIGUEL GUZMAN,Planner: Robert Miles,Planner: Robert Miles | FINAL | 25.9983 | 143.59 | 2760.5813 | 4890.418 | 2443.8504 | 3339.273 | 2734.5829 | 316.7309 | 106.1831 | 1.1296 | 60218.2479 | 54865.6499 | 58661.1945 | -5352.598 | -3795.5446 | 0.91111 | 0.9353 | 1.1864 | 60218.2479 | 63172.995 | 5352.598 | -2954.7471 | 91% | 97.41% | 60218.2479 | 62997.0545 | 64384.0793 | 64942.394 | 0.92857 | 0.3913 |  | 1.1296 |  | -2954.7471 | 51768 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | TOW | 0EP8 | TOS EVO | 9 | Development |  |  |  | Steady | Active | Finance: UMRAN CEPHANECIOGLU,Finance: UMRAN CEPHANECIOGLU,PM: David Edmondson,PM: David Edmondson,PM: Justin Bailes,PM: Justin Bailes,Planner: Pamela Blackowiak,Planner: Pamela Blackowiak | FINAL | 794.2841 | 3915.7 | 733.5315 | 3824.714 | 856.4531 | 4786.713 | -60.7527 | -122.9216 | 0.92351 | 0.85648 | 10046.1837 | 8244.801 | 8888.3577 | -1801.3826 | -643.5567 | 0.82069 | 0.9276 | 1.0768 | 13124.3887 | 13419.9351 | 4879.5876 | -295.5465 | 63% | 67.72% | 13496.5409 | 12205.8313 | 14148.8267 | 15298.1714 | 0.96154 | 0.81818 | 0.92351 | 0.85648 |  | -295.5465 |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | INTEGRATED MISSION SYSTEMS | 615G | MK30 ESSM Canisters UAE | 39 | Production |  |  |  | Steady | Active | Finance: Cynthia Gauvin,Finance: Cynthia Gauvin,PM: Fabrice Tefoung,PM: Fabrice Tefoung,PM: John Titmas,PM: John Titmas,Planner: Cynthia Gauvin,Planner: Cynthia Gauvin,Planner: Daniel Cardella,Planner: Daniel Cardella | PRELIMINARY | 19.04 | 89.8 | 23.7156 | 111.854 | 3530.0565 | 1039.176 | 4.6757 | -3506.3408 | 1.2456 | 0.0067182 | 14189.4216 | 9445.9363 | 11890.9628 | -4743.4852 | -2445.0265 | 0.6657 | 0.79438 | 0 | 14189.4216 | 11890.9628 | 4743.4852 | 2298.4587 | 67% | 83.8% | 14170.3816 | 8360.9064 | 17862.2721 | 20860.8967 | - | - | 1.2456 | 0.0067182 |  | 2298.4587 | 0 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | MRAD PROGRAMS | 61HF | SENTINEL UKRAINE F1 CONV | 59 | Internal |  |  |  | Steady | Active | Finance: Dillon Allen,Finance: Dillon Allen,Finance: Jonathan Adsit,Finance: Jonathan Adsit,Finance: Joseph Ferrara,Finance: Joseph Ferrara,PM: KATHY DESON,PM: KATHY DESON,Planner: Charles Barnes,Planner: Charles Barnes,Planner: Seth Van Norman,Planner: Seth Van Norman | FINAL | 145.4025 | 524.86 | 178.6167 | 644.54 | 161.4703 | 612.81 | 33.2142 | 17.1464 | 1.2284 | 1.1062 | 897.091 | 650.3837 | 610.9664 | -246.7073 | 39.4173 | 0.72499 | 1.0645 | 0.91235 | 5352.6922 | 5765.0397 | 4702.3086 | -412.3475 | 12% | 11.41% | 5998.8556 | 5696.6632 | 5028.2862 | 6703.8895 | 0.64706 | 0.625
| Naval Power | ESSM | 0DXW | ESSM EMD Phase | 49 | Development |  |  |  | Steady | Active | Finance: Jordan McCombs,Finance: Jordan McCombs,PM: Christopher Driscoll,PM: Christopher Driscoll,PM: David Bujak,PM: David Bujak,Planner: Andrea Huerta,Planner: Andrea Huerta,Planner: Charles Green,Planner: Charles Green,Planner: David Rutter,Planner: David Rutter,Planner: Fallyn VAN DER WIELE SPINA,Planner: Fallyn VAN DER WIELE SPINA,Planner: Jennifer Stein,Planner: Jennifer Stein,Planner: Kathryn LOWE,Planner: Kathryn LOWE,Planner: Rhoda Doan,Planner: Rhoda Doan,Planner: Sara Wilson,Planner: Sara Wilson | FINAL | 631.21 | 3391.64 | 574.7163 | 3105 | 64.3322 | 2699.056 | -56.4937 | 510.3842 | 0.9105 | 8.9336 | 497103.6749 | 495362.7595 | 547541.4809 | -1740.9154 | -52178.7214 | 0.9965 | 0.9047 | 0.78047 | 499800.8091 | 553227.8807 | 4438.0495 | -53427.0716 | 99% | 109.6% | 499800.8091 | 553657.9905 | 552447.0096 | 552464.2497 | 0.98886 | 0.5 | 0.9105 |  | 0.78047 |  |  | MTD SPI 5 month average is less than ITD SPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. |  | 105322.5383 | 104545.1746 | 156016.5855 | -777.3637 | -51471.4109 | 0.99262 | 0.67009
| Naval Power | INTEGRATED MISSION SYSTEMS | 61E1 | GPNTS Coast Guard TO2 | 28 | DoD - Operations and Support |  |  |  | Steady | Active | PM: Brett Balazs,PM: Brett Balazs,PM: Mazin Ghorab,PM: Mazin Ghorab,Planner: Anthony Muhl,Planner: Anthony Muhl,Planner: Christopher Shoup,Planner: Christopher Shoup,Planner: David Lafleur,Planner: David Lafleur | FINAL | 468.3994 | 1311.66 | 491.2648 | 1379.66 | 690.9321 | 2235.492 | 22.8654 | -199.6673 | 1.0488 | 0.71102 | 5273.1158 | 3818.7004 | 4143.7169 | -1454.4154 | -325.0165 | 0.72418 | 0.92156 | 1.0117 | 8131.6913 | 8406.9082 | 4312.9909 | -275.2169 | 47% | 50.96% | 8131.6913 | 8290.8284 | 8823.7943 | 10606.2794 | 0.8773 | - | 1.0488 | 0.71102 |  | -275.2169 | 0 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | ANS | 61AB | SMO LNU ULOG | 60 | Development |  |  |  | Steady | Active | Finance: Holly Johnson,Finance: Holly Johnson,PM: Dale Wainwright,PM: Dale Wainwright,PM: Kim Rohwer,PM: Kim Rohwer,Planner: Colin Faherty,Planner: Colin Faherty,Planner: David Ponte,Planner: David Ponte,Planner: Holly Johnson,Planner: Holly Johnson | FINAL | 292.2352 | 1072.488 | -65.1181 | 614.113 | -119.6802 | 581.495 | -357.3533 | 54.5621 | -0.22283 | 0.5441 | 7967.0207 | 5046.1663 | 4503.6229 | -2920.8544 | 542.5433 | 0.63338 | 1.1205 | 1.1675 | 9242.9175 | 8098.421 | 4196.7513 | 1144.4966 | 55% | 48.73% | 9242.9175 | 8630.7315 | 8249.1565 | 10417.1704 | 0.54023 | - |  | 0.5441 | 1.1675 | 1144.4966 |  | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | NAVAL RADARS | 61G4 | DBR DLA Spares DK0E | 62 | Internal |  |  |  | Steady | Active | PM: Dale Wainwright,PM: Dale Wainwright,PM: Kim Rohwer,PM: Kim Rohwer,Planner: Kim Rohwer,Planner: Kim Rohwer | FINAL | 90.9755 | 297.31 | 55.3387 | 265.1 | 17.9169 | 100.542 | -35.6369 | 37.4218 | 0.60828 | 3.0886 | 305.2256 | 149.8113 | 154.5075 | -155.4143 | -4.6962 | 0.49082 | 0.96961 | 1.0397 | 4221.3646 | 4070.6464 | 4071.5532 | 150.7181 | 4% | 3.66% | 4221.3646 | 4229.8474 | 4353.6935 | 8709.9309 | - | - |  |  | 1.0397 | 150.7181 |  | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | ANS | 619L | CAP Bank | 25 | Development |  |  |  | Deteriorating | Active | Finance: Holly Johnson,Finance: Holly Johnson,Finance: Ralph Ungaro,Finance: Ralph Ungaro,PM: Dale Wainwright,PM: Dale Wainwright,PM: Kim Rohwer,PM: Kim Rohwer,PM: Ralph Ungaro,PM: Ralph Ungaro,Planner: Colin Faherty,Planner: Colin Faherty,Planner: David Ponte,Planner: David Ponte,Planner: Holly Johnson,Planner: Holly Johnson,Planner: Ralph Ungaro,Planner: Ralph Ungaro,Planner: SHEA BARRON,Planner: SHEA BARRON | FINAL | 605.889 | 3564.94 | 378.1954 | 1948.294 | 233.7448 | 1224.705 | -227.6936 | 144.4506 | 0.6242 | 1.618 | 13982.7248 | 10904.5238 | 9053.5664 | -3078.201 | 1850.9574 | 0.77986 | 1.2044 | 2.6222 | 14360.1419 | 10371.4011 | 3455.6181 | 3988.7408 | 76% | 63.05% | 14360.1419 | 13343.5269 | 11922.6204 | 12732.516 | 0.81863 | - | 0.6242 | 1.618 | 2.6222 | 3988.7408 |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | RAM | 0ELB | RAM Block 2B | 57 | Development |  |  |  | Steady | Active | PM: Christopher Marr,PM: Christopher Marr,PM: Daniel Melonis,PM: Daniel Melonis,Planner: Erin St. Germain,Planner: Erin St. Germain,Planner: JOSE CARDOZA,Planner: JOSE CARDOZA | FINAL | 1004.94 | 5304.43 | 1069.2165 | 5248.85 | 1269.3533 | 6479.098 | 64.2765 | -200.1368 | 1.064 | 0.84233 | 74423.1665 | 73276.9928 | 78314.9856 | -1146.1736 | -5037.9928 | 0.9846 | 0.93567 | 1.3447 | 76581.2366 | 80772.2767 | 3304.2438 | -4191.0402 | 96% | 102.3% | 76581.2366 | 80634.1012 | 81846.4051 | 81901.6424 | 0.97802 | 0.78125 |  |  | 1.3447 | -4191.0402 |  | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Air Power | AMRAAM | 0ERQ | AMRAAM SECURE LOCKER | 23 | Internal |  |  |  | Steady | Active | PM: Floyd Cordisco,PM: Floyd Cordisco,PM: Michael Good,PM: Michael Good,Planner: Evan LAGUNA,Planner: Evan LAGUNA,Planner: Seth Van Norman,Planner: Seth Van Norman | FINAL | 70.5411 | 457.52 | 57.519 | 369.52 | 77.0148 | 491.921 | -13.0221 | -19.4958 | 0.8154 | 0.74686 | 70.5411 | 57.519 | 85.211 | -13.0221 | -27.692 | 0.8154 | 0.67502 | 1.0043 | 3120.063 | 3134.7329 | 3062.544 | -14.6699 | 2% | 2.731% | 3120.063 | 8.1962 | 4622.1895 | 5649.3448 | 0.5 | 1
| Land Warfare & Air Defense | PATRIOT SYSTEMS | 6186 | MIR 2020 | 35 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: Anthony Sinagra,Finance: Anthony Sinagra,Finance: Cesar Pellerano,Finance: Cesar Pellerano,Finance: Cheryl Gaudet,Finance: Cheryl Gaudet,Finance: DAVID LEE,Finance: DAVID LEE,PM: Cheryl Norsworthy,PM: Cheryl Norsworthy,PM: Raymond Villavicencio,PM: Raymond Villavicencio,Planner: Anthony Sinagra,Planner: Anthony Sinagra,Planner: Catherine Arno,Planner: Catherine Arno,Planner: MATTHEW CANFIELD,Planner: MATTHEW CANFIELD | FINAL | 279.3665 | 45.461 | 145.603 | 0.09 | 491.6453 | 1035.135 | -133.7635 | -346.0423 | 0.52119 | 0.29615 | 27031.7008 | 24264.8589 | 21714.1857 | -2766.8419 | 2550.6731 | 0.89764 | 1.1175 | 14.3037 | 27031.7008 | 21907.6209 | 2766.8419 | 5124.0799 | 90% | 80.33% | 27031.7008 | 21879.6534 | 24190.1828 | 24472.5126 | - | - | 0.52119 | 0.29615 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Land Warfare & Air Defense | PATRIOT SYSTEMS | 6172 | DMPE 22 | 25 | Production |  |  |  | Steady | Active | Finance: Cesar Pellerano,Finance: Cesar Pellerano,Finance: Cheryl Gaudet,Finance: Cheryl Gaudet,Finance: DAVID LEE,Finance: DAVID LEE,PM: Brian Tavares,PM: Brian Tavares,PM: Cheryl Norsworthy,PM: Cheryl Norsworthy,Planner: Alvin Neff,Planner: Alvin Neff,Planner: Cesar Pellerano,Planner: Cesar Pellerano,Planner: MATTHEW RONDEAU,Planner: MATTHEW RONDEAU,Planner: Michael Hoffman,Planner: Michael Hoffman | FINAL | 296.79 | 1564.512 | 532.7843 | 2887.651 | 600.8208 | 3148.908 | 235.9942 | -68.0366 | 1.7952 | 0.88676 | 21635.6765 | 20329.6984 | 18012.3785 | -1305.9782 | 2317.3199 | 0.93964 | 1.1287 | 0.96232 | 22936.1218 | 20720.8631 | 2606.4234 | 2215.2587 | 89% | 78.53% | 22936.1218 | 20799.2113 | 20321.7037 | 20470.0545 | 0.82299 | 1 |  | 0.88676 | 0.96232 | 2215.2587 | 131342.8 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Air Power | PERSISTENT AND STRATEGIC SENSORS | 6018 | Clear Cod UEWR | 119 | Development |  |  |  | Steady | Active | Finance: Emerson Laundis,Finance: Emerson Laundis,Finance: JEFFREY JABLONSKI,Finance: JEFFREY JABLONSKI,Finance: JOHN PANETTA,Finance: JOHN PANETTA,Finance: Ryan Haggerty,Finance: Ryan Haggerty,PM: JEREMY HURLEY,PM: JEREMY HURLEY,PM: Joseph DiGiovanni,PM: Joseph DiGiovanni,PM: Tommy Wong,PM: Tommy Wong,Planner: CALVIN LEE,Planner: CALVIN LEE,Planner: JACKIE RYAN,Planner: JACKIE RYAN,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Jacqueline Walbourne,Planner: Jacqueline Walbourne,Planner: Jason Iovanna,Planner: Jason Iovanna,Planner: REEJA MATHEW,Planner: REEJA MATHEW | FINAL | 618.2611 | 2344.97 | 780.9213 | 2285.573 | 1463.1215 | 4773.399 | 162.6602 | -682.2002 | 1.2631 | 0.53374 | 288736.5736 | 287045.2055 | 316613.0885 | -1691.368 | -29567.883 | 0.99414 | 0.90661 | 0.33787 | 289164.1715 | 322884.5413 | 2118.9659 | -33720.3698 | 99% | 109.5% | 289141.8534 | 322050.6757 | 318950.3244 | 318964.0962 | 0.95491 | 0.55556 |  |  | 0.33787 | -33720.3698 |  | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Land Warfare & Air Defense | TOW | 0END | TOS Qualification | 46 | Production |  |  |  | Steady | Active | Finance: UMRAN CEPHANECIOGLU,Finance: UMRAN CEPHANECIOGLU,PM: David Edmondson,PM: David Edmondson,PM: Justin Bailes,PM: Justin Bailes,Planner: Pamela Blackowiak,Planner: Pamela Blackowiak | FINAL | 345.874 | 1844.26 | 288.7499 | 1570.979 | 449.0193 | 2401.452 | -57.1241 | -160.2694 | 0.83484 | 0.64307 | 12600.0232 | 12217.3217 | 13316.1271 | -382.7016 | -1098.8054 | 0.96963 | 0.91748 | 1.4668 | 14279.0808 | 14721.7913 | 2061.7591 | -442.7105 | 86% | 93.26% | 14293.9886 | 16318.9206 | 15563.3173 | 15633.7094 | 0.9626 | 0.31818 |  | 0.64307 | 1.4668 | -442.7105 | 42748220 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Advanced Technology | AS: S&T PORTFOLIO | 61D4 | DARPA JAWS | 14 | Development |  |  |  | Steady | Active | PM: Brian Klobucher,PM: Brian Klobucher,Planner: Adam Genetti,Planner: Adam Genetti,Planner: CHRISTINA CORACCIO,Planner: CHRISTINA CORACCIO,Planner: David Lafleur,Planner: David Lafleur,Planner: Judith Kopeloff,Planner: Judith Kopeloff | FINAL | 640.321 | 1717.28 | 0 | 0 | 775.4632 | 2362.006 | -640.321 | -775.4632 | 0 | 0 | 8157.5909 | 7121.6491 | 7233.1917 | -1035.9418 | -111.5426 | 0.87301 | 0.98458 | 2.6504 | 9140.9791 | 7995.0891 | 2019.33 | 1145.8901 | 78% | 79.13% | 9140.9791 | 7799.4565 | 9284.1494 | 9582.4895 | - | - | 0 | 0 |  | 1145.8901 | 0 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | UNDERSEA SYSTEMS (LEGACY) | 612V | Gen2 Test Device FY19 | 37 | Production |  |  |  | Steady | Active | Finance: Linda Henderson,Finance: Linda Henderson,Finance: Mark Purcell,Finance: Mark Purcell,PM: Peter Lombardo,PM: Peter Lombardo,Planner: Kevin Mcvey,Planner: Kevin Mcvey,Planner: Richard Helle,Planner: Richard Helle | FINAL | 294.0862 | 1386.93 | 290.2504 | 853.071 | 289.6528 | 942.889 | -3.8359 | 0.59756 | 0.98696 | 1.0021 | 11204.4898 | 10694.1465 | 9411.6599 | -510.3432 | 1282.4866 | 0.95445 | 1.1363 | 1.4238 | 12666.7596 | 10797.1282 | 1972.6131 | 1869.6314 | 84% | 74.3% | 12666.7596 | 10949.4156 | 11147.709 | 11230.5563 | 0.14286 | - | 0.98696 | 1.0021 | 1.4238 |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | Naval Surface & Undersea Systems | 60ML | AMNS PRODUCTION 3 LOT 6305 CONTRACT | 2 | Production |  |  |  | Steady | Active | Finance: Karen Lariviere,Finance: Karen Lariviere,PM: David Chapman,PM: David Chapman,PM: JASMINKA Otton,PM: JASMINKA Otton,PM: James Hopkins,PM: James Hopkins,PM: Richard Adey,PM: Richard Adey,Planner: Anthony RUOTI,Planner: Anthony RUOTI,Planner: David Ponte,Planner: David Ponte,Planner: Deborah Fowler,Planner: Deborah Fowler,Planner: Deborah Fowler,Planner: Deborah Fowler,Planner: Divinia Maguire,Planner: Divinia Maguire,Planner: JACKIE RYAN,Planner: JACKIE RYAN,Planner: Kevin Mcvey,Planner: Kevin Mcvey,Planner: Richard Helle,Planner: Richard Helle | FINAL | 26.503 | 137.53 | 57.07 | 293.536 | -1088.2142 | 52.712 | 30.5669 | 1145.2841 | 2.1533 | -0.052444 | 26102.9328 | 24378.3582 | 21831.8871 | -1724.5746 | 2546.471 | 0.93393 | 1.1166 | 2.056 | 26139.9611 | 22688.6857 | 1761.6029 | 3451.2754 | 93% | 83.52% | 26139.9611 | 24931.2274 | 23409.4797 | 23521.0818 | 0.75527 | - |  | -0.052444 |  |  |  | MTD CPI 5 month average is less than ITD CPI.
| Naval Power | NAVAL RADARS | 61B2 | Aegis Korea Australia Spares | 3 | Production |  |  |  | Steady | Active | Finance: Holly Johnson,Finance: Holly Johnson,Finance: JACK LAHIFF,Finance: JACK LAHIFF,Finance: JONATHAN BAZARIAN,Finance: JONATHAN BAZARIAN,Finance: Jason O'Neil,Finance: Jason O'Neil,Finance: Katie Bittner,Finance: Katie Bittner,Finance: Matthew Logan,Finance: Matthew Logan,PM: Brad Smith,PM: Brad Smith,PM: Joseph O'Brien,PM: Joseph O'Brien,Planner: David Lafleur,Planner: David Lafleur,Planner: JENNA GERBER,Planner: JENNA GERBER,Planner: Lawrence Bernabei,Planner: Lawrence Bernabei,Planner: Richard Todd,Planner: Richard Todd | FINAL | 225.8532 | 1245.01 | 320.8704 | 1013.055 | 303.5779 | 1066.723 | 95.0172 | 17.2924 | 1.4207 | 1.057 | 9268.1027 | 8207.445 | 7581.6748 | -1060.6577 | 625.7703 | 0.88556 | 1.0825 | 1.0061 | 9938.826 | 9302.5925 | 1731.3809 | 636.2334 | 83% | 76.28% | 9938.826 | 9302.5925 | 9181.0479 | 9387.7367 | - | - | 1.4207 | 1.057 |  |  | 0 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Naval Power | NAVAL RADARS | 617T | AEGIS Japan Korea Spares | 0 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: JONATHAN BAZARIAN,Finance: JONATHAN BAZARIAN,Finance: Jason O'Neil,Finance: Jason O'Neil,Finance: Katie Bittner,Finance: Katie Bittner,PM: Brad Smith,PM: Brad Smith,PM: Joseph O'Brien,PM: Joseph O'Brien,PM: Katie Bittner,PM: Katie Bittner,Planner: JENNA GERBER,Planner: JENNA GERBER,Planner: Katie Bittner,Planner: Katie Bittner,Planner: Lawrence Bernabei,Planner: Lawrence Bernabei,Planner: Richard Todd,Planner: Richard Todd | FINAL | 676.4691 | 1623.36 | 402.2605 | 2732.667 | 347.7325 | 2232.383 | -274.2086 | 54.528 | 0.59465 | 1.1568 | 10807.2371 | 9393.6906 | 9226.2917 | -1413.5466 | 167.3988 | 0.8692 | 1.0181 | 3.0971 | 11056.4794 | 9763.182 | 1662.7889 | 1293.2974 | 85% | 83.45% | 11056.4794 | 9763.182 | 10859.4491 | 11105.2039 | - | - | 0.59465 | 1.1568 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Air Power | COMMAND AND CONTROL | 61BN | Qatar AOC Upgrade nonReportable | 0 | Development |  |  |  | Deteriorating | Active | Finance: ERIN LEONARD,Finance: ERIN LEONARD,Finance: JOHN PANETTA,Finance: JOHN PANETTA,Finance: TIFFANY O'KEEFE,Finance: TIFFANY O'KEEFE,PM: Abigail Capano,PM: Abigail Capano,PM: Glenn Ouyang,PM: Glenn Ouyang,Planner: CHRISTINA CORACCIO,Planner: CHRISTINA CORACCIO,Planner: David Lafleur,Planner: David Lafleur,Planner: GRACIELA Amundsen,Planner: GRACIELA Amundsen,Planner: Jackie Hollandsworth,Planner: Jackie Hollandsworth,Planner: TIM MCCORMICK,Planner: TIM MCCORMICK,Planner: William Marcley,Planner: William Marcley | FINAL | 352.4988 | 2572.42 | 182.508 | 1381.922 | 137.3954 | 1577.632 | -169.9908 | 45.1126 | 0.51775 | 1.3283 | 2251.1908 | 1826.9661 | 1501.702 | -424.2247 | 325.2641 | 0.81156 | 1.2166 | 0.85931 | 3295.082 | 3210.191 | 1468.1159 | 84.891 | 55% | 45.57% | 3295.084 | 3210.3034 | 2708.4417 | 2988.6488 | 0.90955 | 0.6 | 0.51775 |  | 0.85931 |  |  | MTD SPI 5 month average is less than ITD SPI. TCPI 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | AIM-9X | 0EK1 | LAND 19 IOT | 40 | Development |  |  |  | Steady | Active | Finance: Bradley Miller,Finance: Bradley Miller,PM: Deepak Basandrai,PM: Deepak Basandrai,PM: Jerry Morales,PM: Jerry Morales,Planner: Lawrence Brown,Planner: Lawrence Brown | PRELIMINARY | 53.448 | 271.27 | 25.051 | 123.1 | 28.2822 | 159.35 | -28.397 | -3.2312 | 0.4687 | 0.88575 | 3525.6411 | 3380.7077 | 4072.7751 | -144.9335 | -692.0674 | 0.95889 | 0.83007 | 1.1508 | 4697.4617 | 5217.0166 | 1316.754 | -519.5549 | 72% | 86.7% | 4697.4617 | 4364.6513 | 5659.0829 | 5727.0891 | 0.94203 | 0.5 | 0.4687 |  |  |  |  | MTD SPI 5 month average is less than ITD SPI.
| Naval Power | RAM | 0ERG | LSCU Redesign | 23 | Internal |  |  |  | Steady | Active | PM: Chad Anderson,PM: Chad Anderson,PM: Gary Chupp,PM: Gary Chupp,Planner: Kristen Marcum,Planner: Kristen Marcum,Planner: Kristin Jiroudek,Planner: Kristin Jiroudek,Planner: Malinda Seagraves,Planner: Malinda Seagraves,Planner: Seth Van Norman,Planner: Seth Van Norman | FINAL | 355.7385 | 1675.66 | 379.4471 | 1850.224 | 378.5653 | 2038.981 | 23.7086 | 0.88184 | 1.0666 | 1.0023 | 2266.1477 | 1991.9743 | 2245.9541 | -274.1735 | -253.9799 | 0.87901 | 0.88692 | 1.4436 | 2901.4005 | 2875.9331 | 909.4263 | 25.4675 | 69% | 77.41% | 2907.1138 | 2855.6593 | 3271.3337 | 3412.466 | 0.83 | 0.35 | 1.0666 |  |  |  |  | MTD SPI 5 month average is less than ITD SPI.
| Naval Power | ANS | 60Y0 | SPY 3 Restoration | 49 | Production |  |  |  | Steady | Active | Finance: Leif Sorenson,Finance: Leif Sorenson,PM: Mark Silveira,PM: Mark Silveira,Planner: Anthony Muhl,Planner: Anthony Muhl | FINAL | 20.2101 | 116.42 | 12.185 | 22.652 | 190.1979 | 717.666 | -8.0251 | -178.0129 | 0.60292 | 0.064065 | 12038.3646 | 11261.9439 | 9465.5805 | -776.4207 | 1796.3634 | 0.9355 | 1.1898 | 2.3315 | 12123.2475 | 9835.0027 | 861.3037 | 2288.2448 | 93% | 78.08% | 11998.9546 | 9502.5132 | 10189.4998 | 10239.4082 | 0.94194 | 1 |  | 0.064065 |  | 2288.2448 | 0 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Air Power | PERSISTENT AND STRATEGIC SENSORS | 60E1 | FSSMI FPIF | 36 | Development |  |  |  | Steady | Watch Program | Finance: Patrick Gallagher,Finance: Patrick Gallagher,Finance: Ram Purushotaman,Finance: Ram Purushotaman,PM: Ladd Horvath,PM: Ladd Horvath,Planner: Byron Chin,Planner: Byron Chin,Planner: Catherine Arno,Planner: Catherine Arno,Planner: Jason Iovanna,Planner: Jason Iovanna | FINAL | 31.6399 | 0 | 503.5317 | 2312.594 | 1904.6132 | 7384.249 | 471.8918 | -1401.0815 | 15.9145 | 0.26437 | 241108.1989 | 240664.6668 | 423798.7645 | -443.5322 | -183134.0978 | 0.99816 | 0.56787 | 0.23251 | 241417.5531 | 427036.8964 | 752.8863 | -185619.3433 | 99% | 175.5% | 241417.5531 | 425709.1848 | 425124.5607 | 425127.004 | 0.82693 | - |  | 0.26437 | 0.23251 | -185619.3433 | 0 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 61G3 | THAAD KSA PHASE 2 TRAINING DEVICES | 12 | Internal |  |  |  | Deteriorating | Active | Finance: Nakia Gallegos,Finance: Nakia Gallegos,PM: Gregory Thomas,PM: Gregory Thomas,Planner: Adam Genetti,Planner: Adam Genetti | FINAL | 238.7399 | 993.07 | 0 | 0 | 265.4583 | 1565.56 | -238.7399 | -265.4583 | 0 | 0 | 636.4022 | 397.6624 | 549.7669 | -238.7399 | -152.1045 | 0.62486 | 0.72333 | 0 | 1131.2471 | 549.7669 | 733.5847 | 581.4802 | 35% | 48.6% | 1006.4351 | 425.269 | 1563.9454 | 2172.8158 | - | - |  |  |  | 581.4802 |  | VAC 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | INTEGRATED MISSION SYSTEMS | 613V | CEC AEGIS CPIF CLIN 0001 | 41 | DoD - Engineering Manufacturing and Development |  |  |  | Steady | Active | Finance: BONNIE REBELO,Finance: BONNIE REBELO,Finance: Matthew Proehl,Finance: Matthew Proehl,PM: Daniel Anderson,PM: Daniel Anderson,PM: Donn Slaughter,PM: Donn Slaughter,Planner: CHARLES KENNA,Planner: CHARLES KENNA,Planner: David Ponte,Planner: David Ponte,Planner: Gary Sorensen,Planner: Gary Sorensen,Planner: Jennifer O'Rorke,Planner: Jennifer O'Rorke,Planner: TIM MCCORMICK,Planner: TIM MCCORMICK | FINAL | 38.7247 | 281.645 | 32.7495 | 293.528 | 87.3226 | 558.637 | -5.9752 | -54.5731 | 0.8457 | 0.37504 | 9401.7411 | 8732.5051 | 7946.9505 | -669.2361 | 785.5546 | 0.92882 | 1.0988 | 0.50568 | 9417.6455 | 9301.8481 | 685.1404 | 115.7974 | 93% | 84.38% | 9412.4622 | 9279.3657 | 8570.4574 | 8618.2413 | 0.89831 | 0.14286 | 0.8457 | 0.37504 | 0.50568 | 115.7974 |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Strategic Missile Defense | C2 OTHER | 60UE | AFMC3AS 6th Battalion | 6 | Development |  |  |  | Steady | Active | Finance: Dale Principe,Finance: Dale Principe,PM: Gregg Osborn,PM: Gregg Osborn,PM: Robert Christian,PM: Robert Christian,Planner: Dale Principe,Planner: Dale Principe,Planner: Richard Todd,Planner: Richard Todd | FINAL | 154.3495 | 0 | 1.1856 | 0 | 7.7478 | 37.737 | -153.1638 | -6.5622 | 0.0076815 | 0.15303 | 5034.9141 | 4891.7823 | 6515.2576 | -143.1318 | -1623.4753 | 0.97157 | 0.75082 | 0.61492 | 5389.3634 | 7324.4395 | 497.5811 | -1935.0762 | 91% | 120.9% | 5389.3634 | 7325.8809 | 7177.9749 | 7197.3658 | - | - | 0.0076815 | 0.15303 |  | -1935.0762 | 0 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Air Power | HARM | 0EIO | HARM REIK NRE | 2 | Development |  |  |  | Steady | Active | Finance: Elizabeth Mobley,Finance: Elizabeth Mobley,PM: HILLARY ULLRICH,PM: HILLARY ULLRICH,PM: SCOTT PEDERSON,PM: SCOTT PEDERSON,Planner: Daniel Jester,Planner: Daniel Jester,Planner: Jose Ruben Romo,Planner: Jose Ruben Romo,Planner: Laurence Harris,Planner: Laurence Harris,Planner: MIGUEL GUZMAN,Planner: MIGUEL GUZMAN,Planner: Yesenia Hernandez,Planner: Yesenia Hernandez | FINAL | 62.6203 | 335.8 | 196.133 | 1071.916 | 424.8992 | 2444.557 | 133.5127 | -228.7662 | 3.1321 | 0.4616 | 21716.442 | 21365.1085 | 25964.1411 | -351.3334 | -4599.0325 | 0.98382 | 0.82287 | 0.38999 | 21834.447 | 27167.5953 | 469.3385 | -5333.1484 | 98% | 118.9% | 21834.447 | 26510.9637 | 26534.5089 | 26543.8881 | 0.9404 | - |  | 0.4616 | 0.38999 | -5333.1484 | 721334 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | NAVAL RADARS | 60HT | Enterprise Air Surveillance Radar EMD | 108 | Development |  |  |  | Steady | Watch Program | Finance: Erin JOHNSTON,Finance: Erin JOHNSTON,Finance: Jonathan Phelps,Finance: Jonathan Phelps,Finance: Joshua Stedman,Finance: Joshua Stedman,Finance: Nikhiles Lombard,Finance: Nikhiles Lombard,PM: David Fenn,PM: David Fenn,PM: Shezan Kanjiyani,PM: Shezan Kanjiyani,Planner: Anna Davydan,Planner: Anna Davydan,Planner: Byron Chin,Planner: Byron Chin,Planner: Jennifer O'Rorke,Planner: Jennifer O'Rorke,Planner: Kevin Mcvey,Planner: Kevin Mcvey,Planner: Sherri Scofield,Planner: Sherri Scofield,Planner: Stephen Colwell,Planner: Stephen Colwell,Planner: ZACHARY SHAW,Planner: ZACHARY SHAW | FINAL | 0 | 0 | 14.8005 | 42.995 | 278.3362 | 1128.609 | 14.8005 | -263.5358 | 0 | 0.053175 | 82796.6573 | 82634.8144 | 134685.0755 | -161.8429 | -52050.2611 | 0.99805 | 0.61354 | 0.039788 | 82810.702 | 139105.7442 | 175.8876 | -56295.0422 | 99% | 162.6% | 82796.6573 | 139340.7973 | 134971.7517 | 134972.3131 | 0.9812 | 0.33333 | 0 | 0.053175 |  |  | 724381.81 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Naval Power | AIM-9X | 0EJN | AIM9X SCU101 | 24 | Development |  |  |  | Steady | Active | Finance: Bradley Miller,Finance: Bradley Miller,PM: Deepak Basandrai,PM: Deepak Basandrai,PM: Jerry Morales,PM: Jerry Morales,Planner: Lawrence Brown,Planner: Lawrence Brown | PRELIMINARY | 54.1588 | 279.24 | 47.658 | 246.5 | 45.534 | 257.092 | -6.5008 | 2.1241 | 0.87997 | 1.0466 | 1137.4197 | 1018.7073 | 906.7785 | -118.7124 | 111.9288 | 0.89563 | 1.1234 | 2.6078 | 1138.4478 | 952.694 | 119.7405 | 185.7537 | 89% | 79.65% | 1138.4478 | 864.4491 | 1013.3627 | 1025.7832 | 0.725 | 0.33333 | 0.87997 |  |  |  |  | MTD SPI 5 month average is less than ITD SPI.
| Strategic Missile Defense | MISSILE DEFENSE | 619Z | KSA THAAD Production Non Reportable | 6 | Development |  |  |  | Steady | Active | Finance: Adam Muzerall,Finance: Adam Muzerall,Finance: Joseph Chop,Finance: Joseph Chop,Finance: MICHAEL AHLIN,Finance: MICHAEL AHLIN,PM: Joseph DiCesare,PM: Joseph DiCesare,PM: William Lawton,PM: William Lawton,Planner: Catherine Arno,Planner: Catherine Arno,Planner: Dawid Wolski,Planner: Dawid Wolski,Planner: Jereme Coste,Planner: Jereme Coste,Planner: Michael Mirabile,Planner: Michael Mirabile,Planner: Monica Dwyre-Wortman,Planner: Monica Dwyre-Wortman,Planner: SAMANTHA HATFIELD-COLANGELO,Planner: SAMANTHA HATFIELD-COLANGELO,Planner: SARAH DIXON,Planner: SARAH DIXON,Planner: Thomas Wegerski,Planner: Thomas Wegerski,Planner: ZACHARY SHAW,Planner: ZACHARY SHAW | FINAL | 11495.9639 | 38482.65 | 3706.6575 | 16968.244 | 7639.3231 | 23743.072 | -7789.3063 | -3932.6656 | 0.32243 | 0.48521 | 304989.9085 | 326306.9265 | 335334.5971 | 21317.018 | -9027.6706 | 1.0699 | 0.97308 | 1.0084 | 1330111.5535 | 1330796.3958 | 1003804.627 | -684.8423 | 25% | 25.21% | 1299137.1968 | 1298229.9555 | 1299519.7516 | 1366910.6773 | 0.34698 | - | 0.32243 | 0.48521 | 1.0084 | -684.8423 |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Land Warfare & Air Defense | QATAR PROGRAMS | 615P | Qatar NASAMS | 13 | Development |  |  |  | Deteriorating | Active | Finance: ANDRA HAGGERTY,Finance: ANDRA HAGGERTY,Finance: JOHN ARICO,Finance: JOHN ARICO,Finance: Joseph Burns,Finance: Joseph Burns,PM: Alan Hart,PM: Alan Hart,PM: MICHAEL Manchini,PM: MICHAEL Manchini,Planner: Byron Chin,Planner: Byron Chin,Planner: Charles Barnes,Planner: Charles Barnes,Planner: Dawid Wolski,Planner: Dawid Wolski,Planner: Dayle DaSilva,Planner: Dayle DaSilva,Planner: MATTHEW RONDEAU,Planner: MATTHEW RONDEAU,Planner: MICHAEL GILL,Planner: MICHAEL GILL,Planner: Prashant Navkal,Planner: Prashant Navkal,Planner: TIMOTHY REHFELDT,Planner: TIMOTHY REHFELDT | FINAL | 6661.6455 | 18133.38 | 7770.0982 | 18345.711 | 7153.3794 | 21519.541 | 1108.4527 | 616.7188 | 1.1664 | 1.0862 | 958479.0554 | 944389.6498 | 916620.1846 | -14089.4055 | 27769.4653 | 0.9853 | 1.0303 | 1.0224 | 1445323.8021 | 1406582.9732 | 500934.1522 | 38740.8289 | 65% | 63.42% | 1444608.2268 | 1406582.9732 | 1402824.5338 | 1410078.2455 | 0.93591 | - | 1.1664 |  | 1.0224 | 38740.8289 | 17572810 | MTD SPI 5 month average is less than ITD SPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | UAE PROGRAMS | 616R | UAE GEMT 200 Lot | 1 | Production |  |  |  | Steady | Active | Finance: Christopher Dicenso,Finance: Christopher Dicenso,Finance: Ryan Hwang,Finance: Ryan Hwang,PM: Brian Gath,PM: Brian Gath,PM: Erik French,PM: Erik French,Planner: Michael Jordan,Planner: Michael Jordan | PRELIMINARY | 26023.2488 | 58734.41 | 8244.3687 | 21792.671 | 9186.9227 | 21566.405 | -17778.88 | -942.5539 | 0.31681 | 0.8974 | 196422.9481 | 196962.9486 | 194525.5674 | 540.0005 | 2437.3812 | 1.0027 | 1.0125 | 0.9471 | 569634.525 | 588013.139 | 372671.5764 | -18378.614 | 35% | 34.15% | 569634.525 | 588013.139 | 561576.3141 | 562585.3999 | - | - | 0.31681 |  |  | -18378.614 |  | MTD SPI 5 month average is less than ITD SPI. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Strategic Missile Defense | MISSILE DEFENSE | 61B1 | UAE THAAD A6 | 1 | Development |  |  |  | Steady | Active | Finance: Jeffrey Morrow,Finance: Jeffrey Morrow,Finance: KATHERINE KELLEY,Finance: KATHERINE KELLEY,Finance: Ryan McCarthy,Finance: Ryan McCarthy,PM: Danial Ashmun,PM: Danial Ashmun,Planner: June Duggan,Planner: June Duggan | FINAL | 1774.0522 | 5270.16 | 1941.399 | 4702.626 | 2233.9187 | 7747.93 | 167.3468 | -292.5197 | 1.0943 | 0.86906 | 30785.5528 | 35719.1848 | 35580.4133 | 4933.632 | 138.7715 | 1.1603 | 1.0039 | 0.97198 | 123288.521 | 125673.7419 | 87569.3361 | -2385.221 | 29% | 28.86% | 123046.463 | 125439.9397 | 110761.2102 | 122809.5364 | - | - |  | 0.86906 |  |  | 3596654.53 | MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Naval Power | NAVAL RADARS | 6102 | AEGIS FY18 FY20 Production | 93 | Production |  |  |  | Steady | Active | Finance: JENNA GERBER,Finance: JENNA GERBER,Finance: JONATHAN BAZARIAN,Finance: JONATHAN BAZARIAN,Finance: Jason O'Neil,Finance: Jason O'Neil,Finance: Katie Bittner,Finance: Katie Bittner,PM: Brad Smith,PM: Brad Smith,PM: JONATHAN BAZARIAN,PM: JONATHAN BAZARIAN,PM: Jason O'Neil,PM: Jason O'Neil,PM: Joseph O'Brien,PM: Joseph O'Brien,PM: Katie Bittner,PM: Katie Bittner,Planner: JENNA GERBER,Planner: JENNA GERBER,Planner: JONATHAN BAZARIAN,Planner: JONATHAN BAZARIAN,Planner: Katie Bittner,Planner: Katie Bittner,Planner: Lawrence Bernabei,Planner: Lawrence Bernabei,Planner: Melanie HACKETT,Planner: Melanie HACKETT,Planner: Richard Todd,Planner: Richard Todd | FINAL | 3871.1461 | 11934.75 | 3356.3291 | 12518.55 | 4520.7579 | 18314.663 | -514.817 | -1164.4289 | 0.86701 | 0.74243 | 152995.0146 | 155155.9534 | 146970.3272 | 2160.9388 | 8185.6262 | 1.0141 | 1.0557 | 1.1153 | 226797.4149 | 211202.7596 | 71641.4615 | 15594.6552 | 68% | 64.8% | 226797.4149 | 211202.7596 | 213887.0231 | 214832.1708 | - | - | 0.86701 | 0.74243 |  |  | 0 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Naval Power | Naval Surface & Undersea Systems | 60TB | Barracuda | 89 | Development |  |  |  | Steady | Active | Finance: AMANDA GRAMMEL,Finance: AMANDA GRAMMEL,Finance: Gail Gormally,Finance: Gail Gormally,PM: Joseph Jussila,PM: Joseph Jussila,PM: Stephen Skirzenski,PM: Stephen Skirzenski,Planner: Divinia Maguire,Planner: Divinia Maguire,Planner: Richard Helle,Planner: Richard Helle | FINAL | 2155.5461 | 7650.22 | 2273.1999 | 7627.699 | 2848.7955 | 9732.977 | 117.6538 | -575.5956 | 1.0546 | 0.79795 | 97957.4575 | 95860.1952 | 97776.4991 | -2097.2623 | -1916.304 | 0.97859 | 0.9804 | 1.0495 | 156431.4453 | 155490.5095 | 60571.2501 | 940.9358 | 61% | 62.5% | 156701.3254 | 154946.3245 | 159558.6056 | 160910.2958 | 0.8807 | 0.64444 |  | 0.79795 |  | 940.9358 | 3554213 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget. |  | 50137.1886 | 48039.9263 | 49956.2302 | -2097.2623 | -1916.304 | 0.95817 | 0.96164
| Strategic Missile Defense | MISSILE DEFENSE | 612Q | KSA THAAD Long Lead Fixed Price | 0 | Development |  |  |  | Steady | Active | Finance: Adam Muzerall,Finance: Adam Muzerall,Finance: Joseph Chop,Finance: Joseph Chop,Finance: MICHAEL AHLIN,Finance: MICHAEL AHLIN,PM: Joseph DiCesare,PM: Joseph DiCesare,Planner: Catherine Arno,Planner: Catherine Arno,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Michael Mirabile,Planner: Michael Mirabile,Planner: SARAH DIXON,Planner: SARAH DIXON,Planner: Thomas Wegerski,Planner: Thomas Wegerski,Planner: ZACHARY SHAW,Planner: ZACHARY SHAW | FINAL | 101.6986 | 500.82 | 918.8161 | 2292.288 | 883.7629 | 2530.6 | 817.1175 | 35.0533 | 9.0347 | 1.0397 | 133274.8235 | 117465.1709 | 110987.0134 | -15809.6526 | 6478.1575 | 0.88138 | 1.0584 | 0.97819 | 172303.8458 | 167048.2901 | 54838.6749 | 5255.5557 | 68% | 64.41% | 172306.155 | 163592.6087 | 162801.3573 | 169775.0565 | 0.81569 | - |  | 1.0397 |  | 5255.5557 | 11182398.79 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | NAVAL RADARS | 615J | AEGIS FMS FY18 20 Production | 89 | Production |  |  |  | Steady | Active | Finance: JENNA GERBER,Finance: JENNA GERBER,Finance: JONATHAN BAZARIAN,Finance: JONATHAN BAZARIAN,Finance: Jason O'Neil,Finance: Jason O'Neil,Finance: Katie Bittner,Finance: Katie Bittner,PM: Brad Smith,PM: Brad Smith,PM: JONATHAN BAZARIAN,PM: JONATHAN BAZARIAN,PM: Jason O'Neil,PM: Jason O'Neil,PM: Joseph O'Brien,PM: Joseph O'Brien,PM: Katie Bittner,PM: Katie Bittner,Planner: JENNA GERBER,Planner: JENNA GERBER,Planner: JONATHAN BAZARIAN,Planner: JONATHAN BAZARIAN,Planner: Katie Bittner,Planner: Katie Bittner,Planner: Lawrence Bernabei,Planner: Lawrence Bernabei,Planner: Richard Todd,Planner: Richard Todd | FINAL | 58.4748 | 197.24 | -649.0572 | 71.689 | -456.6477 | 171.241 | -707.532 | -192.4094 | -11.0998 | 1.4214 | 1425.8265 | 10183.0033 | 10109.1563 | 8757.1768 | 73.847 | 7.1418 | 1.0073 | 0.97403 | 53591.6351 | 54674.9416 | 43408.6318 | -1083.3065 | 19% | 18.86% | 53591.6351 | 54674.9416 | 16143.1648 | 53202.9892 | 1 | - | -11.0998 | 1.4214 |  |  | 0 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | QATAR PROGRAMS | 60U2 | Qatar Depot Operations Cost Type | 55 | Development |  |  |  | Steady | Active | Finance: LISA WALLACE,Finance: LISA WALLACE,PM: Melissa Hughes,PM: Melissa Hughes,PM: STEPHEN CONNOR,PM: STEPHEN CONNOR,PM: Shawn Steele,PM: Shawn Steele,PM: Thomas Mcgovern,PM: Thomas Mcgovern,Planner: Ani Days,Planner: Ani Days,Planner: Dominique Laplanche,Planner: Dominique Laplanche,Planner: Stephen Pike,Planner: Stephen Pike | FINAL | 1998.6107 | 608.8 | 2232.2911 | 539.72 | 2215.0894 | 1223.414 | 233.6805 | 17.2017 | 1.1169 | 1.0078 | 61995.7115 | 61122.4708 | 61969.7805 | -873.2407 | -847.3096 | 0.98591 | 0.98633 | 0.98772 | 99794.3255 | 101122.6071 | 38671.8546 | -1328.2816 | 61% | 62.1% | 99794.3255 | 99943.502 | 101177.7232 | 101737.8768 | 0.99415 | - |  | 1.0078 |  |  | 3174396.43 | MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | AREA DEFENSE SYSTEMS | 610N | LCCS FY19 CP TR | 48 | Development |  |  |  | Steady | Active | PM: Alan Moore,PM: Alan Moore,PM: SUSAN OVERMAN,PM: SUSAN OVERMAN,Planner: Leticia Goodwin,Planner: Leticia Goodwin | FINAL | 1462.5522 | 1508.964 | 1661.0938 | 1508.964 | 1229.3888 | 607.792 | 198.5415 | 431.705 | 1.1358 | 1.3512 | 51296.5272 | 50038.1882 | 48507.1233 | -1258.3389 | 1531.0649 | 0.97547 | 1.0316 | 1.2782 | 77085.8342 | 69667.1341 | 27047.646 | 7418.7001 | 65% | 62.93% | 77085.8342 | 72091.367 | 74727.1674 | 75386.5378 | - | - | 1.1358 |  |  |  |  | MTD SPI 5 month average is less than ITD SPI.
| Strategic Missile Defense | MISSILE DEFENSE | 616G | CLS FY20 IDIQ | 3 | Development |  |  |  | Deteriorating | Active | Finance: Carmine Vara,Finance: Carmine Vara,Finance: John Dewitt,Finance: John Dewitt,PM: Alexander Umansky,PM: Alexander Umansky,PM: Antone Lawrence,PM: Antone Lawrence,PM: CHARLES KENNA,PM: CHARLES KENNA,PM: ELIZABETH SWEENEY,PM: ELIZABETH SWEENEY,PM: Teresa Rudolph,PM: Teresa Rudolph,PM: Thomas Mccarthy,PM: Thomas Mccarthy,Planner: CHRISTINA CORACCIO,Planner: CHRISTINA CORACCIO,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Jereme Coste,Planner: Jereme Coste,Planner: SAMANTHA HATFIELD-COLANGELO,Planner: SAMANTHA HATFIELD-COLANGELO | FINAL | 1260.0313 | -538.133 | 381.2537 | 1686.923 | 1006.1889 | 4014.048 | -878.7776 | -624.9352 | 0.30257 | 0.37891 | 149082.4319 | 143123.0014 | 130543.527 | -5959.4305 | 12579.4744 | 0.96003 | 1.0964 | 0.9755 | 165861.312 | 153852.8938 | 22738.3106 | 12008.4182 | 86% | 78.71% | 165857.277 | 154108.7019 | 151283.3049 | 152146.8787 | 0.91814 | 0.36842 |  | 0.37891 |  |  | 2030621 | MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 61AY | RDC T05 | 1 | Development |  |  |  | Steady | Active | Finance: Nancy Nugent,Finance: Nancy Nugent,Finance: Paolo Cataldi,Finance: Paolo Cataldi,Finance: TARA CHANDLER,Finance: TARA CHANDLER,Finance: TIMOTHY HEPWORTH,Finance: TIMOTHY HEPWORTH,Finance: Tevian Mazzotta,Finance: Tevian Mazzotta,PM: CAITLIN MEDEIROS,PM: CAITLIN MEDEIROS,PM: David Rourke,PM: David Rourke,PM: Jeffrey Lewitzky,PM: Jeffrey Lewitzky,PM: TYLER STRATTON,PM: TYLER STRATTON,Planner: CHARLES KENNA,Planner: CHARLES KENNA,Planner: Jereme Coste,Planner: Jereme Coste,Planner: Monica Dwyre-Wortman,Planner: Monica Dwyre-Wortman,Planner: Paul Bonin,Planner: Paul Bonin,Planner: Timothy Parella,Planner: Timothy Parella | FINAL | 1981.2198 | 10468.33 | 1965.771 | 10357.936 | 2040.3449 | 11771.439 | -15.4488 | -74.5739 | 0.9922 | 0.96345 | 30765.4824 | 30345.5932 | 29978.4403 | -419.8893 | 367.1529 | 0.98635 | 1.0122 | 1.0054 | 49744.1802 | 49273.4947 | 19398.587 | 470.6855 | 61% | 60.27% | 49911.3586 | 48981.4153 | 49142.3228 | 49407.4917 | 0.91213 | 0.57143 |  | 0.96345 | 1.0054 | 470.6855 | 1825446 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | AIM-9X | 0EMO | ABMS cCM Demo | 58 | Development |  |  |  | Improving | Active | Finance: Bradley Miller,Finance: Bradley Miller,PM: Deepak Basandrai,PM: Deepak Basandrai,PM: Jerry Morales,PM: Jerry Morales,Planner: Lawrence Brown,Planner: Lawrence Brown | FINAL | 1860.3145 | 5487.31 | 1601.1586 | 5124.886 | 1212.046 | 3243.273 | -259.1558 | 389.1127 | 0.86069 | 1.321 | 6793.4156 | 6402.4425 | 6575.1748 | -390.9731 | -172.7323 | 0.94245 | 0.97373 | 1.0266 | 22636.1894 | 22388.3032 | 16233.7469 | 247.8862 | 28% | 29.05% | 22636.1894 | 23032.3068 | 23246.8941 | 24264.9734 | 0.83051 | 0.25926
| Land Warfare & Air Defense | AREA DEFENSE SYSTEMS | 610O | LCCS FY19 FFP | 48 | Development |  |  |  | Deteriorating | Active | Finance: Leticia Goodwin,Finance: Leticia Goodwin,PM: Alan Moore,PM: Alan Moore,PM: SUSAN OVERMAN,PM: SUSAN OVERMAN,Planner: Leticia Goodwin,Planner: Leticia Goodwin | FINAL | 455.8774 | 1095.09 | 356.7866 | 1095.09 | 516.1806 | 1043.72 | -99.0908 | -159.394 | 0.78264 | 0.6912 | 25311.9149 | 25168.538 | 23892.9182 | -143.3769 | 1275.6198 | 0.99434 | 1.0534 | 0.91402 | 35922.8645 | 35658.9204 | 10754.3265 | 263.9441 | 70% | 66.51% | 35922.8645 | 35922.8637 | 34102.182 | 34160.3409 | - | - | 0.78264 | 0.6912 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Advanced Technology | AS: S&T PORTFOLIO | 619Q | ROCR | 24 | Development |  |  |  | Improving | Active | Finance: CASEY MCLAUGHLIN,Finance: CASEY MCLAUGHLIN,PM: Joanne Attridge,PM: Joanne Attridge,Planner: Judith Kopeloff,Planner: Judith Kopeloff | FINAL | 675.7498 | 3310.53 | 682.8769 | 3514.677 | 771.2422 | 3474.037 | 7.127 | -88.3654 | 1.0105 | 0.88542 | 14307.3108 | 13334.2948 | 11796.0895 | -973.016 | 1538.2053 | 0.93199 | 1.1304 | 1.2829 | 24069.4009 | 20163.7321 | 10735.1061 | 3905.6688 | 55% | 49.01% | 24069.7014 | 20287.9707 | 21292.8251 | 21985.8108 | 0.7987 | 0.24138 |  | 0.88542 |  |  | -1452566 | MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 612P | KSA THAAD Long Lead Cost Type | 27 | Development |  |  |  | Improving | Active | Finance: Adam Muzerall,Finance: Adam Muzerall,Finance: Joseph Chop,Finance: Joseph Chop,Finance: MICHAEL AHLIN,Finance: MICHAEL AHLIN,PM: Joseph DiCesare,PM: Joseph DiCesare,Planner: Catherine Arno,Planner: Catherine Arno,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Michael Mirabile,Planner: Michael Mirabile,Planner: SARAH DIXON,Planner: SARAH DIXON,Planner: Thomas Wegerski,Planner: Thomas Wegerski,Planner: ZACHARY SHAW,Planner: ZACHARY SHAW | FINAL | -249.1661 | 244.89 | 1145.5029 | 4422.726 | 393.9861 | 1713.783 | 1394.669 | 751.5168 | -4.5973 | 2.9075 | 124861.9379 | 118535.3075 | 113361.0356 | -6326.6305 | 5174.2719 | 0.94933 | 1.0456 | 0.69992 | 125149.0838 | 122810.326 | 6613.7764 | 2338.7578 | 95% | 90.58% | 125149.0838 | 119948.9918 | 119686.1091 | 120023.6997 | 0.81579 | - |  |  | 0.69992 | 2338.7578 | 807929.93 | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Advanced Technology | AMS: ADV PROGRAMS | 0EKI | CPS Blk 1 | 36 | Development |  |  |  | Improving | Active | Finance: BENJAMIN JAEDECKE,Finance: BENJAMIN JAEDECKE,Finance: Carlo Pedrazzini,Finance: Carlo Pedrazzini,Finance: JARAN HOOVER,Finance: JARAN HOOVER,PM: Carlo Pedrazzini,PM: Carlo Pedrazzini,PM: JANNA MITCHKE,PM: JANNA MITCHKE,PM: JARAN HOOVER,PM: JARAN HOOVER,Planner: Carlo Pedrazzini,Planner: Carlo Pedrazzini,Planner: Gregory Ornella,Planner: Gregory Ornella,Planner: JARAN HOOVER,Planner: JARAN HOOVER | FINAL | 396.9607 | 2016.04 | 389.6178 | 1976.04 | 616.683 | 3212.645 | -7.3429 | -227.0652 | 0.9815 | 0.6318 | 27022.9942 | 24918.6951 | 24637.3985 | -2104.2991 | 281.2966 | 0.92213 | 1.0114 | 0.73062 | 31451.4517 | 33578.8214 | 6532.7566 | -2127.3697 | 79% | 78.33% | 31451.4517 | 29247.6704 | 31096.4096 | 31641.8511 | 0.71831 | - |  | 0.6318 | 0.73062 | -2127.3697 | 854028.44 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | EUCOM PROGRAMS | 614T | German Patriot C3 Plus Upgrade Program | 36 | Production |  |  |  | Improving | Active | Finance: NICHOLAS MUZERALL,Finance: NICHOLAS MUZERALL,PM: Wayne Weichel,PM: Wayne Weichel,Planner: CHRISTOPHER COLMAN,Planner: CHRISTOPHER COLMAN,Planner: Curtis Nolet,Planner: Curtis Nolet,Planner: NICHOLAS MUZERALL,Planner: NICHOLAS MUZERALL,Planner: Paul Salamone,Planner: Paul Salamone | FINAL | 230.1408 | 1127.2 | 559.6253 | 3037.776 | 524.7136 | 3755.571 | 329.4845 | 34.9117 | 2.4317 | 1.0665 | 70267.668 | 66557.2934 | 59254.2718 | -3710.3745 | 7303.0216 | 0.9472 | 1.1232 | 1.6943 | 72949.9162 | 63027.3913 | 6392.6228 | 9922.5249 | 91% | 81.23% | 72949.9162 | 63427.4867 | 64945.4619 | 65262.7291 | - | - |  | 1.0665 |  | 9922.5249 | 0 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Air Power | PERSISTENT AND STRATEGIC SENSORS | 612K | AGD Analysis and Integration | 13 | Development |  |  |  | Improving | Active | Finance: Brian Burns,Finance: Brian Burns,Finance: Christa Mixon,Finance: Christa Mixon,Finance: Emerson Laundis,Finance: Emerson Laundis,Finance: JOHN PANETTA,Finance: JOHN PANETTA,PM: CAROLINE JACOBSON,PM: CAROLINE JACOBSON,PM: JEREMY HURLEY,PM: JEREMY HURLEY,Planner: Bridget Harrod,Planner: Bridget Harrod,Planner: DAVID DEDONATO,Planner: DAVID DEDONATO,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Jacqueline Walbourne,Planner: Jacqueline Walbourne,Planner: Jason Crane,Planner: Jason Crane,Planner: Paul Bonin,Planner: Paul Bonin,Planner: REEJA MATHEW,Planner: REEJA MATHEW,Planner: Ryan Driscoll,Planner: Ryan Driscoll,Planner: Sean Liddell,Planner: Sean Liddell | FINAL | -20.2056 | 832.43 | 108.2792 | 770.666 | 299.2835 | 1441.075 | 128.4848 | -191.0044 | -5.3589 | 0.36179 | 14283.6186 | 12478.6165 | 12792.3327 | -1805.002 | -313.7162 | 0.87363 | 0.97548 | 1.1253 | 18832.4474 | 18438.8574 | 6353.8308 | 393.59 | 66% | 67.93% | 18873.7438 | 18050.457 | 19305.9008 | 20248.0729 | 0.81107 | 0.36364 |  | 0.36179 |  |  | 1335927.69 | MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Air Power | PERSISTENT AND STRATEGIC SENSORS | 61FD | ROTHR SHELTERS LOT III | 30 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: Gladys Johnson,Finance: Gladys Johnson,Finance: Kathleen Edgar,Finance: Kathleen Edgar,PM: Eugene Blincoe,PM: Eugene Blincoe,Planner: Brenda Cubelli,Planner: Brenda Cubelli,Planner: David Lafleur,Planner: David Lafleur,Planner: Paul Bonin,Planner: Paul Bonin,Planner: SARAH GREEN,Planner: SARAH GREEN | FINAL | 260.8191 | 350.47 | 197.7676 | 350.47 | 306.7429 | 199.665 | -63.0515 | -108.9752 | 0.75826 | 0.64473 | 2842.9219 | 2123.0551 | 2320.2938 | -719.8669 | -197.2387 | 0.74679 | 0.91499 | 1.0527 | 7207.1209 | 7149.8747 | 5084.0659 | 57.2462 | 29% | 32.19% | 7207.1209 | 7123.157 | 7876.686 | 9760.6987 | - | -
| Naval Power | AIM-9X | 0EKK | AIM9X F35 C2D2 | 3 | Development |  |  |  | Deteriorating | Active | Finance: Bradley Miller,Finance: Bradley Miller,PM: Jerry Morales,PM: Jerry Morales,PM: Nathaniel Charani,PM: Nathaniel Charani,Planner: Lawrence Brown,Planner: Lawrence Brown,Planner: MIGUEL GUZMAN,Planner: MIGUEL GUZMAN | PRELIMINARY | 104.193 | 566.22 | 74.3597 | 446.22 | 75.6513 | 412.281 | -29.8333 | -1.2917 | 0.71367 | 0.98293 | 2529.6485 | 2455.4379 | 1808.4581 | -74.2105 | 646.9798 | 0.97066 | 1.3578 | 1.0914 | 7416.7613 | 6354.4318 | 4961.3234 | 1062.3295 | 33% | 24.38% | 7416.7613 | 6361.6862 | 5462.5296 | 5572.9663 | 0.87629 | - | 0.71367 |  |  |  |  | MTD SPI 5 month average is less than ITD SPI.
| Land Warfare & Air Defense | AREA DEFENSE SYSTEMS | 60G9 | LCCS FY16 CP and CP Travel | 36 | Development |  |  |  | Steady | Active | PM: SUSAN OVERMAN,PM: SUSAN OVERMAN,Planner: Leticia Goodwin,Planner: Leticia Goodwin | FINAL | 0 | 0 | 0 | 0 | 0.22551 | 0.042 | 0 | -0.22551 | 0 | 0 | 36569.9454 | 34690.0251 | 31605.4844 | -1879.9203 | 3084.5407 | 0.94859 | 1.0976 | 15.2835 | 36569.9454 | 31728.4877 | 1879.9203 | 4841.4577 | 95% | 86.42% | 36569.9454 | 31728.4876 | 33318.2474 | 33411.0654 | - | - | 0 | 0 | 15.2835 |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast.
| Air Power | PERSISTENT AND STRATEGIC SENSORS | 60PC | ROTHR Shelters Lot 1 | 7 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: Gladys Johnson,Finance: Gladys Johnson,Finance: Kathleen Edgar,Finance: Kathleen Edgar,PM: Eugene Blincoe,PM: Eugene Blincoe,Planner: Brenda Cubelli,Planner: Brenda Cubelli,Planner: Paul Bonin,Planner: Paul Bonin,Planner: SARAH GREEN,Planner: SARAH GREEN | FINAL | 96.2957 | 35.75 | 5.8435 | 35.75 | 17.0873 | 10.272 | -90.4522 | -11.2438 | 0.060683 | 0.34198 | 16826.8572 | 16742.6278 | 17408.3062 | -84.2294 | -665.6784 | 0.99499 | 0.96176 | 1.0178 | 18603.9827 | 19237.0458 | 1861.3549 | -633.0631 | 90% | 93.57% | 16730.5614 | 17391.2189 | 19343.6677 | 19353.4041 | 1.1515 | - |  |  | 1.0178 | -633.0631 |  | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Air Power | PERSISTENT AND STRATEGIC SENSORS | 616C | ROTHR Shelters Lot 2 | 53 | Production |  |  |  | Steady | Active | Finance: Gladys Johnson,Finance: Gladys Johnson,Finance: Kathleen Edgar,Finance: Kathleen Edgar,PM: Eugene Blincoe,PM: Eugene Blincoe,Planner: Brenda Cubelli,Planner: Brenda Cubelli,Planner: Paul Bonin,Planner: Paul Bonin,Planner: SARAH GREEN,Planner: SARAH GREEN | FINAL | 13.4972 | 47.58 | 113.2578 | 47.58 | 60.1444 | 202.228 | 99.7606 | 53.1134 | 8.3912 | 1.8831 | 6203.8063 | 5796.1573 | 5585.8094 | -407.649 | 210.348 | 0.93429 | 1.0377 | 1.425 | 6944.7767 | 6391.8485 | 1148.6194 | 552.9282 | 83% | 80.43% | 6944.7767 | 6608.9681 | 6692.7443 | 6770.596 | 0.375 | - |  |  | 1.425 | 552.9282 | 0 | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Advanced Technology | AS: S&T PORTFOLIO | 61D8 | DARPA ASTARTE | 12 | Development |  |  |  | Steady | Active | PM: David Altman,PM: David Altman,Planner: Adam Genetti,Planner: Adam Genetti,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Judith Kopeloff,Planner: Judith Kopeloff | FINAL | 481.2784 | 643.81 | 636.5242 | 529.49 | 573.1169 | 803.49 | 155.2459 | 63.4073 | 1.3226 | 1.1106 | 5414.7724 | 5278.1836 | 6055.5707 | -136.5889 | -777.3872 | 0.97477 | 0.87162 | 0 | 6269.3642 | 6055.5708 | 991.1806 | 213.7934 | 84% | 96.59% | 6174.2551 | 5482.4538 | 7192.7355 | 7222.1631 | 1.0833 | 1 |  |  |  | 213.7934 | 715693 | VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | SM3 IB | 0EL9 | SM3 IB Multi Year | 84 | Production |  |  |  | Steady | Watch Program | Finance: Matthew Swinford,Finance: Matthew Swinford,PM: John Melichar,PM: John Melichar,PM: LAWRENCE VAN RYN,PM: LAWRENCE VAN RYN,PM: Marco Edmondson,PM: Marco Edmondson,Planner: Erik Hammer,Planner: Erik Hammer,Planner: Evan LAGUNA,Planner: Evan LAGUNA,Planner: JULIE SHARPLESS,Planner: JULIE SHARPLESS,Planner: MATTHEW CHASTAGNER,Planner: MATTHEW CHASTAGNER,Planner: georgia leyva,Planner: georgia leyva | PRELIMINARY | 15972.8134 | 28249.377 | 20089.0763 | 24837.395 | 17933.9686 | 24781.326 | 4116.2629 | 2155.1077 | 1.2577 | 1.1202 | 475427.9932 | 567818.7251 | 565574.0863 | 92390.7319 | 2244.6388 | 1.1943 | 1.004 | 1.0011 | 1762597.628 | 1759076.5121 | 1194778.9029 | 3521.1159 | 32% | 32.09% | 1762536.8393 | 1754742.6989 | 1561993.9504 | 1755629.9202 | 1.6818 | - | 1.2577 |  |  | 3521.1159 | 0 | MTD SPI 5 month average is less than ITD SPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Air Power | AWS: ADV PROGRAMS | 0EQG | CUI Iron Dragon | 54 | Development |  |  |  | Deteriorating | Active | PM: Kurt Wuest,PM: Kurt Wuest,PM: Mandy McNeill,PM: Mandy McNeill | FINAL | 5176.3122 | 290.77 | 3298.2072 | 290.77 | 3205.8347 | 14940.029 | -1878.105 | 92.3725 | 0.63717 | 1.0288 | 24820.5847 | 24706.2048 | 23723.9879 | -114.3799 | 982.2169 | 0.99539 | 1.0414 | 0.99955 | 305287.8177 | 304432.1572 | 280581.6129 | 855.6605 | 8% | 7.771% | 305236.2809 | 305814.7524 | 293150.8315 | 294398.171 | - | - |  |  |  |  | 26029476.15 | Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | EKV | 0D8G | EKV DSC | 138 | Development |  |  |  | Steady | Active | Finance: Tamim Aslamy,Finance: Tamim Aslamy,PM: Caryn Nath,PM: Caryn Nath,Planner: Alexander Wojack,Planner: Alexander Wojack,Planner: Maria Brusati,Planner: Maria Brusati,Planner: Michael Hoffman,Planner: Michael Hoffman | FINAL | 6127.9129 | 29176.233 | 5208.5915 | 27509.825 | 5996.9551 | 28435.042 | -919.3214 | -788.3637 | 0.84998 | 0.86854 | 909177.3452 | 904472.7197 | 912113.6738 | -4704.6255 | -7640.9541 | 0.99483 | 0.99162 | 1.0282 | 1044289.7536 | 1048098.6461 | 139817.034 | -3808.8925 | 87% | 87.34% | 1040310.2298 | 1045599.9536 | 1053111.8772 | 1053845.281 | 0.95795 | 0.52239 | 0.84998 |  |  |  |  | MTD SPI 5 month average is less than ITD SPI.
| Naval Power | ESSM | 0EK2 | ESSM Block II LRIP | 11 | Production |  |  |  | Steady | Active | Finance: Edward Pajor,Finance: Edward Pajor,Finance: Jordan McCombs,Finance: Jordan McCombs,PM: Christopher Driscoll,PM: Christopher Driscoll,PM: MICHAEL ATWATER,PM: MICHAEL ATWATER,Planner: Brett Muxen,Planner: Brett Muxen,Planner: David Rutter,Planner: David Rutter,Planner: Kristin Jiroudek,Planner: Kristin Jiroudek | FINAL | 13235.7532 | 19561.25 | 5784.2497 | 18413.31 | 5107.8525 | 17543.926 | -7451.5035 | 676.3972 | 0.43702 | 1.1324 | 205787.125 | 264579.2755 | 265087.2635 | 58792.1505 | -507.988 | 1.2857 | 0.99808 | 0.97996 | 360452.9341 | 362921.8265 | 95873.6586 | -2468.8923 | 73% | 73.54% | 360367.1882 | 357815.0995 | 339800.0125 | 361144.998 | 1.4086 | 0.30882 | 0.43702 |  | 0.97996 | -2468.8923 |  | MTD SPI 5 month average is less than ITD SPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Strategic Missile Defense | C2 OTHER | 619C | TAADS | 3 | Development |  |  |  | Improving | Active | Finance: Andrew Timmons,Finance: Andrew Timmons,Finance: Curtis Neiswender,Finance: Curtis Neiswender,Finance: DEREK WALTERS,Finance: DEREK WALTERS,PM: Sarya Danawi,PM: Sarya Danawi,Planner: Curtis Neiswender,Planner: Curtis Neiswender,Planner: Hedieh Heshmatipour,Planner: Hedieh Heshmatipour,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS | FINAL | 3256.8827 | 13887.83 | 2379.5724 | 10869.903 | 2399.0439 | 10973.811 | -877.3103 | -19.4715 | 0.73063 | 0.99188 | 63274.7269 | 63964.1987 | 65285.5274 | 689.4718 | -1321.3287 | 1.0109 | 0.97976 | 1.0299 | 152315.1503 | 151067.6973 | 88350.9516 | 1247.453 | 42% | 42.86% | 152328.3269 | 150903.1663 | 154489.5627 | 155461.5727 | 0.96894 | 0.28571 |  |  | 1.0299 | 1247.453 | 699005 | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | SAUDI PROGRAMS | 616Y | KSA FCS | 105 | Production |  |  |  | Deteriorating | Active | PM: THOMAS FURLONG,PM: THOMAS FURLONG,Planner: Lee Brucks,Planner: Lee Brucks,Planner: SUSAN MAPLES,Planner: SUSAN MAPLES | FINAL | 5185.2491 | 16304.46 | 2284.4672 | 8566.487 | 2412.523 | 5576.005 | -2900.7819 | -128.0558 | 0.44057 | 0.94692 | 171586.5529 | 164247.9075 | 138100.7086 | -7338.6453 | 26147.1989 | 0.95723 | 1.1893 | 1.0466 | 247269.0692 | 217424.1066 | 83021.1616 | 29844.9626 | 66% | 55.85% | 247269.0692 | 217424.1066 | 207905.4411 | 211024.3373 | - | - |  | 0.94692 |  |  |  | MTD CPI 5 month average is less than ITD CPI. | On Quarterly EV cycle - data potentially skewed
| Land Warfare & Air Defense | QATAR PROGRAMS | 613S | Qatar Patriot 2 Lot | 2 | Production |  |  |  | Deteriorating | Active | Finance: ANDRA HAGGERTY,Finance: ANDRA HAGGERTY,Finance: JOHN ARICO,Finance: JOHN ARICO,Finance: LISA WALLACE,Finance: LISA WALLACE,PM: LADI KEHINDE,PM: LADI KEHINDE,PM: MICHAEL Manchini,PM: MICHAEL Manchini,Planner: Dominique Laplanche,Planner: Dominique Laplanche,Planner: Jeremy Koen,Planner: Jeremy Koen,Planner: Nicole Moore,Planner: Nicole Moore,Planner: Zubair Maqsood,Planner: Zubair Maqsood | FINAL | 9094.5224 | 5787.028 | 1467.666 | 5501.669 | 1678.5407 | 4230.681 | -7626.8563 | -210.8746 | 0.16138 | 0.87437 | 174366.3373 | 180598.6524 | 168109.2566 | 6232.3151 | 12489.3958 | 1.0357 | 1.0743 | 1.0465 | 260906.2467 | 244845.7295 | 80307.5943 | 16060.5172 | 69% | 64.43% | 260906.7863 | 244845.7295 | 240283.4399 | 242863.1366 | - | - | 0.16138 |  |  |  |  | MTD SPI 5 month average is less than ITD SPI. | On Quarterly EV cycle - data potentially skewed
| Land Warfare & Air Defense | UAE PROGRAMS | 60S4 | UAE 3 Lot Fire Units | 8 | Production |  |  |  | Steady | Active | Finance: Christopher Dicenso,Finance: Christopher Dicenso,Finance: Matthew Waine,Finance: Matthew Waine,Finance: RYAN MCCUE,Finance: RYAN MCCUE,Finance: Ryan Hwang,Finance: Ryan Hwang,PM: Brian Gath,PM: Brian Gath,PM: James Mullen,PM: James Mullen,Planner: JAMES RICHARD,Planner: JAMES RICHARD,Planner: JULIA ROGERS,Planner: JULIA ROGERS,Planner: Jeremy Koen,Planner: Jeremy Koen,Planner: MATTHEW RONDEAU,Planner: MATTHEW RONDEAU,Planner: Michael Jordan,Planner: Michael Jordan,Planner: Nanette Halliburton,Planner: Nanette Halliburton,Planner: Zubair Maqsood,Planner: Zubair Maqsood | FINAL | 2205.3814 | 6018.27 | 1188.6581 | 7078.247 | 1031.8799 | 6691.588 | -1016.7233 | 156.7782 | 0.53898 | 1.1519 | 671940.6991 | 665908.2157 | 633363.2326 | -6032.4834 | 32544.9831 | 0.99102 | 1.0514 | 0.90709 | 745096.9522 | 720663.3054 | 79188.7365 | 24433.6468 | 89% | 85% | 745096.9522 | 720663.3054 | 708681.772 | 709364.085 | - | - | 0.53898 | 1.1519 |  |  | 1727651 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget. | On Quarterly EV cycle - data potentially skewed
| Land Warfare & Air Defense | PATRIOT SYSTEMS | 6134 | DSLC FRP | 3 | Production |  |  |  | Steady | Active | Finance: Danielle POLCARI-BALBONI,Finance: Danielle POLCARI-BALBONI,Finance: NICHOLAS MUZERALL,Finance: NICHOLAS MUZERALL,Finance: Thomas Hackett,Finance: Thomas Hackett,PM: LINDSAY PENNEY,PM: LINDSAY PENNEY,Planner: Danielle POLCARI-BALBONI,Planner: Danielle POLCARI-BALBONI,Planner: NICHOLAS MUZERALL,Planner: NICHOLAS MUZERALL,Planner: Nicholas Czelewicz,Planner: Nicholas Czelewicz,Planner: Thomas Hackett,Planner: Thomas Hackett | FINAL | 5259.8571 | 12871.08 | 1601.8985 | 4755.825 | 1649.1636 | 5633.684 | -3657.9587 | -47.2652 | 0.30455 | 0.97134 | 47770.8595 | 91570.7447 | 79996.6477 | 43799.8851 | 11574.097 | 1.9169 | 1.1447 | 1.0843 | 161005.5374 | 144030.7458 | 69434.7927 | 16974.7915 | 57% | 49.69% | 161005.5374 | 144030.7458 | 111641.1664 | 140655.2201 | - | - | 0.30455 |  |  |  |  | MTD SPI 5 month average is less than ITD SPI. | On Quarterly EV cycle - data potentially skewed
| Strategic Missile Defense | MISSILE DEFENSE | 61FZ | CLS FY22 IDIQ | 12 | Internal |  |  |  | Improving | Active | PM: Alexander Umansky,PM: Alexander Umansky,PM: Antone Lawrence,PM: Antone Lawrence,PM: CHARLES KENNA,PM: CHARLES KENNA,PM: ELIZABETH SWEENEY,PM: ELIZABETH SWEENEY,PM: Teresa Rudolph,PM: Teresa Rudolph,PM: Thomas Mccarthy,PM: Thomas Mccarthy,Planner: Adam Genetti,Planner: Adam Genetti,Planner: CHRISTINA CORACCIO,Planner: CHRISTINA CORACCIO,Planner: Christopher Shoup,Planner: Christopher Shoup,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Jereme Coste,Planner: Jereme Coste,Planner: SAMANTHA HATFIELD-COLANGELO,Planner: SAMANTHA HATFIELD-COLANGELO,Planner: ZACHARY SHAW,Planner: ZACHARY SHAW | FINAL | 6542.4253 | 18901.97 | 6565.6807 | 18903.12 | 6441.2029 | 19747.074 | 23.2554 | 124.4778 | 1.0036 | 1.0193 | 23036.5382 | 22992.926 | 23687.8327 | -43.6122 | -694.9068 | 0.99811 | 0.97066 | 1.0056 | 86507.2448 | 86849.3193 | 63514.3189 | -342.0744 | 27% | 27.38% | 86426.502 | 86640.4455 | 89121.7216 | 89245.8343 | 0.33333 | 0.33333 |  |  | 1.0056 |  | 195354 | TCPI 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | SM3 IIA | 0EOL | SM 3 SEPS IDIQ | 2 | Production |  |  |  | Improving | Active | Finance: Michael Starace,Finance: Michael Starace,PM: Elena Efremova,PM: Elena Efremova,PM: Timothy Keeland,PM: Timothy Keeland,Planner: Cory Bull,Planner: Cory Bull,Planner: Erik Hammer,Planner: Erik Hammer,Planner: Helen Trujillo,Planner: Helen Trujillo | FINAL | 1309.1317 | 7125.65 | 2523.2415 | 14349.27 | 973.9579 | 5834.325 | 1214.1098 | 1549.2836 | 1.9274 | 2.5907 | 2523.2415 | 2523.2415 | 2571.9617 | 1e-05 | -48.7202 | 1 | 0.98106 | 1 | 60168.7954 | 60217.5156 | 57645.5539 | -48.7202 | 4% | 4.275% | 0 | 1598.0039 | 61330.5696 | 61330.5699 | 1.05 | -
| Naval Power | AIM-9X | 0ENU | AIM 9X SIP III Follow On | 1 | Development |  |  |  | Steady | Active | PM: Anthony Jinks,PM: Anthony Jinks,PM: Sandy Pelusi,PM: Sandy Pelusi,Planner: Bruce Mcdaniel,Planner: Bruce Mcdaniel,Planner: Florence Iyer,Planner: Florence Iyer,Planner: Lawrence Brown,Planner: Lawrence Brown,Planner: Lisa Sparks,Planner: Lisa Sparks | FINAL | 2194.9411 | 11800.85 | 1823.0395 | 9670.91 | 1678.9826 | 9202.24 | -371.9016 | 144.0568 | 0.83056 | 1.0858 | 20628.903 | 19777.2033 | 17876.086 | -851.6996 | 1901.1174 | 0.95871 | 1.1063 | 1.0044 | 76134.0293 | 73986.466 | 56356.826 | 2147.5634 | 26% | 23.48% | 76135.1373 | 73940.595 | 68815.5159 | 71009.208 | 0.96865 | 0.55556
| Air Power | PERSISTENT AND STRATEGIC SENSORS | 61EP | QEWR CLS | 68 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: ANDREW MYETTE,Finance: ANDREW MYETTE,Finance: Brian Potter,Finance: Brian Potter,Finance: Thomas Hackett,Finance: Thomas Hackett,PM: Linda Fronsdahl,PM: Linda Fronsdahl,PM: Paul Grigsby,PM: Paul Grigsby,Planner: Brenda Cubelli,Planner: Brenda Cubelli,Planner: CONSTANCE PELLETIER,Planner: CONSTANCE PELLETIER,Planner: David Lafleur,Planner: David Lafleur,Planner: REEJA MATHEW,Planner: REEJA MATHEW | FINAL | 245.5025 | 1326.98 | 217.479 | 1294.95 | 164.4806 | 566.006 | -28.0235 | 52.9984 | 0.88585 | 1.3222 | 1486.2104 | 1458.1869 | 613.1696 | -28.0235 | 845.0173 | 0.98114 | 2.3781 | 1.0385 | 55798.7851 | 52940.9079 | 54340.5982 | 2857.8772 | 3% | 1.099% | 55811.2339 | 55025.8405 | 23463.4648 | 23902.6024 | - | - | 0.88585 | 1.3222 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Strategic Missile Defense | MISSILE DEFENSE | 61AZ | RDC T06 | 24 | Development |  |  |  | Steady | Active | Finance: Carrie Schoenholtz,Finance: Carrie Schoenholtz,Finance: David Rourke,Finance: David Rourke,Finance: Jacquelin Brogan,Finance: Jacquelin Brogan,Finance: Jeffrey Lewitzky,Finance: Jeffrey Lewitzky,Finance: Michael Leschinski,Finance: Michael Leschinski,Finance: Stephen Kim,Finance: Stephen Kim,Finance: TIMOTHY HEPWORTH,Finance: TIMOTHY HEPWORTH,PM: ANTHONY MAWHINNEY,PM: ANTHONY MAWHINNEY,PM: Alexander Umansky,PM: Alexander Umansky,PM: CAITLIN MEDEIROS,PM: CAITLIN MEDEIROS,PM: CHARLES KENNA,PM: CHARLES KENNA,PM: David Rourke,PM: David Rourke,PM: ELIZABETH SWEENEY,PM: ELIZABETH SWEENEY,PM: Erin Scheaffer,PM: Erin Scheaffer,PM: Jeffrey Lewitzky,PM: Jeffrey Lewitzky,PM: TYLER STRATTON,PM: TYLER STRATTON,Planner: CHARLES KENNA,Planner: CHARLES KENNA,Planner: Jereme Coste,Planner: Jereme Coste,Planner: Monica Dwyre-Wortman,Planner: Monica Dwyre-Wortman,Planner: Paul Bonin,Planner: Paul Bonin,Planner: Timothy Parella,Planner: Timothy Parella | FINAL | 5880.4392 | 30910.08 | 6425.6913 | 32621.147 | 6337.0828 | 34963.236 | 545.2521 | 88.6085 | 1.0927 | 1.014 | 86498.6095 | 85777.1944 | 82198.9079 | -721.4151 | 3578.2865 | 0.99166 | 1.0435 | 1.0969 | 139925.7924 | 131564.0971 | 54148.598 | 8361.6953 | 61% | 58.74% | 140754.9192 | 136945.8364 | 134088.6398 | 134525.05 | 0.96303 | 0.78846 |  | 1.014 |  | 8361.6953 | 3252374.85 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | EUCOM PROGRAMS | 612M | Patriot Sweden | 52 | Production |  |  |  | Improving | Active | Finance: Trevor Waters,Finance: Trevor Waters,PM: Julie Praino,PM: Julie Praino,Planner: Alvin Neff,Planner: Alvin Neff,Planner: Andrea Miller,Planner: Andrea Miller,Planner: Ani Days,Planner: Ani Days,Planner: Brian Martinez,Planner: Brian Martinez,Planner: CHARLES KENNA,Planner: CHARLES KENNA,Planner: JAMES RICHARD,Planner: JAMES RICHARD,Planner: JULIA ROGERS,Planner: JULIA ROGERS,Planner: Joaquin Casanova,Planner: Joaquin Casanova,Planner: Lee Brucks,Planner: Lee Brucks,Planner: MATTHEW RONDEAU,Planner: MATTHEW RONDEAU,Planner: Michael Jordan,Planner: Michael Jordan,Planner: Prashant Navkal,Planner: Prashant Navkal,Planner: Stephen Pike,Planner: Stephen Pike | FINAL | 3995.906 | 12299.53 | 10135.4335 | 37539.29 | 8592.4233 | 42456.703 | 6139.5274 | 1543.0102 | 2.5365 | 1.1796 | 505575.717 | 490080.2232 | 471866.0443 | -15495.4938 | 18214.1789 | 0.96935 | 1.0386 | 0.91195 | 538925.4394 | 525427.1749 | 48845.2162 | 13498.2646 | 91% | 87.56% | 538925.4394 | 524709.4049 | 518895.8934 | 520382.8964 | 0.93378 | 0.23636 | 2.5365 | 1.1796 |  | 13498.2646 | 27077176.97 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | MULTINATIONAL PROGRAMS | 61BP | NASAMS Hungary | 53 | Production |  |  |  | Deteriorating | Active | Finance: Ashley PAPPALARDO,Finance: Ashley PAPPALARDO,Finance: Brendan Kelleher,Finance: Brendan Kelleher,PM: Paul Brown,PM: Paul Brown,Planner: David Lafleur,Planner: David Lafleur,Planner: Jeremy Koen,Planner: Jeremy Koen,Planner: Lee Brucks,Planner: Lee Brucks,Planner: TIMOTHY REHFELDT,Planner: TIMOTHY REHFELDT,Planner: Zubair Maqsood,Planner: Zubair Maqsood | FINAL | 1185.6127 | 5314.232 | 2587.6342 | 8207.961 | 2979.9567 | 12064.974 | 1402.0215 | -392.3225 | 2.1825 | 0.86835 | 43644.5477 | 50601.2841 | 48289.5104 | 6956.7363 | 2311.7736 | 1.1594 | 1.0479 | 1.152 | 96289.069 | 87949.3322 | 45687.785 | 8339.7368 | 53% | 50.15% | 96289.0697 | 94039.1535 | 85895.743 | 91890.0002 | 0.69008 | 0.11765 |  | 0.86835 |  |  | 3056339 | MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | AREA DEFENSE SYSTEMS | 619E | Sentinel A3 USG 25 | 45 | Production |  |  |  | Steady | Active | Finance: Dillon Allen,Finance: Dillon Allen,Finance: Jonathan Adsit,Finance: Jonathan Adsit,Finance: Joseph Ferrara,Finance: Joseph Ferrara,Finance: Nikhiles Lombard,Finance: Nikhiles Lombard,PM: KATHY DESON,PM: KATHY DESON,PM: Richard Russell,PM: Richard Russell,Planner: TIMOTHY REHFELDT,Planner: TIMOTHY REHFELDT | FINAL | 6582.2816 | 16645.513 | 4666.3983 | 18392.714 | 3452.4813 | 9543.808 | -1915.8834 | 1213.9169 | 0.70893 | 1.3516 | 51207.5615 | 59058.0673 | 54390.8489 | 7850.5058 | 4667.2184 | 1.1533 | 1.0858 | 1.0341 | 103318.9314 | 97191.2368 | 44260.8641 | 6127.6946 | 57% | 52.64% | 103318.9314 | 71183.8682 | 89735.3097 | 95153.8824 | - | - | 0.70893 |  |  |  | 2109494.62 | MTD SPI 5 month average is less than ITD SPI. Staffing 5 month average actuals exceed your budget.
| Naval Power | UNDERSEA SYSTEMS (LEGACY) | 61DA | AQS 20A TO 20C Upgrade Variant | 41 | Production |  |  |  | Deteriorating | Active | Finance: Jeffrey Spalti,Finance: Jeffrey Spalti,Finance: Karen Lariviere,Finance: Karen Lariviere,Finance: Kristina Del Ricci,Finance: Kristina Del Ricci,PM: Mark Tseytlin,PM: Mark Tseytlin,Planner: Adam Genetti,Planner: Adam Genetti,Planner: Jeffrey Spalti,Planner: Jeffrey Spalti,Planner: Kevin Mcvey,Planner: Kevin Mcvey,Planner: Richard Helle,Planner: Richard Helle,Planner: Seth Van Norman,Planner: Seth Van Norman | FINAL | 1083.9174 | 4856.075 | 265.6277 | -361.472 | 806.2637 | 4018.275 | -818.2897 | -540.636 | 0.24506 | 0.32946 | 12387.6661 | 11866.592 | 11043.9063 | -521.0741 | 822.6857 | 0.95794 | 1.0745 | 1.03 | 54948.4844 | 52872.5265 | 43081.8924 | 2075.9579 | 22% | 20.1% | 55269.2778 | 53629.7182 | 51139.0222 | 52899.6395 | 0.7029 | 0.31818 |  | 0.32946 | 1.03 | 2075.9579 |  | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Air Power | PERSISTENT AND STRATEGIC SENSORS | 60PT | SRP FoS 2 | 2 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: Emerson Laundis,Finance: Emerson Laundis,PM: Alexis Sanchez-Ortiz,PM: Alexis Sanchez-Ortiz,PM: Antoinette Mcbride,PM: Antoinette Mcbride,PM: Shari Pletta,PM: Shari Pletta,Planner: Brenda Cubelli,Planner: Brenda Cubelli,Planner: Monica Dwyre-Wortman,Planner: Monica Dwyre-Wortman,Planner: SARAH GREEN,Planner: SARAH GREEN | FINAL | 3291.6632 | 9474.49 | 3207.1315 | 9669.517 | 2873.1608 | 10094.873 | -84.5318 | 333.9707 | 0.97432 | 1.1162 | 229764.1781 | 230657.2865 | 208397.1361 | 893.1084 | 22260.1504 | 1.0039 | 1.1068 | 0.92699 | 266236.4065 | 246778.3545 | 35579.1199 | 19458.0519 | 87% | 78.28% | 265370.6792 | 246490.8899 | 240418.1376 | 240542.6053 | 0.98518 | 0.5 |  |  | 0.92699 |  | 12081607 | TCPI 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 61BD | XBR FY21 22 | 3 | Development |  |  |  | Improving | Active | PM: Thomas Collins,PM: Thomas Collins,Planner: CHRISTINA CORACCIO,Planner: CHRISTINA CORACCIO,Planner: David Lafleur,Planner: David Lafleur,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Jereme Coste,Planner: Jereme Coste,Planner: Michael Mirabile,Planner: Michael Mirabile,Planner: SAMANTHA HATFIELD-COLANGELO,Planner: SAMANTHA HATFIELD-COLANGELO | FINAL | 2242.2283 | 9854.73 | 3258.6731 | 9709.092 | 3317.4732 | 10795.952 | 1016.4448 | -58.8001 | 1.4533 | 0.98228 | 41387.5102 | 41891.183 | 39874.397 | 503.6728 | 2016.786 | 1.0122 | 1.0506 | 0.98035 | 74948.3553 | 73594.2184 | 33057.1724 | 1354.137 | 56% | 53.2% | 74948.3651 | 73532.1667 | 70961.7599 | 71340.0832 | 0.87586 | 0.71429 |  | 0.98228 |  | 1354.137 | 3207153 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | PATRIOT SYSTEMS | 61D6 | CY21 Patriot Engineering Services | 12 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: MICHAEL DOREN,Finance: MICHAEL DOREN,PM: John Bottino,PM: John Bottino,PM: John Kerr,PM: John Kerr,PM: Michael Trahan,PM: Michael Trahan,Planner: Adam Blais,Planner: Adam Blais,Planner: Adam Genetti,Planner: Adam Genetti,Planner: Andrea Miller,Planner: Andrea Miller,Planner: Audris Terrero,Planner: Audris Terrero,Planner: Brian Martinez,Planner: Brian Martinez,Planner: Colleen McAlpine,Planner: Colleen McAlpine,Planner: Emma Ginsburg,Planner: Emma Ginsburg,Planner: Evan Royer,Planner: Evan Royer,Planner: JULIAN MARDENLI,Planner: JULIAN MARDENLI,Planner: Jeremy Koen,Planner: Jeremy Koen,Planner: Joaquin Casanova,Planner: Joaquin Casanova,Planner: KHANH VO,Planner: KHANH VO,Planner: Lawrence Harlow,Planner: Lawrence Harlow,Planner: Lindsay Webb,Planner: Lindsay Webb,Planner: MICHAEL DOREN,Planner: MICHAEL DOREN,Planner: Michael Jordan,Planner: Michael Jordan,Planner: Robert Hamernik,Planner: Robert Hamernik,Planner: SABRINA BOERMEESTER,Planner: SABRINA BOERMEESTER,Planner: Steven Grant,Planner: Steven Grant | FINAL | 8398.0884 | 31996.65 | 7355.3148 | 35838.166 | 6604.1269 | 33723.495 | -1042.7737 | 751.1879 | 0.87583 | 1.1137 | 323585.0752 | 320129.4393 | 306656.4008 | -3455.6359 | 13473.0385 | 0.98932 | 1.0439 | 1.2105 | 349907.4736 | 331256.9675 | 29778.0342 | 18650.5061 | 91% | 87.64% | 349820.1984 | 335210.0202 | 335181.1901 | 335489.1008 | - | - | 0.87583 |  |  |  |  | MTD SPI 5 month average is less than ITD SPI.
| Land Warfare & Air Defense | MULTINATIONAL PROGRAMS | 6143 | Australia Land 19 Phase 7B | 44 | Production |  |  |  | Steady | Active | Finance: Kenneth Sullivan,Finance: Kenneth Sullivan,Finance: Megan Petersen,Finance: Megan Petersen,PM: Michelle Tallent,PM: Michelle Tallent,Planner: Michael Hoffman,Planner: Michael Hoffman | FINAL | 2737.1124 | 6704.29 | 2401.8651 | 5440.113 | 2034.4217 | 5816.432 | -335.2473 | 367.4434 | 0.87752 | 1.1806 | 71414.1901 | 67930.214 | 60011.8967 | -3483.9761 | 7918.3173 | 0.95121 | 1.1319 | 1.0465 | 96602.1869 | 87408.7463 | 28671.9728 | 9193.4406 | 70% | 62.12% | 94143.9476 | 85029.8171 | 85341.7076 | 86640.8122 | 0.78483 | - |  |  | 1.0465 | 9193.4406 | 1097830 | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | AREA DEFENSE SYSTEMS | 610Z | Sentinel SDP Kits Production | 64 | Production |  |  |  | Steady | Active | Finance: Joseph Ferrara,Finance: Joseph Ferrara,PM: ANNE ROBLES,PM: ANNE ROBLES,PM: Richard Russell,PM: Richard Russell,Planner: Anna Davydan,Planner: Anna Davydan,Planner: Dayle DaSilva,Planner: Dayle DaSilva,Planner: TIMOTHY REHFELDT,Planner: TIMOTHY REHFELDT | FINAL | 2447.7795 | 1705.3 | 1217.9848 | 1564.646 | 1027.0061 | 1415.811 | -1229.7947 | 190.9788 | 0.49759 | 1.186 | 70586.7992 | 74233.5172 | 68816.699 | 3646.718 | 5416.8182 | 1.0517 | 1.0787 | 1.0098 | 102435.024 | 96743.4416 | 28201.5068 | 5691.5824 | 72% | 67.18% | 102435.024 | 97711.1523 | 93676.0372 | 94960.3424 | 1.0152 | - | 0.49759 |  | 1.0098 |  |  | MTD SPI 5 month average is less than ITD SPI. TCPI 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | NAVAL RADARS | 61F4 | AEGIS AMOD FY21 SSSA KITS | 36 | Production |  |  |  | Deteriorating | Active | Finance: GRACIELA Amundsen,Finance: GRACIELA Amundsen,Finance: JENNA GERBER,Finance: JENNA GERBER,Finance: Jason O'Neil,Finance: Jason O'Neil,Finance: Katie Bittner,Finance: Katie Bittner,Finance: Matthew Logan,Finance: Matthew Logan,PM: Brad Smith,PM: Brad Smith,PM: GRACIELA Amundsen,PM: GRACIELA Amundsen,PM: JENNA GERBER,PM: JENNA GERBER,PM: JONATHAN BAZARIAN,PM: JONATHAN BAZARIAN,PM: Jason O'Neil,PM: Jason O'Neil,PM: Joseph O'Brien,PM: Joseph O'Brien,PM: Katie Bittner,PM: Katie Bittner,Planner: David Lafleur,Planner: David Lafleur,Planner: GRACIELA Amundsen,Planner: GRACIELA Amundsen,Planner: JENNA GERBER,Planner: JENNA GERBER,Planner: JONATHAN BAZARIAN,Planner: JONATHAN BAZARIAN,Planner: Katie Bittner,Planner: Katie Bittner,Planner: Lawrence Bernabei,Planner: Lawrence Bernabei,Planner: Melanie HACKETT,Planner: Melanie HACKETT,Planner: Richard Todd,Planner: Richard Todd | FINAL | 757.5438 | 1490.8 | 521.5802 | 1166.147 | 784.5796 | 654.951 | -235.9636 | -262.9994 | 0.68851 | 0.66479 | 3106.3212 | 3761.6534 | 3884.7711 | 655.3321 | -123.1177 | 1.211 | 0.96831 | 0.9746 | 31188.5943 | 32026.6032 | 27426.9409 | -838.0089 | 12% | 12.46% | 31188.5943 | 31120.6122 | 27274.8462 | 32209.3867 | 0.79688 | 0.28571 |  | 0.66479 | 0.9746 | -838.0089 |  | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Land Warfare & Air Defense | LWS OTHER | 0EPM | LWAD Stinger SVUL | 26 | Production |  |  |  | Improving | Active | Finance: Christopher Butler,Finance: Christopher Butler,PM: Amanda Pena,PM: Amanda Pena,PM: Robert Gourley,PM: Robert Gourley,Planner: Nan Gao,Planner: Nan Gao,Planner: Pamela Blackowiak,Planner: Pamela Blackowiak | FINAL | 739.8888 | 3599.2 | 853.9088 | 3622.963 | 784.9386 | 3410.831 | 114.02 | 68.9702 | 1.1541 | 1.0879 | 9224.26 | 8867.821 | 7289.477 | -356.439 | 1578.344 | 0.96136 | 1.2165 | 1.1169 | 35561.3337 | 31189.2491 | 26693.5127 | 4372.0846 | 25% | 20.5% | 35561.3302 | 30557.0706 | 29231.93 | 30113.8994 | 0.9682 | 0.5 |  | 1.0879 |  |  |  | MTD CPI 5 month average is less than ITD CPI.
| Air Power | PERSISTENT AND STRATEGIC SENSORS | 60JF | QEWR Non Reportable CLINs 2001 2002 3001 CFR | 25 | Production |  |  |  | Steady | Active | Finance: ANDREW MYETTE,Finance: ANDREW MYETTE,Finance: Brian Potter,Finance: Brian Potter,Finance: Thomas Hackett,Finance: Thomas Hackett,PM: Linda Fronsdahl,PM: Linda Fronsdahl,PM: Paul Grigsby,PM: Paul Grigsby,PM: Shari Pletta,PM: Shari Pletta,Planner: Brenda Cubelli,Planner: Brenda Cubelli,Planner: CONSTANCE PELLETIER,Planner: CONSTANCE PELLETIER,Planner: REEJA MATHEW,Planner: REEJA MATHEW | FINAL | 1863.3927 | 4543.328 | 1935.805 | 1046.118 | 1137.4756 | 4001.102 | 72.4124 | 798.3295 | 1.0389 | 1.7018 | 383365.5242 | 371109.9952 | 354423.0339 | -12255.529 | 16686.9614 | 0.96803 | 1.0471 | 1.2872 | 397089.1608 | 374605.9597 | 25979.1655 | 22483.201 | 93% | 89.26% | 398951.1039 | 374871.44 | 379234.0462 | 380053.4045 | 0.98008 | 0.16667 | 1.0389 |  |  | 22483.201 | 6580835.05 | MTD SPI 5 month average is less than ITD SPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | C2 OTHER | 613T | Engineering Support Services for ALD | 5 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: Jeffrey Koshimizu,Finance: Jeffrey Koshimizu,PM: Adrian Kemps,PM: Adrian Kemps,Planner: Andrew Timmons,Planner: Andrew Timmons,Planner: Duy Le,Planner: Duy Le,Planner: Jeffrey Koshimizu,Planner: Jeffrey Koshimizu,Planner: Robert Bakke,Planner: Robert Bakke | FINAL | 1937.655 | 1396.41 | 2014.9618 | 1396.41 | 1879.4552 | 1333 | 77.3067 | 135.5066 | 1.0399 | 1.0721 | 60215.2576 | 60114.3009 | 55050.2591 | -100.9566 | 5064.0418 | 0.99832 | 1.092 | 0.88522 | 81430.1504 | 79129.9955 | 21315.8494 | 2300.1549 | 74% | 67.6% | 81430.1504 | 79405.4782 | 74570.4567 | 74603.2392 | - | - |  | 1.0721 |  | 2300.1549 | 0 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Air Power | STORMBREAKER | 0EHR | EMD F35B Integration | 48 | Development |  |  |  | Improving | Active | Finance: Garrett McGhee,Finance: Garrett McGhee,PM: Cachandra Irving,PM: Cachandra Irving,PM: Lance Lewis,PM: Lance Lewis,Planner: Allan LAGUNA,Planner: Allan LAGUNA,Planner: MIGUEL GUZMAN,Planner: MIGUEL GUZMAN | FINAL | 489.458 | 2518.44 | 718.2953 | 3811.463 | 709.5583 | 3846.859 | 228.8373 | 8.737 | 1.4675 | 1.0123 | 29568.4699 | 29090.534 | 27179.6757 | -477.936 | 1910.8583 | 0.98384 | 1.0703 | 0.91516 | 49327.1654 | 49292.3012 | 20236.6315 | 34.8643 | 59% | 55.1% | 49327.1496 | 48608.8258 | 46087.0316 | 46397.6655 | 0.9358 | 0.88889 |  | 1.0123 |  |  | 1868791 | MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | AREA DEFENSE SYSTEMS | 61EW | KUTLASEE | 12 | DoD - Operations and Support |  |  |  | Improving | Active | Finance: JOSEPH CHIARELLI,Finance: JOSEPH CHIARELLI,Finance: MICHAEL TURTUR,Finance: MICHAEL TURTUR,Finance: Yan Ye,Finance: Yan Ye,PM: Anjani Baswa,PM: Anjani Baswa,PM: Greg Callison,PM: Greg Callison,Planner: David Lafleur,Planner: David Lafleur,Planner: Yoreida Andrieu,Planner: Yoreida Andrieu | FINAL | 3812.0192 | 15888.33 | 3812.0192 | 15888.33 | 2836.2316 | 15930.863 | 0 | 975.7875 | 1 | 1.344 | 32341.6324 | 32341.6324 | 32302.5937 | 0 | 39.0387 | 1 | 1.0012 | 0.98645 | 52339.0913 | 52574.8009 | 19997.4588 | -235.7096 | 62% | 61.72% | 53611.6745 | 50419.4008 | 52275.9141 | 52275.9141 | - | - |  | 1.344 |  | -235.7096 | 2434484.06 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | ANS | 61HG | CEC BLKII Capablity Integration | 12 | Internal |  |  |  | Deteriorating | Active | PM: Daniel Anderson,PM: Daniel Anderson,Planner: Adam Genetti,Planner: Adam Genetti,Planner: Matthew Mchenry,Planner: Matthew Mchenry,Planner: TIM MCCORMICK,Planner: TIM MCCORMICK | FINAL | 1450.4731 | 9502.27 | 1317.3853 | 8579.827 | 1307.9352 | 9414.864 | -133.0878 | 9.45 | 0.90825 | 1.0072 | 2279.7844 | 2352.3166 | 2079.7795 | 72.5322 | 272.5372 | 1.0318 | 1.131 | 1.0032 | 21702.9913 | 21368.2374 | 19350.6746 | 334.7539 | 11% | 9.583% | 21788.9189 | 21395.4191 | 18660.9669 | 19188.5035 | 0.66667 | 0.125 |  |  | 1.0032 | 334.7539 | 2806964 | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | PATRIOT SYSTEMS | 6180 | PMSC CY20 thru 24 | 13 | DoD - Operations and Support |  |  |  | Improving | Active | Finance: QUINTIN FORBES,Finance: QUINTIN FORBES,Finance: Sarah Serio,Finance: Sarah Serio,PM: Ted Urbowicz,PM: Ted Urbowicz,Planner: Andrea Miller,Planner: Andrea Miller,Planner: Dominique Laplanche,Planner: Dominique Laplanche,Planner: Nicole Moore,Planner: Nicole Moore | FINAL | -26.1743 | 4437.14 | 3073.0117 | 8724.77 | 1726.7342 | 5301.1 | 3099.1859 | 1346.2775 | -117.4059 | 1.7797 | 41430.7483 | 40689.509 | 38676.2406 | -741.2394 | 2013.2684 | 0.98211 | 1.0521 | 0.92579 | 59576.3061 | 59076.9932 | 18886.7972 | 499.3129 | 68% | 64.92% | 42551.5579 | 42042.6403 | 56628.5416 | 56955.578 | 0.26316 | - |  |  | 0.92579 | 499.3129 |  | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Land Warfare & Air Defense | PATRIOT SYSTEMS | 60ZT | Sweep IX | 5 | Production |  |  |  | Steady | Active | Finance: Danielle POLCARI-BALBONI,Finance: Danielle POLCARI-BALBONI,Finance: NICHOLAS MUZERALL,Finance: NICHOLAS MUZERALL,Finance: Thomas Hackett,Finance: Thomas Hackett,PM: LINDSAY PENNEY,PM: LINDSAY PENNEY,Planner: Danielle POLCARI-BALBONI,Planner: Danielle POLCARI-BALBONI,Planner: NICHOLAS MUZERALL,Planner: NICHOLAS MUZERALL,Planner: Nicholas Czelewicz,Planner: Nicholas Czelewicz,Planner: Thomas Hackett,Planner: Thomas Hackett | FINAL | 1553.1653 | 6556.61 | 679.8953 | 4690.551 | 785.8966 | 3488.456 | -873.27 | -106.0013 | 0.43775 | 0.86512 | 36463.8133 | 38484.4712 | 36253.0644 | 2020.6579 | 2231.4068 | 1.0554 | 1.0616 | 1.4089 | 56570.1716 | 49090.2129 | 18085.7003 | 7479.9587 | 68% | 64.09% | 56570.1716 | 49090.2129 | 52395.5753 | 53290.1195 | - | - | 0.43775 | 0.86512 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Land Warfare & Air Defense | QATAR PROGRAMS | 60QA | Qatar TA NET FFP | 4 | Development |  |  |  | Steady | Active | Finance: LISA WALLACE,Finance: LISA WALLACE,PM: DAVID MCCORMICK,PM: DAVID MCCORMICK,PM: LADI KEHINDE,PM: LADI KEHINDE,Planner: Alvin Neff,Planner: Alvin Neff,Planner: Anna Davydan,Planner: Anna Davydan,Planner: Brian Martinez,Planner: Brian Martinez,Planner: MICHAEL GILL,Planner: MICHAEL GILL,Planner: Michael Jordan,Planner: Michael Jordan,Planner: SUSAN MAPLES,Planner: SUSAN MAPLES,Planner: Stephen Pike,Planner: Stephen Pike | FINAL | 969.887 | 1993.384 | 825.203 | 1255.464 | 1790.7158 | 2826.612 | -144.684 | -965.5127 | 0.85082 | 0.46082 | 90215.6617 | 90210.1263 | 85338.0659 | -5.5354 | 4872.0604 | 0.99994 | 1.0571 | 1.0442 | 107381.4157 | 101783.1867 | 17171.2894 | 5598.229 | 84% | 79.47% | 107513.5011 | 102876.8313 | 101581.9699 | 101582.9666 | 0.96082 | 0.4 |  | 0.46082 |  |  | 2354643.38 | MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Naval Power | UNDERSEA SYSTEMS (LEGACY) | 616I | ALFS BBP 31 STR Spares | 3 | Production |  |  |  | Improving | Active | PM: Susan Romano,PM: Susan Romano,Planner: David Ponte,Planner: David Ponte,Planner: Mark Purcell,Planner: Mark Purcell,Planner: Richard Todd,Planner: Richard Todd | FINAL | 90.6765 | 445.71 | 214.29 | 495.087 | 148.8306 | 511.638 | 123.6135 | 65.4593 | 2.3632 | 1.4398 | 6162.7133 | 5841.5324 | 4219.3546 | -321.1809 | 1622.1777 | 0.94788 | 1.3845 | 1.0559 | 21430.8788 | 18983.6945 | 15589.3464 | 2447.1843 | 27% | 19.69% | 21430.8788 | 19136.7048 | 15479.5818 | 16098.6951 | 1.5 | - |  | 1.4398 | 1.0559 | 2447.1843 | 57733 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Air Power | PERSISTENT AND STRATEGIC SENSORS | 60JE | QEWR Reportable CLINs 1001 5001 | 120 | Production |  |  |  | Steady | Active | Finance: ANDREW MYETTE,Finance: ANDREW MYETTE,Finance: Brian Potter,Finance: Brian Potter,Finance: Thomas Hackett,Finance: Thomas Hackett,PM: Linda Fronsdahl,PM: Linda Fronsdahl,PM: Paul Grigsby,PM: Paul Grigsby,Planner: Brenda Cubelli,Planner: Brenda Cubelli,Planner: CONSTANCE PELLETIER,Planner: CONSTANCE PELLETIER,Planner: REEJA MATHEW,Planner: REEJA MATHEW | FINAL | 2062.2478 | 5453.12 | 3040.4704 | 3614.79 | 4041.5765 | 11398.562 | 978.2226 | -1001.1061 | 1.4743 | 0.7523 | 595325.9399 | 587207.8751 | 597095.6464 | -8118.0648 | -9887.7713 | 0.98636 | 0.98344 | 0.63402 | 601942.2153 | 620335.3138 | 14734.3402 | -18393.0985 | 98% | 99.19% | 601940.8063 | 615697.0107 | 612078.0926 | 612285.2228 | 0.9839 | 0.25 |  | 0.7523 | 0.63402 | -18393.0985 | -9094060 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 618X | RTC T03 | 33 | Development |  |  |  | Improving | Active | Finance: CHRISTINE LEBRUTO,Finance: CHRISTINE LEBRUTO,Finance: KATHERINE KELLEY,Finance: KATHERINE KELLEY,Finance: Marcus Nichols,Finance: Marcus Nichols,PM: Nikki East,PM: Nikki East,PM: Surya Achalla,PM: Surya Achalla,PM: Wayne Richards,PM: Wayne Richards,PM: Yvette Thomas,PM: Yvette Thomas,Planner: ADAM MCCARTHY,Planner: ADAM MCCARTHY,Planner: Alyssa Broberg,Planner: Alyssa Broberg,Planner: Jereme Coste,Planner: Jereme Coste,Planner: Michael Mirabile,Planner: Michael Mirabile,Planner: Monica Dwyre-Wortman,Planner: Monica Dwyre-Wortman,Planner: Paul Bonin,Planner: Paul Bonin,Planner: Tevian Mazzotta,Planner: Tevian Mazzotta | FINAL | 2697.0923 | 9848.69 | 2991.4492 | 11037.074 | 3062.8485 | 12905.431 | 294.3568 | -71.3993 | 1.1091 | 0.97669 | 65220.073 | 64074.0625 | 63021.9129 | -1146.0105 | 1052.1496 | 0.98243 | 1.0167 | 0.95349 | 77439.7661 | 77039.5719 | 13365.7035 | 400.1941 | 83% | 81.38% | 77911.5033 | 77137.3408 | 76168.1404 | 76403.2701 | 0.80451 | 0.66667 | 1.1091 | 0.97669 |  |  | 274338.17 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | PATRIOT SYSTEMS | 60XE | 1C002900 System Improvement FY18 IDIQ | 4 | Internal |  |  |  | Steady | Active | Finance: Lindsay Webb,Finance: Lindsay Webb,PM: Steven Coscia,PM: Steven Coscia,Planner: JULIA ROGERS,Planner: JULIA ROGERS,Planner: Lindsay Webb,Planner: Lindsay Webb,Planner: Michael Jordan,Planner: Michael Jordan,Planner: SUSAN MAPLES,Planner: SUSAN MAPLES | FINAL | 1798.3659 | 6558.69 | 1789.1362 | 6529.769 | 1920.398 | 7864.765 | -9.2298 | -131.2618 | 0.99487 | 0.93165 | 59881.9448 | 59666.2539 | 52903.6065 | -215.691 | 6762.6474 | 0.9964 | 1.1278 | 1.2747 | 71112.6491 | 61883.1059 | 11446.3952 | 9229.5432 | 84% | 74.39% | 71152.4077 | 61991.3347 | 63052.653 | 63089.3414 | 0.94714 | 0.61905 |  | 0.93165 |  |  | 1795919.69 | MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 618Y | RTC T04 | 9 | Development |  |  |  | Steady | Active | Finance: CHRISTINE LEBRUTO,Finance: CHRISTINE LEBRUTO,Finance: KATHERINE KELLEY,Finance: KATHERINE KELLEY,Finance: Marcus Nichols,Finance: Marcus Nichols,PM: KENNETH MCCURDY,PM: KENNETH MCCURDY,PM: TAMARA TSAVDARIS,PM: TAMARA TSAVDARIS,Planner: Alyssa Broberg,Planner: Alyssa Broberg,Planner: Jereme Coste,Planner: Jereme Coste,Planner: Paul Bonin,Planner: Paul Bonin | FINAL | -583.5484 | -9950.251 | -769.6939 | -9950.251 | 2784.1043 | 11292.562 | -186.1455 | -3553.7982 | 1.319 | -0.27646 | 61941.9348 | 61936.5378 | 58607.8238 | -5.397 | 3328.714 | 0.99991 | 1.0568 | 0.9963 | 73187.8108 | 69900.8485 | 11251.273 | 3286.9623 | 85% | 80.08% | 82814.0606 | 80972.4044 | 69254.4089 | 69255.3366 | 0.98193 | 0.25 |  | -0.27646 | 0.9963 |  | 2168.38 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 61D3 | THAAD LM Phase 2 | 24 | Development |  |  |  | Steady | Active | Finance: Debra Cnockaert,Finance: Debra Cnockaert,Finance: KATHERINE KELLEY,Finance: KATHERINE KELLEY,Finance: Nakia Gallegos,Finance: Nakia Gallegos,Finance: Yan Ye,Finance: Yan Ye,PM: Gregory Thomas,PM: Gregory Thomas,Planner: June Duggan,Planner: June Duggan | FINAL | 471.9605 | 2762.34 | 489.2342 | 2921.88 | 391.535 | 2597.701 | 17.2737 | 97.6992 | 1.0366 | 1.2495 | 5436.3881 | 5419.3163 | 5222.3003 | -17.0718 | 197.0159 | 0.99686 | 1.0377 | 1.0756 | 16190.0354 | 15236.2989 | 10770.7191 | 953.7365 | 33% | 32.26% | 16190.0354 | 15240.3255 | 15601.4566 | 15634.1529 | - | - | 1.0366 |  |  |  |  | MTD SPI 5 month average is less than ITD SPI.
| Land Warfare & Air Defense | UAE PROGRAMS | 610E | UAE Patriot 100 Lot GEMT Missile | 8 | Production |  |  |  | Steady | Active | Finance: Christopher Dicenso,Finance: Christopher Dicenso,Finance: Ryan Hwang,Finance: Ryan Hwang,PM: Brian Gath,PM: Brian Gath,PM: Erik French,PM: Erik French,PM: Tracy Milburn,PM: Tracy Milburn,Planner: Tracy Milburn,Planner: Tracy Milburn | PRELIMINARY | 5.6493 | 27 | -121.1555 | -1070.771 | 1269.6361 | 5274.64 | -126.8049 | -1390.7916 | -21.446 | -0.095425 | 265526.5331 | 258810.4741 | 267699.1415 | -6716.059 | -8888.6674 | 0.97471 | 0.9668 | 0.42041 | 267462.8193 | 288279.9481 | 8652.3452 | -20817.1288 | 97% | 100.1% | 267462.8193 | 288279.9481 | 276648.6455 | 276880.8827 | - | - |  |  | 0.42041 | -20817.1288 | 0 | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Advanced Technology | AMS: ADV PROGRAMS | 0EPC | TBG2 Restart | 49 | DoD - Technology Maturation and Risk Reduction |  |  |  | Steady | Active | Finance: BENJAMIN JAEDECKE,Finance: BENJAMIN JAEDECKE,Finance: Carlo Pedrazzini,Finance: Carlo Pedrazzini,Finance: Jonathan Serie,Finance: Jonathan Serie,Finance: Kevin Johnson,Finance: Kevin Johnson,Finance: PAVAGADA JAIRAM,Finance: PAVAGADA JAIRAM,PM: Carlo Pedrazzini,PM: Carlo Pedrazzini,PM: Janet Laird,PM: Janet Laird,PM: Jonathan Serie,PM: Jonathan Serie,PM: Lance Lewis,PM: Lance Lewis,PM: Nathan Szyba,PM: Nathan Szyba,Planner: CHARLES KENNA,Planner: CHARLES KENNA,Planner: Carlo Pedrazzini,Planner: Carlo Pedrazzini,Planner: Helen Trujillo,Planner: Helen Trujillo,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Jonathan Serie,Planner: Jonathan Serie,Planner: Lance Lewis,Planner: Lance Lewis,Planner: Lisa SILVA,Planner: Lisa SILVA,Planner: Marilyn Buckelew,Planner: Marilyn Buckelew,Planner: Seth Van Norman,Planner: Seth Van Norman,Planner: VIRGINIA WILKINSON,Planner: VIRGINIA WILKINSON | FINAL | 650.2167 | 2098.71 | 897.1479 | 1650.061 | 1236.3217 | 2349.24 | 246.9312 | -339.1738 | 1.3798 | 0.72566 | 140645.2768 | 137364.7159 | 139076.0276 | -3280.5609 | -1711.3117 | 0.97667 | 0.9877 | 1.7094 | 146007.1377 | 144131.8665 | 8642.4217 | 1875.2712 | 94% | 95.25% | 146007.1377 | 149244.3286 | 147826.118 | 148035.0888 | 0.94635 | 1 | 1.3798 | 0.72566 |  | 1875.2712 |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Land Warfare & Air Defense | QATAR PROGRAMS | 60SN | Qatar Depot Ops FFP | 1 | Development |  |  |  | Steady | Active | Finance: LISA WALLACE,Finance: LISA WALLACE,PM: Melissa Hughes,PM: Melissa Hughes,PM: STEPHEN CONNOR,PM: STEPHEN CONNOR,PM: Shawn Steele,PM: Shawn Steele,PM: Thomas Mcgovern,PM: Thomas Mcgovern,Planner: Ani Days,Planner: Ani Days,Planner: Dominique Laplanche,Planner: Dominique Laplanche,Planner: GREG BIONELLI,Planner: GREG BIONELLI | FINAL | 481.7278 | 1177.19 | 481.7278 | 1177.19 | 622.4596 | 1840.183 | 0 | -140.7317 | 1 | 0.77391 | 18094.2978 | 18094.2978 | 17698.9423 | 0 | 395.3555 | 1 | 1.0223 | 1.0377 | 25994.7461 | 25312.6905 | 7900.4483 | 682.0557 | 70% | 68.09% | 25994.7461 | 25380.4822 | 25426.768 | 25426.768 | 0.99415 | - |  | 0.77391 |  |  | 0 | MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | C2 OTHER | 613Z | ESS for ALD IDS IOT | 5 | Internal |  |  |  | Steady | Active | Finance: Andrew Timmons,Finance: Andrew Timmons,Finance: Jeffrey Koshimizu,Finance: Jeffrey Koshimizu,PM: Derek Simpson,PM: Derek Simpson,Planner: Andrew Timmons,Planner: Andrew Timmons,Planner: Duy Le,Planner: Duy Le,Planner: Jeffrey Koshimizu,Planner: Jeffrey Koshimizu,Planner: Robert Bakke,Planner: Robert Bakke | FINAL | 950.273 | 3917.46 | 954.0999 | 3942.273 | 798.1467 | 4039.211 | 3.8269 | 155.9533 | 1.004 | 1.1954 | 32898.676 | 32953.0959 | 25986.2457 | 54.4199 | 6966.8502 | 1.0017 | 1.2681 | 0.7901 | 40652.1568 | 35730.6338 | 7699.0609 | 4921.523 | 81% | 63.92% | 40652.1568 | 36061.6761 | 32047.5665 | 32057.593 | - | - |  |  | 0.7901 |  |  | TCPI 5 month average is less than the furthest month in the 5 month forecast.
| Advanced Technology | AS: S&T PORTFOLIO | 618L | SESU | 12 | Development |  |  |  | Deteriorating | Active | PM: David Altman,PM: David Altman,Planner: CHRISTINA CORACCIO,Planner: CHRISTINA CORACCIO,Planner: Judith Kopeloff,Planner: Judith Kopeloff | FINAL | 1111.4358 | 3601.71 | 960.8885 | 3647.509 | 1265.717 | 3628.466 | -150.5473 | -304.8285 | 0.86455 | 0.75917 | 15454.7905 | 15744.6921 | 16229.6625 | 289.9016 | -484.9704 | 1.0188 | 0.97012 | 0 | 22560.4236 | 16229.6625 | 6815.7314 | 6330.761 | 70% | 71.94% | 22560.4236 | 14963.9455 | 23125.9719 | 23255.3331 | 0.69767 | - |  |  | 0 | 6330.761 |  | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Strategic Missile Defense | MISSILE DEFENSE | 6137 | THAAD LM KSA Phase 1 | 23 | Development |  |  |  | Deteriorating | Active | Finance: KATHERINE KELLEY,Finance: KATHERINE KELLEY,Finance: Marcus Nichols,Finance: Marcus Nichols,Finance: Nakia Gallegos,Finance: Nakia Gallegos,Finance: Yan Ye,Finance: Yan Ye,PM: Gregory Thomas,PM: Gregory Thomas,Planner: June Duggan,Planner: June Duggan | FINAL | 186.5155 | 966.14 | 186.5155 | 966.14 | 149.3425 | 881.205 | 0 | 37.173 | 1 | 1.2489 | 6776.0405 | 6742.762 | 5479.8068 | -33.2785 | 1262.9552 | 0.99509 | 1.2305 | 1.0462 | 13323.477 | 11770.2187 | 6580.715 | 1553.2582 | 51% | 41.13% | 13372.8689 | 11864.8647 | 10827.9189 | 10854.3141 | - | - |  |  | 1.0462 | 1553.2582 |  | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Air Power | COMMAND AND CONTROL | 60D4 | QATAR ADOC Contract 2 FFP | 7 | Development |  |  |  | Improving | Active | Finance: ERIN LEONARD,Finance: ERIN LEONARD,Finance: Kathryn Morse,Finance: Kathryn Morse,PM: Abigail Capano,PM: Abigail Capano,PM: Glenn Ouyang,PM: Glenn Ouyang,Planner: CHRISTINA CORACCIO,Planner: CHRISTINA CORACCIO,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Jackie Hollandsworth,Planner: Jackie Hollandsworth,Planner: KEVIN CRAIG,Planner: KEVIN CRAIG,Planner: TIM MCCORMICK,Planner: TIM MCCORMICK,Planner: William Marcley,Planner: William Marcley | FINAL | 79.3551 | 411.97 | 578.6906 | 956.32 | 517.897 | 251.257 | 499.3355 | 60.7936 | 7.2924 | 1.1174 | 56692.4369 | 55034.5734 | 52265.1593 | -1657.8635 | 2769.4141 | 0.97076 | 1.053 | 0.91966 | 60153.8495 | 57831.6267 | 5119.2761 | 2322.2228 | 91% | 86.89% | 60153.8502 | 57170.5641 | 57126.8265 | 57273.2795 | 0.9874 | 0.15385 | 7.2924 |  | 0.91966 | 2322.2228 |  | MTD SPI 5 month average is less than ITD SPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Air Power | COMMAND AND CONTROL | 60D5 | QATAR ADOC Contract 2 Cost Type | 42 | Development |  |  |  | Steady | Active | Finance: ERIN LEONARD,Finance: ERIN LEONARD,PM: Andrew Witkowski,PM: Andrew Witkowski,PM: GRACIELA Amundsen,PM: GRACIELA Amundsen,PM: Glenn Ouyang,PM: Glenn Ouyang,Planner: Jackie Hollandsworth,Planner: Jackie Hollandsworth,Planner: KEVIN CRAIG,Planner: KEVIN CRAIG,Planner: TIM MCCORMICK,Planner: TIM MCCORMICK,Planner: William Marcley,Planner: William Marcley | FINAL | 1199.2779 | 5321.49 | 1112.8006 | 5301.8 | 1379.4487 | 5936.972 | -86.4773 | -266.6481 | 0.92789 | 0.8067 | 254107.4723 | 253212.8921 | 251993.8598 | -894.5802 | 1219.0323 | 0.99648 | 1.0048 | 0.90859 | 258182.3908 | 257463.313 | 4969.4987 | 719.0778 | 98% | 97.6% | 257427.0651 | 256691.5163 | 256939.434 | 256956.9063 | 0.98858 | 0.30769 |  |  | 0.90859 | 719.0778 | 9952546.25 | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | KUWAIT | 613H | Kuwait CRG and Launcher Kits | 2 | Production |  |  |  | Improving | Active | Finance: Cheryl Gaudet,Finance: Cheryl Gaudet,Finance: John Lehtinen,Finance: John Lehtinen,Finance: Joseph Galli,Finance: Joseph Galli,Finance: KIMBERLY KMIEC,Finance: KIMBERLY KMIEC,PM: Stefanie Chiou,PM: Stefanie Chiou,Planner: Andrea Miller,Planner: Andrea Miller,Planner: Anna Davydan,Planner: Anna Davydan,Planner: Joseph Galli,Planner: Joseph Galli,Planner: MATTHEW RONDEAU,Planner: MATTHEW RONDEAU,Planner: Melanie Parente,Planner: Melanie Parente,Planner: Prashant Navkal,Planner: Prashant Navkal | FINAL | 233.0864 | 962.45 | 292.0695 | 1559.904 | 417.3591 | 2478.825 | 58.9831 | -125.2896 | 1.2531 | 0.6998 | 19798.2708 | 19024.6439 | 18460.8468 | -773.627 | 563.7971 | 0.96092 | 1.0305 | 0.88748 | 23781.2749 | 23820.5632 | 4756.631 | -39.2883 | 80% | 77.63% | 23781.2749 | 23769.4052 | 23076.5147 | 23264.2083 | 1.0114 | 0.71429 |  | 0.6998 | 0.88748 | -39.2883 | 0 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | SM3 IIA | 0EGV | SM3 BLK IIA DEV | 114 | Development |  |  |  | Steady | Active | Finance: Brad Slentz,Finance: Brad Slentz,Finance: Darin Esplin,Finance: Darin Esplin,Finance: Jonathan McMillen,Finance: Jonathan McMillen,Finance: Laura Wanzer,Finance: Laura Wanzer,PM: Craig Schafer,PM: Craig Schafer,PM: Elena Efremova,PM: Elena Efremova,PM: Erick Elkins,PM: Erick Elkins,PM: Laura Pekny,PM: Laura Pekny,PM: MATTHEW MCGUIRE,PM: MATTHEW MCGUIRE,PM: Marco Edmondson,PM: Marco Edmondson,PM: Melissa Elliott,PM: Melissa Elliott,PM: Michael Allison,PM: Michael Allison,PM: Sharon Walk,PM: Sharon Walk,PM: Shelley Moehle,PM: Shelley Moehle,PM: Timothy Keeland,PM: Timothy Keeland,Planner: Alexander Wojack,Planner: Alexander Wojack,Planner: CHARLES KENNA,Planner: CHARLES KENNA,Planner: Christopher Elliott,Planner: Christopher Elliott,Planner: Erik Hammer,Planner: Erik Hammer,Planner: Helen Trujillo,Planner: Helen Trujillo,Planner: Kelsi Dornquast,Planner: Kelsi Dornquast,Planner: Matthew Kirk,Planner: Matthew Kirk,Planner: Michael Tucker,Planner: Michael Tucker,Planner: Sara Wilson,Planner: Sara Wilson,Planner: TIM MCCORMICK,Planner: TIM MCCORMICK | FINAL | 1886.0408 | 10780.56 | 1543.3609 | 8815.129 | 1434.0476 | 8116.321 | -342.6799 | 109.3133 | 0.81831 | 1.0762 | 1728569.572 | 1726324.7212 | 1783490.0256 | -2244.8508 | -57165.3044 | 0.9987 | 0.96795 | 2.2068 | 1730891.2761 | 1785559.2924 | 4566.5549 | -54668.0163 | 99% | 103% | 1730603.0502 | 1786014.7104 | 1788207.7968 | 1788213.9316 | 0.99055 | - | [7 empty] | 1034723.9121 | 1034723.9121 | 165278.0882 | 1.1921e-10 | 869445.824 | 1 | 6.2605
| Air Power | AWS: ADV PROGRAMS | 0ERE | HTS FTE Phase 5 | 38 | Development |  |  |  | Steady | Active | PM: Galen Goldsmith,PM: Galen Goldsmith,Planner: Daniel Duran,Planner: Daniel Duran | FINAL | 178.6836 | 840.14 | 177.9047 | 765.181 | 147.1014 | 577.666 | -0.77888 | 30.8033 | 0.99564 | 1.2094 | 628.8701 | 625.8781 | 486.7878 | -2.992 | 139.0903 | 0.99524 | 1.2857 | 1.0041 | 4703.3175 | 4547.4829 | 4077.4394 | 155.8346 | 13% | 10.35% | 4703.3175 | 4577.1977 | 3658.0887 | 3673.2491 | 1 | 1
| Land Warfare & Air Defense | KUWAIT | 60HQ | 1P000392 Kuwait Modernization | 46 | Production |  |  |  | Steady | Active | Finance: John Lehtinen,Finance: John Lehtinen,Finance: KIMBERLY KMIEC,Finance: KIMBERLY KMIEC,PM: John Lehtinen,PM: John Lehtinen,PM: KIMBERLY KMIEC,PM: KIMBERLY KMIEC,PM: Stefanie Chiou,PM: Stefanie Chiou,Planner: Alex Valenti,Planner: Alex Valenti,Planner: Alvin Neff,Planner: Alvin Neff,Planner: Andrea Miller,Planner: Andrea Miller,Planner: Brian Martinez,Planner: Brian Martinez,Planner: Catherine Arno,Planner: Catherine Arno,Planner: JAMES RICHARD,Planner: JAMES RICHARD,Planner: JULIA ROGERS,Planner: JULIA ROGERS,Planner: Jessica Vanco,Planner: Jessica Vanco,Planner: John Lehtinen,Planner: John Lehtinen,Planner: KIMBERLY KMIEC,Planner: KIMBERLY KMIEC,Planner: Kennedy Fredericks,Planner: Kennedy Fredericks,Planner: Lee Brucks,Planner: Lee Brucks,Planner: MATTHEW RONDEAU,Planner: MATTHEW RONDEAU,Planner: Monique Larose,Planner: Monique Larose,Planner: Nicole Moore,Planner: Nicole Moore,Planner: SUMEET LEWIS,Planner: SUMEET LEWIS,Planner: TIM MCCORMICK,Planner: TIM MCCORMICK,Planner: Zubair Maqsood,Planner: Zubair Maqsood | FINAL | 1485.0387 | 2615.02 | 1396.0112 | 2587.02 | 694.7002 | 1737.272 | -89.0275 | 701.311 | 0.94005 | 2.0095 | 294566.1296 | 294626.0234 | 258803.7115 | 59.8939 | 35822.312 | 1.0002 | 1.1384 | 1.8506 | 298666.4359 | 260987.0269 | 4040.4125 | 37679.409 | 99% | 86.65% | 299415.3961 | 261264.8563 | 262352.1461 | 262352.8676 | 0.98489 | 1 | 0.94005 |  |  |  |  | MTD SPI 5 month average is less than ITD SPI.
| Strategic Missile Defense | C2 OTHER | 6179 | Romania Poland Artillery C2 AFATDS | 31 | Development |  |  |  | Improving | Active | Finance: Suzanne Braddock,Finance: Suzanne Braddock,PM: Stephen Bohan,PM: Stephen Bohan,PM: Waseem Hanna,PM: Waseem Hanna,Planner: Dale Principe,Planner: Dale Principe,Planner: Dayle DaSilva,Planner: Dayle DaSilva,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: ZACHARY SHAW,Planner: ZACHARY SHAW | FINAL | 131.1514 | 295.79 | 173.684 | 419.735 | 100.754 | 328.332 | 42.5326 | 72.93 | 1.3243 | 1.7238 | 17171.6255 | 16978.1265 | 13516.5214 | -193.499 | 3461.605 | 0.98873 | 1.2561 | 0.78783 | 20988.0383 | 18606.3607 | 4009.9118 | 2381.6776 | 81% | 64.4% | 20797.418 | 18437.8208 | 16708.8677 | 16745.2508 | 0.93578 | 1 |  | 1.7238 | 0.78783 | 2381.6776 |  | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Strategic Missile Defense | C2 OTHER | 612R | AFMC3AS Nexter P02 | 37 | Development |  |  |  | Steady | Active | PM: Gregg Osborn,PM: Gregg Osborn,Planner: Dayle DaSilva,Planner: Dayle DaSilva,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: ZACHARY SHAW,Planner: ZACHARY SHAW | FINAL | 131.9185 | 3.55 | 166.1537 | 4.437 | 165.2962 | 495.704 | 34.2352 | 0.85752 | 1.2595 | 1.0052 | 12705.1791 | 12665.0946 | 11252.8563 | -40.0845 | 1412.2383 | 0.99685 | 1.1255 | 0.78013 | 15980.6951 | 15502.9065 | 3315.6005 | 477.7886 | 79% | 70.42% | 15980.6951 | 15497.9776 | 14198.7464 | 14208.07 | 0.97333 | - |  | 1.0052 | 0.78013 | 477.7886 | 1162803 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | AREA DEFENSE SYSTEMS | 614M | ATSP4 TO 1616 SPDRACR | 14 | DoD - Engineering Manufacturing and Development |  |  |  | Steady | Active | PM: Shawn Steele,PM: Shawn Steele,PM: TIMOTHY STELLY,PM: TIMOTHY STELLY,Planner: Yoreida Andrieu,Planner: Yoreida Andrieu | FINAL | 1768.0236 | 10057.6 | 1674.0771 | 9524.35 | 1749.4941 | 10702.138 | -93.9465 | -75.4169 | 0.94686 | 0.95689 | 103972.7766 | 101442.8231 | 104562.4253 | -2529.9535 | -3119.6022 | 0.97567 | 0.97017 | 12.9057 | 104690.7682 | 104814.092 | 3247.9451 | -123.3238 | 97% | 99.88% | 104690.7682 | 104876.8697 | 107910.2522 | 107993.746 | 0.97981 | 0.47826 | 0.94686 | 0.95689 |  | -123.3238 | 0 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | ANS | 60EJ | DDG 1002 Ship Set 3 Non Reportable | 25 | Production |  |  |  | Steady | Active | Finance: Leif Sorenson,Finance: Leif Sorenson,PM: Mark Silveira,PM: Mark Silveira,PM: Timothy Sutherland,PM: Timothy Sutherland,Planner: Anthony Muhl,Planner: Anthony Muhl | FINAL | 0 | 0 | 150.3094 | 1302.322 | 379.4508 | 2269.109 | 150.3094 | -229.1414 | 0 | 0.39612 | 321671.7071 | 318945.8607 | 300519.5518 | -2725.8464 | 18426.3089 | 0.99153 | 1.0613 | 0.9906 | 321671.7071 | 303271.2552 | 2725.8464 | 18400.4518 | 99% | 93.42% | 321671.7071 | 303226.095 | 303087.9192 | 303109.8695 | - | - |  | 0.39612 |  | 18400.4518 | 0 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Advanced Technology | AMS: ADV PROGRAMS | 0EQM | CPS Blk2 new | 39 | Development |  |  |  | Steady | Active | Finance: BENJAMIN JAEDECKE,Finance: BENJAMIN JAEDECKE,Finance: Carlo Pedrazzini,Finance: Carlo Pedrazzini,Finance: Ivana Carreon,Finance: Ivana Carreon,PM: Carlo Pedrazzini,PM: Carlo Pedrazzini,PM: Janet Laird,PM: Janet Laird,PM: Michael Franks,PM: Michael Franks,PM: VERONICA SISEMORE,PM: VERONICA SISEMORE,Planner: AMY JOYCE,Planner: AMY JOYCE,Planner: Carlo Pedrazzini,Planner: Carlo Pedrazzini,Planner: David Lafleur,Planner: David Lafleur,Planner: Kari Jones,Planner: Kari Jones,Planner: Rhoda Doan,Planner: Rhoda Doan | FINAL | 500.0267 | 1936.87 | 415.3656 | 1603.97 | 519.5225 | 1545.764 | -84.6611 | -104.1569 | 0.83069 | 0.79951 | 42259.0412 | 41805.0124 | 42384.6263 | -454.0288 | -579.6139 | 0.98926 | 0.98632 | 0.98417 | 44310.9991 | 44930.9326 | 2505.9867 | -619.9335 | 94% | 95.65% | 44302.1284 | 44788.4884 | 44925.3577 | 44952.9517 | 0.58824 | 0.78261 | 0.83069 | 0.79951 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Advanced Technology | AS: S&T PORTFOLIO | 6163 | Hawkeye Phase 2 | 25 | Development |  |  |  | Steady | Active | Finance: Andrew Papanicolau,Finance: Andrew Papanicolau,Finance: Edward Petruccelli,Finance: Edward Petruccelli,Finance: Trisha Guglielmo,Finance: Trisha Guglielmo,PM: JESSICA KELLY,PM: JESSICA KELLY,PM: John Bergeron,PM: John Bergeron,Planner: CHARLES KENNA,Planner: CHARLES KENNA,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Joseph Morin,Planner: Joseph Morin,Planner: Judith Kopeloff,Planner: Judith Kopeloff,Planner: Teresa Rudolph,Planner: Teresa Rudolph | FINAL | 205.8991 | 1158.51 | 334.766 | 1315.604 | 556.3207 | 1936.303 | 128.8668 | -221.5547 | 1.6259 | 0.60175 | 49030.6236 | 48774.762 | 50411.6602 | -255.8615 | -1636.8982 | 0.99478 | 0.96753 | 1.7383 | 51259.2067 | 51840.8733 | 2484.4447 | -581.6666 | 95% | 98.35% | 51101.7865 | 51986.1351 | 52979.4837 | 52992.954 | 0.98565 | - |  | 0.60175 |  | -581.6666 | 815621 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 604K | THAAD UAE Fixed Price | 81 | Production |  |  |  | Steady | Active | Finance: CARRIE UEDA,Finance: CARRIE UEDA,Finance: KATHERINE KELLEY,Finance: KATHERINE KELLEY,Finance: MICHAEL DOREN,Finance: MICHAEL DOREN,PLANNER: Bruce Reppucci,PLANNER: Bruce Reppucci,PM: Danial Ashmun,PM: Danial Ashmun,Planner: Akilah Couvson,Planner: Akilah Couvson,Planner: Bridget Harrod,Planner: Bridget Harrod,Planner: CONSTANCE PELLETIER,Planner: CONSTANCE PELLETIER,Planner: JACKIE RYAN,Planner: JACKIE RYAN,Planner: Jason Iovanna,Planner: Jason Iovanna,Planner: June Duggan,Planner: June Duggan,Planner: Michael Mirabile,Planner: Michael Mirabile,Planner: Paul Bonin,Planner: Paul Bonin,Planner: Sean Liddell,Planner: Sean Liddell,Planner: Wendy Farrell,Planner: Wendy Farrell,Planner: ZACHARY SHAW,Planner: ZACHARY SHAW | PRELIMINARY | 79.6451 | 0 | 355.477 | 446.107 | 7.2299 | 78.853 | 275.8319 | 348.2472 | 4.4633 | 49.1679 | 445413.9449 | 444826.4378 | 425669.331 | -587.5072 | 19157.1067 | 0.99868 | 1.045 | 190.8519 | 447233.3346 | 425681.9424 | 2406.8968 | 21551.3922 | 99% | 95.18% | 451468.7308 | 429304.8688 | 427972.5713 | 427975.6133 | - | - |  |  | 190.8519 |  | 0 | TCPI 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | CRDP | 0EK4 | METEOR | 38 | DoD - Engineering Manufacturing and Development |  |  |  | Steady | Active | PM: AMANDEEP DHALIWAL,PM: AMANDEEP DHALIWAL,PM: Abel Ghanooni,PM: Abel Ghanooni,PM: Emily Kose,PM: Emily Kose,Planner: Pamela Blackowiak,Planner: Pamela Blackowiak | FINAL | 1415.3285 | 7993.72 | 1314.8327 | 6569.546 | 837.8437 | 2337.723 | -100.4958 | 476.989 | 0.92899 | 1.5693 | 144817.4665 | 143897.6126 | 144037.6227 | -919.8539 | -140.01 | 0.99365 | 0.99903 | 0.94873 | 146254.3646 | 146521.7308 | 2356.7519 | -267.3663 | 98% | 98.48% | 146254.3646 | 146960.736 | 146396.6677 | 146411.7477 | 0.99772 | 0.33333 | 0.92899 |  |  |  |  | MTD SPI 5 month average is less than ITD SPI.
| Land Warfare & Air Defense | EUCOM PROGRAMS | 60SX | Romania Patriot | 7 | Production |  |  |  | Steady | Active | Finance: JESSICA KING CERNIGLIA,Finance: JESSICA KING CERNIGLIA,Finance: PRESTON CALLANDER,Finance: PRESTON CALLANDER,PM: Patrick Griffin,PM: Patrick Griffin,PM: Tracy Milburn,PM: Tracy Milburn,Planner: Alvin Neff,Planner: Alvin Neff,Planner: Andrea Miller,Planner: Andrea Miller,Planner: Brian Martinez,Planner: Brian Martinez,Planner: Courtney Koldys,Planner: Courtney Koldys,Planner: JAMES RICHARD,Planner: JAMES RICHARD,Planner: Joaquin Casanova,Planner: Joaquin Casanova,Planner: Lee Brucks,Planner: Lee Brucks,Planner: MATTHEW RONDEAU,Planner: MATTHEW RONDEAU,Planner: Melanie Parente,Planner: Melanie Parente,Planner: Stephen Pike,Planner: Stephen Pike,Planner: Tracy Milburn,Planner: Tracy Milburn | FINAL | 297.8723 | 1107.85 | 2083.3496 | 11915.049 | 1258.0014 | 7124.882 | 1785.4773 | 825.3482 | 6.9941 | 1.6561 | 315283.0362 | 313796.784 | 302176.3076 | -1486.2522 | 11620.4764 | 0.99529 | 1.0385 | 0.32092 | 315829.3121 | 308509.8129 | 2032.528 | 7319.4991 | 99% | 95.68% | 315829.3121 | 307970.0926 | 304133.5674 | 304142.8376 | 0.99049 | - |  |  | 0.32092 | 7319.4991 | 703625 | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | ANS | 6142 | TSA CLIN 0008 PIO Spares | 7 | Production |  |  |  | Steady | Active | Finance: JOSEPH BOLTON,Finance: JOSEPH BOLTON,Finance: Leif Sorenson,Finance: Leif Sorenson,Finance: Minh Luong,Finance: Minh Luong,PM: Mark Silveira,PM: Mark Silveira,PM: Minh Luong,PM: Minh Luong,Planner: Anthony Muhl,Planner: Anthony Muhl,Planner: Minh Luong,Planner: Minh Luong | FINAL | 44.5089 | 235.55 | 39.2516 | 208.67 | 70.8184 | 357.731 | -5.2573 | -31.5668 | 0.88188 | 0.55426 | 32451.285 | 32130.4474 | 28445.6371 | -320.8377 | 3684.8103 | 0.99011 | 1.1295 | 0 | 34016.9242 | 28445.6371 | 1886.4768 | 5571.2871 | 94% | 83.62% | 34016.9242 | 29983.6806 | 30115.7674 | 30132.4444 | 0.97368 | - | 0.88188 |  |  |  | 0 | MTD SPI 5 month average is less than ITD SPI. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | PATRIOT SYSTEMS | 61D2 | AMDC TO2 | 24 | Development |  |  |  | Steady | Active | Finance: Suzanne Braddock,Finance: Suzanne Braddock,PM: Heather Reeves,PM: Heather Reeves,Planner: David Lafleur,Planner: David Lafleur,Planner: JULIA ROGERS,Planner: JULIA ROGERS,Planner: Lee Brucks,Planner: Lee Brucks,Planner: SUSAN MAPLES,Planner: SUSAN MAPLES,Planner: Stephanie Carter,Planner: Stephanie Carter,Planner: Suzanne Braddock,Planner: Suzanne Braddock | FINAL | 2554.7578 | 13722.72 | 2776.4102 | 15383.823 | 2922.8436 | 16142.282 | 221.6524 | -146.4334 | 1.0868 | 0.9499 | 29550.1986 | 29050.6024 | 28761.3509 | -499.5961 | 289.2516 | 0.98309 | 1.0101 | 1.0056 | 30729.2467 | 30430.5706 | 1678.6443 | 298.6761 | 95% | 93.6% | 30704.2826 | 30287.7868 | 30423.2812 | 30451.8622 | 0.91935 | 0.77778 |  | 0.9499 |  | 298.6761 |  | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Strategic Missile Defense | C2 OTHER | 61CH | Korea MCRC | 18 | Production |  |  |  | Steady | Active | PM: Nesrine Ibrahim,PM: Nesrine Ibrahim,Planner: Robert Bakke,Planner: Robert Bakke | FINAL | 545.9473 | 1973.51 | 529.7413 | 2114.825 | 460.4958 | 969.809 | -16.2061 | 69.2455 | 0.97032 | 1.1504 | 8514.9385 | 8230.9025 | 6056.1505 | -284.036 | 2174.7519 | 0.96664 | 1.3591 | 0.56132 | 9645.8599 | 8576.9408 | 1414.9574 | 1068.9191 | 85% | 62.78% | 9645.8599 | 8520.2237 | 7097.2508 | 7133.1776 | 0.82192 | 0.9 |  | 1.1504 | 0.56132 |  |  | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast.
| Strategic Missile Defense | MISSILE DEFENSE | 6105 | THAAD UAE A5 | 31 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: Debra Cnockaert,Finance: Debra Cnockaert,Finance: KATHERINE KELLEY,Finance: KATHERINE KELLEY,Finance: Nakia Gallegos,Finance: Nakia Gallegos,Finance: Yan Ye,Finance: Yan Ye,PM: Gregory Thomas,PM: Gregory Thomas,Planner: June Duggan,Planner: June Duggan,Planner: Yan Ye,Planner: Yan Ye | FINAL | 70.5355 | 406.84 | 70.5355 | 406.84 | 72.258 | 408.411 | 0 | -1.7224 | 1 | 0.97616 | 10600.3341 | 10599.9587 | 10244.3087 | -0.37539 | 355.65 | 0.99996 | 1.0347 | 1.098 | 11981.8769 | 11502.9307 | 1381.9182 | 478.9463 | 88% | 85.5% | 10954.9222 | 10290.1987 | 11579.8608 | 11579.9081 | - | - |  | 0.97616 |  | 478.9463 | 74290 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Air Power | AMRAAM | 0EHN | AMRAAM ER New IOT | 43 | Development |  |  |  | Steady | Active | Finance: Carlo Pedrazzini,Finance: Carlo Pedrazzini,Finance: HEATHER SIMPSON,Finance: HEATHER SIMPSON,Finance: Hannah Winston,Finance: Hannah Winston,PM: Hannah Winston,PM: Hannah Winston,PM: Jennifer Walker,PM: Jennifer Walker,Planner: AMY JOYCE,Planner: AMY JOYCE,Planner: Carlo Pedrazzini,Planner: Carlo Pedrazzini,Planner: Hannah Winston,Planner: Hannah Winston,Planner: Kari Jones,Planner: Kari Jones,Planner: Scott Huntley,Planner: Scott Huntley,Planner: Susan Lansey,Planner: Susan Lansey | FINAL | 184.893 | 1062.98 | 238.9662 | 2178.88 | 782.2567 | 4931.345 | 54.0732 | -543.2904 | 1.2925 | 0.30548 | 78563.56 | 77626.4 | 74903.6976 | -937.16 | 2722.7024 | 0.98807 | 1.0363 | 2.5468 | 78913.8261 | 75409.2077 | 1287.4261 | 3504.6184 | 98% | 94.92% | 78913.8261 | 74984.1768 | 76145.968 | 76160.9655 | 0.96715 | 0.36842 | 1.2925 | 0.30548 |  | 3504.6184 | 0 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | PATRIOT SYSTEMS | 61DN | Tech Pubs CY21 25 | 60 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: Cesar Pellerano,Finance: Cesar Pellerano,Finance: Cheryl Gaudet,Finance: Cheryl Gaudet,Finance: Colleen McAlpine,Finance: Colleen McAlpine,Finance: DAVID LEE,Finance: DAVID LEE,Finance: Jonathan Rutups,Finance: Jonathan Rutups,Finance: Kara Lodor,Finance: Kara Lodor,Finance: Marcelo Montoya,Finance: Marcelo Montoya,Finance: NATE OEUNG,Finance: NATE OEUNG,Finance: QUINTIN FORBES,Finance: QUINTIN FORBES,Finance: Samuel Baer,Finance: Samuel Baer,Finance: Sarah Serio,Finance: Sarah Serio,PM: Cheryl Norsworthy,PM: Cheryl Norsworthy,PM: Raymond Villavicencio,PM: Raymond Villavicencio,PM: Richard Anz,PM: Richard Anz,Planner: Brian Martinez,Planner: Brian Martinez,Planner: David Lafleur,Planner: David Lafleur,Planner: Dominique Laplanche,Planner: Dominique Laplanche,Planner: MATTHEW RONDEAU,Planner: MATTHEW RONDEAU | FINAL | 475.1841 | 475.52 | 475.1841 | 475.52 | 489.8503 | 727.165 | 0 | -14.6662 | 1 | 0.97006 | 4169.0802 | 4169.0802 | 4000.2482 | 0 | 168.832 | 1 | 1.0422 | 0.88047 | 5295.5727 | 5279.6646 | 1126.4925 | 15.9081 | 79% | 75.54% | 5295.5727 | 5268.6772 | 5081.122 | 5081.122 | - | - |  | 0.97006 | 0.88047 |  | 121 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | NAVAL RADARS | 60GH | AEGIS US | 72 | Production |  |  |  | Steady | Active | Finance: JENNA GERBER,Finance: JENNA GERBER,Finance: JONATHAN BAZARIAN,Finance: JONATHAN BAZARIAN,Finance: Jason O'Neil,Finance: Jason O'Neil,PM: Brad Smith,PM: Brad Smith,PM: JONATHAN BAZARIAN,PM: JONATHAN BAZARIAN,PM: Jason O'Neil,PM: Jason O'Neil,PM: Joseph O'Brien,PM: Joseph O'Brien,Planner: JENNA GERBER,Planner: JENNA GERBER,Planner: Lawrence Bernabei,Planner: Lawrence Bernabei,Planner: Richard Todd,Planner: Richard Todd | FINAL | 11.4914 | 50.2 | 6.3638 | 6 | 53.3333 | 230.769 | -5.1276 | -46.9696 | 0.55378 | 0.11932 | 141265.2046 | 140736.097 | 125177.536 | -529.1076 | 15558.561 | 0.99625 | 1.1243 | 1.2866 | 141708.7375 | 125933.4846 | 972.6405 | 15775.2529 | 99% | 88.33% | 141708.7375 | 125898.2106 | 126042.6499 | 126045.9023 | 0.9061 | - | 0.55378 | 0.11932 |  |  | 0 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. Staffing 5 month average actuals exceed your budget.
| Naval Power | INTEGRATED MISSION SYSTEMS | 61E2 | CLIN 2002 CEC Facility Management | 12 | DoD - Engineering Manufacturing and Development |  |  |  | Steady | Active | Finance: BONNIE REBELO,Finance: BONNIE REBELO,Finance: Matthew Proehl,Finance: Matthew Proehl,PM: Daniel Anderson,PM: Daniel Anderson,PM: Matthew Sisco,PM: Matthew Sisco,Planner: David Lafleur,Planner: David Lafleur | FINAL | 317.1969 | 2055.83 | 317.1969 | 2055.83 | 293.1126 | 2101.343 | 0 | 24.0844 | 1 | 1.0822 | 3135.5616 | 3135.5616 | 2437.9585 | 0 | 697.6032 | 1 | 1.2861 | 0.89827 | 3930.5911 | 3323.0238 | 795.0295 | 607.5673 | 80% | 62.03% | 3930.5911 | 3284.4252 | 3056.1089 | 3056.1089 | - | - |  | 1.0822 | 0.89827 |  |  | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | CLOSE-IN WEAPON SYSTEM | 0EPR | ARMY LPWS BSU IDIQ DO 0027 | 12 | Post Production |  |  |  | Steady | Active | Finance: Marbelio Villatoro,Finance: Marbelio Villatoro,PM: James Keel,PM: James Keel,Planner: CHARLES KENNA,Planner: CHARLES KENNA,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: KEVIN CRAIG,Planner: KEVIN CRAIG,Planner: Kristen Marcum,Planner: Kristen Marcum,Planner: Seth Van Norman,Planner: Seth Van Norman | FINAL | 2339.3244 | 7703.87 | 2298.3525 | 7461.89 | 2131.2953 | 18021.436 | -40.9719 | 167.0572 | 0.98249 | 1.0784 | 17783.9181 | 17661.7181 | 16274.6141 | -122.2 | 1387.104 | 0.99313 | 1.0852 | 0.59565 | 18429.1224 | 17562.9527 | 767.4043 | 866.1697 | 96% | 88.31% | 18187 | 16470.4077 | 16981.7485 | 16986.6411 | 0.84848 | 0.5 |  |  |  |  | 6975.21 | Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | C2 OTHER | 60X7 | BCSF Mod 1 | 45 | Development |  |  |  | Steady | Active | Finance: DEREK WALTERS,Finance: DEREK WALTERS,Finance: Joseph Ferrara,Finance: Joseph Ferrara,PM: Yvonne Osuna,PM: Yvonne Osuna,Planner: Duy Le,Planner: Duy Le,Planner: Joseph Ferrara,Planner: Joseph Ferrara,Planner: MICHELE RODRIGUEZ,Planner: MICHELE RODRIGUEZ,Planner: Robert Bakke,Planner: Robert Bakke | FINAL | 239.4101 | 1336.6 | 243.3602 | 1346.705 | 104.3245 | 460.947 | 3.9501 | 139.0356 | 1.0165 | 2.3327 | 18110.824 | 17867.1505 | 17111.4182 | -243.6735 | 755.7322 | 0.98655 | 1.0442 | 0.73787 | 18425.4505 | 17868.054 | 558.3001 | 557.3965 | 97% | 92.87% | 18425.451 | 17853.681 | 17646.1037 | 17653.3958 | 0.98321 | 0.42857 | 1.0165 |  |  |  |  | MTD SPI 5 month average is less than ITD SPI.
| Land Warfare & Air Defense | PATRIOT SYSTEMS | 60LQ | PMSC CY17 thru 19 | 43 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: QUINTIN FORBES,Finance: QUINTIN FORBES,Finance: Sarah Serio,Finance: Sarah Serio,PM: Ted Urbowicz,PM: Ted Urbowicz,Planner: Andrea Miller,Planner: Andrea Miller,Planner: Dominique Laplanche,Planner: Dominique Laplanche,Planner: Melanie Parente,Planner: Melanie Parente,Planner: Nicole Moore,Planner: Nicole Moore | FINAL | 0 | 0 | 0 | 0 | 30.6552 | -57.345 | 0 | -30.6552 | 0 | 0 | 57273.2173 | 56743.8548 | 56272.5755 | -529.3625 | 471.2793 | 0.99076 | 1.0084 | 1.5229 | 57273.2173 | 56620.1676 | 529.3625 | 653.0497 | 99% | 98.25% | 57273.2173 | 56627.6692 | 56797.5414 | 56802.4388 | 0.9434 | - | 0 | 0 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Land Warfare & Air Defense | KUWAIT | 615Y | Kuwait TA Appendix B and C | 24 | Production |  |  |  | Steady | Active | Finance: John Lehtinen,Finance: John Lehtinen,Finance: Joseph Galli,Finance: Joseph Galli,Finance: KIMBERLY KMIEC,Finance: KIMBERLY KMIEC,PM: Stefanie Chiou,PM: Stefanie Chiou,Planner: Alvin Neff,Planner: Alvin Neff,Planner: KIMBERLY KMIEC,Planner: KIMBERLY KMIEC,Planner: Ryan Silvia,Planner: Ryan Silvia | FINAL | 302.8609 | 1037 | 302.8609 | 1037 | 87.1568 | 510.391 | 0 | 215.704 | 1 | 3.4749 | 20738.1838 | 20589.0682 | 15267.0732 | -149.1156 | 5321.9951 | 0.99281 | 1.3486 | 0.19127 | 21050.2838 | 17678.4504 | 461.2156 | 3371.8334 | 98% | 72.53% | 21050.2839 | 17853.6466 | 15609.0708 | 15611.5477 | - | - |  |  | 0.19127 | 3371.8334 |  | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Land Warfare & Air Defense | AREA DEFENSE SYSTEMS | 60PM | LCCS FY16 to 18 FP | 23 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: Leticia Goodwin,Finance: Leticia Goodwin,PM: SUSAN OVERMAN,PM: SUSAN OVERMAN,Planner: Leticia Goodwin,Planner: Leticia Goodwin | FINAL | 0 | 0 | 0 | 0 | 1.9851 | 11.961 | 0 | -1.9851 | 0 | 0 | 26120.2755 | 25757.8794 | 26106.7772 | -362.3962 | -348.8978 | 0.98613 | 0.98664 | 41.7777 | 26120.2755 | 26115.4516 | 362.3962 | 4.824 | 99% | 99.95% | 26120.2755 | 26115.4239 | 26474.0821 | 26479.2498 | - | - | 0 | 0 |  |  |  | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI.
| Air Power | PERSISTENT AND STRATEGIC SENSORS | 60E4 | FSSMI FFP | 37 | Production |  |  |  | Steady | Watch Program | Finance: Ram Purushotaman,Finance: Ram Purushotaman,PM: Ladd Horvath,PM: Ladd Horvath,Planner: Byron Chin,Planner: Byron Chin,Planner: Catherine Arno,Planner: Catherine Arno,Planner: Jason Iovanna,Planner: Jason Iovanna | FINAL | 0 | 0 | 0 | 0 | 170.4325 | 399.326 | 0 | -170.4325 | 0 | 0 | 17954.1384 | 17626.9501 | 14147.2563 | -327.1883 | 3479.6939 | 0.98178 | 1.246 | 0.89349 | 17954.1384 | 14513.446 | 327.1883 | 3440.6924 | 98% | 78.8% | 17954.1384 | 14348.1316 | 14409.8551 | 14414.7294 | 0.81356 | - |  | 0 |  | 3440.6924 | 0 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 618B | CTV 01 and FTT 21 Flight Test Support Services | 13 | Development |  |  |  | Improving | Active | Finance: KATHERINE KELLEY,Finance: KATHERINE KELLEY,Finance: Marcus Nichols,Finance: Marcus Nichols,Finance: Yan Ye,Finance: Yan Ye,PM: Gregory Thomas,PM: Gregory Thomas,Planner: June Duggan,Planner: June Duggan | FINAL | 190.039 | 1116.58 | 343.0177 | 1769.68 | 235.8235 | 1220.272 | 152.9787 | 107.1943 | 1.805 | 1.4546 | 9030.4902 | 8814.2896 | 8596.7986 | -216.2006 | 217.491 | 0.97606 | 1.0253 | 0.47372 | 9039.9907 | 9073.2426 | 225.7011 | -33.252 | 98% | 95.1% | 9039.9907 | 8942.6412 | 8816.9305 | 8822.33 | - | - | 1.805 |  | 0.47372 | -33.252 |  | MTD SPI 5 month average is less than ITD SPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | ANS | 611Z | Zumwalt MSE Interim Spares | 28 | Production |  |  |  | Steady | Active | Finance: Leif Sorenson,Finance: Leif Sorenson,PM: Mark Silveira,PM: Mark Silveira,Planner: Anthony Muhl,Planner: Anthony Muhl | FINAL | 0 | 0 | 24.3091 | 177.43 | 234.4267 | 866.17 | 24.3091 | -210.1176 | 0 | 0.1037 | 14376.0106 | 14206.5984 | 13348.4033 | -169.4121 | 858.1951 | 0.98822 | 1.0643 | 1.9811 | 14376.0106 | 13433.9166 | 169.4121 | 942.094 | 99% | 92.85% | 14376.0106 | 13382.0962 | 13507.5815 | 13509.4797 | 0.92105 | - | 0 | 0.1037 |  | 942.094 | 0 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 60OX | CLS FY18 IDIQ | 5 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: Carmine Vara,Finance: Carmine Vara,Finance: John Dewitt,Finance: John Dewitt,PM: Antone Lawrence,PM: Antone Lawrence,PM: Esmeralda Guzman,PM: Esmeralda Guzman,PM: Gail Digangi,PM: Gail Digangi,PM: LAURA DAVID,PM: LAURA DAVID,PM: Meltem Osik,PM: Meltem Osik,PM: Michael Burke,PM: Michael Burke,PM: SAGAR PATEL,PM: SAGAR PATEL,PM: Thomas Collins,PM: Thomas Collins,PM: William Regan,PM: William Regan,Planner: CHRISTINA CORACCIO,Planner: CHRISTINA CORACCIO,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Jereme Coste,Planner: Jereme Coste,Planner: SAMANTHA HATFIELD-COLANGELO,Planner: SAMANTHA HATFIELD-COLANGELO | FINAL | 0 | 0 | 0 | 0 | -20.6802 | 26.969 | 0 | 20.6802 | 0 | 0 | 297509.9601 | 297346.0968 | 288314.051 | -163.8633 | 9032.0458 | 0.99945 | 1.0313 | 1.0208 | 297509.9601 | 288474.5696 | 163.8633 | 9035.3906 | 99% | 96.91% | 297509.9601 | 288496.9005 | 288472.9369 | 288473.0245 | - | - |  | 0 |  | 9035.3906 |  | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Naval Power | AIM-9X | 0EF4 | AIM9X EPAF2 | 24 | Development |  |  |  | Steady | Active | Finance: Bradley Miller,Finance: Bradley Miller,Finance: MATTHEW BRIDGEWATER,Finance: MATTHEW BRIDGEWATER,Finance: Mary Alice Kelly,Finance: Mary Alice Kelly,PM: Deepak Basandrai,PM: Deepak Basandrai,PM: Jerry Morales,PM: Jerry Morales,PM: Marcus Ciuryla,PM: Marcus Ciuryla,PM: Sandy Pelusi,PM: Sandy Pelusi,Planner: Lawrence Brown,Planner: Lawrence Brown,Planner: MIGUEL GUZMAN,Planner: MIGUEL GUZMAN | PRELIMINARY | 40.233 | 208.18 | 25.2128 | 130.46 | 23.5665 | 133.112 | -15.0202 | 1.6463 | 0.62667 | 1.0699 | 1830.4023 | 1851.0195 | 1760.0769 | 20.6172 | 90.9426 | 1.0113 | 1.0517 | 1.2341 | 1972.9128 | 1858.8506 | 121.8933 | 114.0622 | 94% | 89.21% | 1972.9128 | 1880.5899 | 1874.6905 | 1875.9815 | 1.0405 | 0.66667
| Strategic Missile Defense | MISSILE DEFENSE | 60OA | THAAD LM EP ODM RL | 4 | Production |  |  |  | Steady | Active | Finance: Debra Cnockaert,Finance: Debra Cnockaert,Finance: KATHERINE KELLEY,Finance: KATHERINE KELLEY,PM: Gregory Thomas,PM: Gregory Thomas,Planner: June Duggan,Planner: June Duggan,Planner: Michael Mirabile,Planner: Michael Mirabile,Planner: Paul Bonin,Planner: Paul Bonin | FINAL | 599.5097 | 3408.8 | 599.5097 | 3408.8 | 247.2535 | 1407.791 | 0 | 352.2561 | 1 | 2.4247 | 23871.7875 | 23871.7875 | 22856.8616 | 7.4506e-12 | 1014.9259 | 1 | 1.0444 | 0.8073 | 23988.0645 | 23000.8936 | 116.277 | 987.1709 | 99% | 95.28% | 23694.608 | 22980.8599 | 22968.1951 | 22968.1951 | 0.98148 | - |  | 2.4247 |  | 987.1709 | 25647 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 60P1 | RDC FY18 TO2 | 28 | Development |  |  |  | Steady | Active | Finance: Nancy Nugent,Finance: Nancy Nugent,Finance: Paolo Cataldi,Finance: Paolo Cataldi,Finance: TARA CHANDLER,Finance: TARA CHANDLER,Finance: TIMOTHY HEPWORTH,Finance: TIMOTHY HEPWORTH,Finance: Tevian Mazzotta,Finance: Tevian Mazzotta,PM: CAITLIN MEDEIROS,PM: CAITLIN MEDEIROS,PM: David Rourke,PM: David Rourke,PM: Jeffrey Lewitzky,PM: Jeffrey Lewitzky,PM: TYLER STRATTON,PM: TYLER STRATTON,Planner: Monica Dwyre-Wortman,Planner: Monica Dwyre-Wortman,Planner: Paul Bonin,Planner: Paul Bonin,Planner: Timothy Parella,Planner: Timothy Parella | FINAL | 138.4313 | 785.75 | 138.4313 | 785.75 | 205.4425 | 1141.032 | 0 | -67.0112 | 1 | 0.67382 | 92029.2634 | 92029.2634 | 90935.273 | 2.9802e-11 | 1093.9905 | 1 | 1.012 | 0.13731 | 92103.5251 | 91476.1056 | 74.2617 | 627.4195 | 99% | 98.73% | 92029.2634 | 91104.8806 | 91008.6519 | 91008.6519 | 1 | - |  | 0.67382 |  | 627.4195 | 170293 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 60ZX | CLS FY19 IDIQ | 12 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: Carmine Vara,Finance: Carmine Vara,Finance: John Dewitt,Finance: John Dewitt,PM: Antone Lawrence,PM: Antone Lawrence,PM: Meltem Osik,PM: Meltem Osik,PM: Michael Burke,PM: Michael Burke,PM: William Regan,PM: William Regan,Planner: CHRISTINA CORACCIO,Planner: CHRISTINA CORACCIO,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Jereme Coste,Planner: Jereme Coste,Planner: Michael Mirabile,Planner: Michael Mirabile,Planner: SAMANTHA HATFIELD-COLANGELO,Planner: SAMANTHA HATFIELD-COLANGELO | FINAL | 0 | 0 | 0 | 0 | 5.9743 | 46.567 | 0 | -5.9743 | 0 | 0 | 135937.0497 | 135896.3843 | 129429.558 | -40.6654 | 6466.8263 | 0.9997 | 1.05 | 0.13324 | 135937.0497 | 129734.7658 | 40.6654 | 6202.2839 | 99% | 95.21% | 135937.0497 | 129692.3334 | 129468.2883 | 129468.2999 | - | - | 0 | 0 | 0.13324 |  | 0 | MTD SPI 5 month average is less than ITD SPI. MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 604J | THAAD UAE Cost Type | 100 | Production |  |  |  | Steady | Active | Finance: CARRIE UEDA,Finance: CARRIE UEDA,Finance: KATHERINE KELLEY,Finance: KATHERINE KELLEY,Finance: MICHAEL DOREN,Finance: MICHAEL DOREN,PLANNER: Bruce Reppucci,PLANNER: Bruce Reppucci,PM: Danial Ashmun,PM: Danial Ashmun,Planner: Akilah Couvson,Planner: Akilah Couvson,Planner: Brenda Markiewicz,Planner: Brenda Markiewicz,Planner: CONSTANCE PELLETIER,Planner: CONSTANCE PELLETIER,Planner: JACKIE RYAN,Planner: JACKIE RYAN,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Jason Iovanna,Planner: Jason Iovanna,Planner: June Duggan,Planner: June Duggan,Planner: Michael Mirabile,Planner: Michael Mirabile,Planner: Paul Bonin,Planner: Paul Bonin,Planner: Sean Liddell,Planner: Sean Liddell,Planner: Wendy Farrell,Planner: Wendy Farrell,Planner: ZACHARY SHAW,Planner: ZACHARY SHAW | PRELIMINARY | 0 | 0 | 15.8553 | 117.927 | 89.0596 | 645.537 | 15.8553 | -73.2043 | 0 | 0.17803 | 172275.4261 | 172238.4831 | 170129.6936 | -36.943 | 2108.7896 | 0.99979 | 1.0124 | 0.69227 | 172275.4261 | 170183.0586 | 36.943 | 2092.3675 | 99% | 98.75% | 172275.4261 | 170071.2721 | 170166.1843 | 170166.1921 | 0.95892 | - |  | 0.17803 | 0.69227 | 2092.3675 | 0 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Air Power | PERSISTENT AND STRATEGIC SENSORS | 60SF | FSSMI CP | 9 | DoD - Engineering Manufacturing and Development |  |  |  | Steady | Watch Program | Finance: Ram Purushotaman,Finance: Ram Purushotaman,PM: Ladd Horvath,PM: Ladd Horvath,Planner: Byron Chin,Planner: Byron Chin,Planner: Catherine Arno,Planner: Catherine Arno,Planner: Jason Iovanna,Planner: Jason Iovanna | FINAL | 0 | 0 | 0 | 0 | 35.5275 | 202.647 | 0 | -35.5275 | 0 | 0 | 5723.2966 | 5712.8169 | 3106.9113 | -10.4797 | 2605.9056 | 0.99817 | 1.8387 | 0.28103 | 5723.2966 | 3144.2015 | 10.4797 | 2579.0951 | 99% | 54.29% | 5723.2966 | 3108.674 | 3112.6107 | 3112.6211 | 0.46154 | - |  | 0 |  | 2579.0951 | 0 | MTD CPI 5 month average is less than ITD CPI. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | AREA DEFENSE SYSTEMS | 6115 | Enhanced Sentinel A3 Radars | 9 | Production |  |  |  | Steady | Active | Finance: Dillon Allen,Finance: Dillon Allen,Finance: Joseph Ferrara,Finance: Joseph Ferrara,Finance: Nikhiles Lombard,Finance: Nikhiles Lombard,PM: KATHY DESON,PM: KATHY DESON,PM: Kevin Newton,PM: Kevin Newton,PM: Richard Russell,PM: Richard Russell,Planner: Kevin Newton,Planner: Kevin Newton,Planner: TIMOTHY REHFELDT,Planner: TIMOTHY REHFELDT | FINAL | 0 | 0 | 0 | 0 | 321.1822 | 1024.297 | 0 | -321.1822 | 0 | 0 | 73302.706 | 73302.6925 | 74532.7089 | -0.0135 | -1230.0163 | 1 | 0.9835 | 0.00056776 | 73302.706 | 74556.4867 | 0.0135 | -1253.7806 | 99% | 101.7% | 73302.706 | 74280.4734 | 74532.7226 | 74532.7226 | - | - |  | 0 | 0.00056776 | -1253.7806 | 0 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | INDOPACOM PROGRAMS | 60ZK | Poland Patriot Phase 1 | 80 | Production |  |  |  | Improving | Active | Finance: Matthew Cody,Finance: Matthew Cody,PM: Ronald Bettencourt,PM: Ronald Bettencourt,PM: SUSAN GLAESER,PM: SUSAN GLAESER,Planner: Akilah Couvson,Planner: Akilah Couvson,Planner: Alvin Neff,Planner: Alvin Neff,Planner: Andrea Miller,Planner: Andrea Miller,Planner: Ani Days,Planner: Ani Days,Planner: CHARLES KENNA,Planner: CHARLES KENNA,Planner: JAMES RICHARD,Planner: JAMES RICHARD,Planner: JULIA ROGERS,Planner: JULIA ROGERS,Planner: Jeremy Koen,Planner: Jeremy Koen,Planner: Jessica Vanco,Planner: Jessica Vanco,Planner: Lee Brucks,Planner: Lee Brucks,Planner: MATTHEW RONDEAU,Planner: MATTHEW RONDEAU,Planner: Matthew Cody,Planner: Matthew Cody,Planner: Michael Jordan,Planner: Michael Jordan,Planner: Nanette Halliburton,Planner: Nanette Halliburton,Planner: Prashant Navkal,Planner: Prashant Navkal,Planner: TIM MCCORMICK,Planner: TIM MCCORMICK | FINAL | 21588.6886 | 44971.76 | 52220.3009 | 46083.308 | 16574.3115 | 52918.174 | 30631.6123 | 35645.9893 | 2.4189 | 3.1507 | 663181.4188 | 665437.6147 | 646220.3781 | 2256.1959 | 19217.2366 | 1.0034 | 1.0297 | 0.96243 | 1160669.5361 | 1160785.0851 | 495231.9213 | -115.549 | 57% | 55.68% | 1161904.1003 | 1154589.7743 | 1125519.8345 | 1127150.4494 | 0.9549 | 0.27027 |  |  |  | -115.549 |  | VAC 5 month average is less than the furthest month in the 5 month forecast.
| Land Warfare & Air Defense | SAUDI PROGRAMS | 61G6 | KSA GEMT 109 Lot LWAD | 69 | Internal |  |  |  | Steady | Active | Finance: Christopher Dicenso,Finance: Christopher Dicenso,Finance: Ryan Hwang,Finance: Ryan Hwang,PM: Brian Gath,PM: Brian Gath,PM: Erik French,PM: Erik French,Planner: Adam Genetti,Planner: Adam Genetti,Planner: Michael Jordan,Planner: Michael Jordan | FINAL | 1493.921 | 4675.32 | 1467.6907 | 7145.153 | 3775.3962 | 10481.73 | -26.2303 | -2307.7055 | 0.98244 | 0.38875 | 7064.0355 | 51628.0596 | 44020.1641 | 44564.0241 | 7607.8956 | 7.3086 | 1.1728 | 0.98753 | 319476.398 | 315249.7772 | 267848.3384 | 4226.6209 | 16% | 13.78% | 319476.398 | 315249.7772 | 75268.1393 | 272398.4508 | - | - |  |  |  |  | 0 | Staffing 5 month average actuals exceed your budget.
| Strategic Missile Defense | MISSILE DEFENSE | 61DT | AN TPY 2 Radar 13 | 47 | Production |  |  |  | Steady | Active | Finance: Jacquelin Brogan,Finance: Jacquelin Brogan,PM: Vanessa Vera,PM: Vanessa Vera,Planner: Jereme Coste,Planner: Jereme Coste,Planner: ZACHARY SHAW,Planner: ZACHARY SHAW | FINAL | 1759.5419 | 5632.85 | 4365.7024 | 6139.182 | 3491.1245 | 6070.622 | 2606.1604 | 874.5779 | 2.4812 | 1.2505 | 8434.4176 | 24917.6557 | 22535.9219 | 16483.2381 | 2381.7338 | 2.9543 | 1.1057 | 0.97359 | 211246.3241 | 213918.196 | 186328.6684 | -2671.8719 | 12% | 10.67% | 211246.2807 | 213119.8263 | 79578.054 | 191054.5167 | 0.61972 | 0.45455 |  |  |  |  | 392302.54 | Staffing 5 month average actuals exceed your budget.
| Naval Power | Naval Surface & Undersea Systems | 60I7 | MK54 FY16 FY20 Production | 32 | Production |  |  |  | Steady | Active | Finance: Heidi Wilson,Finance: Heidi Wilson,Finance: KATHERINE MARKELL,Finance: KATHERINE MARKELL,Finance: SELENA VEACH,Finance: SELENA VEACH,PM: Matthew Holbrook,PM: Matthew Holbrook,PM: SARAH BOTTHOF,PM: SARAH BOTTHOF,Planner: Divinia Maguire,Planner: Divinia Maguire,Planner: Geoffrey Johnson,Planner: Geoffrey Johnson,Planner: Hamon Ashford,Planner: Hamon Ashford,Planner: Kevin Mcvey,Planner: Kevin Mcvey,Planner: Richard Helle,Planner: Richard Helle,Planner: SELENA VEACH,Planner: SELENA VEACH | FINAL | 4144.9015 | 2830.589 | 2470.677 | 8095.585 | 2137.4338 | 6737.573 | -1674.2245 | 333.2432 | 0.59608 | 1.1559 | 255366.7448 | 246525.2835 | 245125.3195 | -8841.4613 | 1399.964 | 0.96538 | 1.0057 | 1.2144 | 318924.4425 | 304742.2956 | 72399.159 | 14182.1469 | 77% | 76.86% | 318924.4425 | 304847.4904 | 317113.3392 | 319695.1405 | 0.68186 | 0.13636 |  |  |  |  | 5042296 | Staffing 5 month average actuals exceed your budget.
| Naval Power | UNDERSEA SYSTEMS (LEGACY) | 61F6 | ALFS MN60 ROMEO | 53 | Production |  |  |  | Steady | Active | Finance: Mark Purcell,Finance: Mark Purcell,Finance: Stephen Esares,Finance: Stephen Esares,PM: Susan Romano,PM: Susan Romano,Planner: Chariae Harbin,Planner: Chariae Harbin,Planner: David Ponte,Planner: David Ponte,Planner: Eric Bierke,Planner: Eric Bierke,Planner: Mark Purcell,Planner: Mark Purcell,Planner: Richard Todd,Planner: Richard Todd | FINAL | 674.7747 | 1510.3 | 451.6089 | 845.25 | 350.584 | 582.526 | -223.1658 | 101.0248 | 0.66927 | 1.2882 | 3401.958 | 4423.1828 | 3933.6185 | 1021.2247 | 489.5643 | 1.3002 | 1.1245 | 1.0087 | 29551.7331 | 28844.3339 | 25128.5503 | 707.3992 | 15% | 13.31% | 29551.7331 | 29174.1043 | 21121.3615 | 26280.9043 | 1.0556 | - |  |  |  | 707.3992 |  | VAC 5 month average is less than the furthest month in the 5 month forecast.
| Land Warfare & Air Defense | CRDP | 0EPW | DAWN | 17 | DoD - Engineering Manufacturing and Development |  |  |  | Improving | Active | PM: AMANDEEP DHALIWAL,PM: AMANDEEP DHALIWAL,Planner: Pamela Blackowiak,Planner: Pamela Blackowiak,Planner: Yoreida Andrieu,Planner: Yoreida Andrieu | FINAL | 2449.3265 | 9908 | 6048.2013 | 11874.978 | 5148.8502 | 8887.166 | 3598.8748 | 899.3511 | 2.4693 | 1.1747 | 25234.4572 | 24765.0037 | 24750.2249 | -469.4535 | 14.7788 | 0.9814 | 1.0006 | 0 | 44173.6561 | 24750.2249 | 19408.6524 | 19423.4312 | 56% | 56.03% | 43288.0843 | 40642.4076 | 44147.2949 | 44514.9921 | 0.86538 | 0.92308 |  |  |  |  | 857962 | Staffing 5 month average actuals exceed your budget.
| Land Warfare & Air Defense | EUCOM PROGRAMS | 6184 | Romania TA | 59 | Production |  |  |  | Steady | Active | PM: David Belliveau,PM: David Belliveau,PM: Patrick Griffin,PM: Patrick Griffin,Planner: Brian Martinez,Planner: Brian Martinez | FINAL | 207.258 | 661.24 | 220.1799 | 633.84 | 114.7947 | 295.184 | 12.9219 | 105.3852 | 1.0623 | 1.918 | 6609.3574 | 6672.5663 | 4488.9866 | 63.209 | 2183.5797 | 1.0096 | 1.4864 | 1.2243 | 24683.647 | 19199.8233 | 18011.0806 | 5483.8237 | 27% | 18.19% | 24683.647 | 19301.0491 | 16491.2048 | 16605.9887 | - | - |  |  | 1.2243 | 5483.8237 |  | TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast.
| Strategic Missile Defense | MISSILE DEFENSE | 61EL | KSA Phase 2 | 74 | Production |  |  |  | Improving | Active | Finance: KATHERINE KELLEY,Finance: KATHERINE KELLEY,Finance: Marcus Nichols,Finance: Marcus Nichols,Finance: Yan Ye,Finance: Yan Ye,PM: Gregory Thomas,PM: Gregory Thomas,Planner: Adam Genetti,Planner: Adam Genetti,Planner: June Duggan,Planner: June Duggan | FINAL | 375.4704 | 2443.61 | 385.4074 | 2488.292 | 311.0517 | 2035.256 | 9.9369 | 74.3556 | 1.0265 | 1.239 | 2629.2121 | 2710.8688 | 2635.9511 | 81.6568 | 74.9177 | 1.0311 | 1.0284 | 1.0161 | 17955.5128 | 17639.2523 | 15244.644 | 316.2605 | 15% | 14.68% | 17955.5208 | 17705.4881 | 17012.7848 | 17459.2934 | - | -
| Strategic Missile Defense | MISSILE DEFENSE | 60YJ | Ground Based Radar GBR Support | 1 | DoD - Operations and Support |  |  |  | Steady | Active | Finance: Carmine Vara,Finance: Carmine Vara,Finance: John Dewitt,Finance: John Dewitt,PM: LAURA DAVID,PM: LAURA DAVID,PM: Thomas Collins,PM: Thomas Collins,Planner: CHRISTINA CORACCIO,Planner: CHRISTINA CORACCIO,Planner: JESSICA ADAMS,Planner: JESSICA ADAMS,Planner: Jereme Coste,Planner: Jereme Coste,Planner: Michael Mirabile,Planner: Michael Mirabile,Planner: SAMANTHA HATFIELD-COLANGELO,Planner: SAMANTHA HATFIELD-COLANGELO | FINAL | 177.6709 | 366.76 | 257.851 | 741.731 | 188.5206 | 696.109 | 80.1801 | 69.3303 | 1.4513 | 1.3678 | 8362.7703 | 8231.8876 | 7213.4794 | -130.8827 | 1018.4082 | 0.98435 | 1.1412 | 0.99168 | 20931.9044 | 20020.038 | 12700.0168 | 911.8663 | 39% | 34.46% | 20931.8737 | 20080.8425 | 18342.3132 | 18519.2558 | 0.92 | - |  |  | 0.99168 |  | 2047431 | TCPI 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | NAVAL RADARS | 61BC | Dual Band Radar Spares J3 | 2 | Production |  |  |  | Steady | Active | Finance: Holly Johnson,Finance: Holly Johnson,PM: Dale Wainwright,PM: Dale Wainwright,PM: Kim Rohwer,PM: Kim Rohwer,Planner: Colin Faherty,Planner: Colin Faherty,Planner: Holly Johnson,Planner: Holly Johnson | FINAL | 269.1285 | 1001.98 | -360.1849 | -4507.122 | 405.8597 | 889.434 | -629.3134 | -766.0445 | -1.3383 | -0.88746 | 4348.4989 | 4838.5493 | 4705.6826 | 490.0504 | 132.8667 | 1.1127 | 1.0282 | 2.5927 | 12304.663 | 7585.3113 | 7466.1137 | 4719.3518 | 39% | 38.24% | 7639.2953 | 7105.8796 | 11231.3697 | 11966.7765 | - | - | -1.3383 |  |  |  | 0 | MTD SPI 5 month average is less than ITD SPI. Staffing 5 month average actuals exceed your budget.
| Naval Power | UNDERSEA SYSTEMS (LEGACY) | 61E5 | ALFS FY21 Spares 2 Lot | 33 | Production |  |  |  | Steady | Active | PM: Susan Romano,PM: Susan Romano,Planner: David Lafleur,Planner: David Lafleur,Planner: David Ponte,Planner: David Ponte,Planner: Mark Purcell,Planner: Mark Purcell,Planner: Richard Todd,Planner: Richard Todd | FINAL | 20.1761 | 111.26 | 20.0157 | 97.683 | 24.7811 | 142.212 | -0.16042 | -4.7655 | 0.99205 | 0.8077 | 468.4628 | 505.008 | 354.7401 | 36.5452 | 150.268 | 1.078 | 1.4236 | 0.9841 | 2766.3356 | 2652.6128 | 2261.3276 | 113.7228 | 18% | 12.82% | 2766.3356 | 2648.0078 | 1828.2475 | 1943.197 | 1.5 | - |  | 0.8077 | 0.9841 | 113.7228 | 929 | MTD CPI 5 month average is less than ITD CPI. TCPI 5 month average is less than the furthest month in the 5 month forecast. VAC 5 month average is less than the furthest month in the 5 month forecast. Staffing 5 month average actuals exceed your budget.
| Naval Power | AIM-9X | 0EOJ | MSeries OFP | 48 | Development |  |  |  | Improving | Active | Finance: Bradley Miller,Finance: Bradley Miller,PM: Deepak Basandrai,PM: Deepak Basandrai,PM: Jerry Morales,PM: Jerry Morales,Planner: Lawrence Brown,Planner: Lawrence Brown | PRELIMINARY | 16.4735 | 86.52 | 16.4735 | 86.52 | 9.2564 | 53.313 | 0 | 7.217 | 1 | 1.7797 | 362.8763 | 362.8763 | 351.1561 | -5.8208e-14 | 11.7202 | 1 | 1.0334 | 1.0728 | 1269.3438 | 1196.0874 | 906.4675 | 73.2564 | 29% | 27.66% | 1269.3438 | 397.688 | 1228.3465 | 1228.3465 | 1 | -