## Engineering BEI
iEPMReporting (ray.com) |  |  | by Discipline | 2020-02-01 |  |  | 2020-03-01 |  |  | 2020-04-01 |  |  | 2020-05-01 |  |  | 2020-06-01 |  |  | 2020-07-01 |  |  | 2020-08-01 |  |  | 2020-09-01 |  |  | 2020-10-01 |  |  | 2020-11-01 |  |  | 2020-12-01 |  |  | 2021-01-01 |  |  |  | 2020-02-01 | 2020-03-04 | 2020-04-05 | 2020-05-07 | 2020-06-08 | 2020-07-10 | 2020-08-11 | 2020-09-12 | 2020-10-14 | 2020-11-15 | 2020-12-17 | 2021-01-18
|  |  |  | Bas Fin | Act Fin | BEI | Bas Fin | Act Fin | BEI | Bas Fin | Act Fin | BEI | Bas Fin | Act Fin | BEI | Bas Fin | Act Fin | BEI | Bas Fin | Act Fin | BEI | Bas Fin | Act Fin | BEI | Bas Fin | Act Fin | BEI | Bas Fin | Act Fin | BEI | Bas Fin | Act Fin | BEI | Bas Fin | Act Fin | BEI | Bas Fin | Act Fin | BEI
Strategic Missile Defense | Major Program | AN/TYP-2 TO3 TO6 | Program | 58 | 38 | 0.65517 | 70 | 45 | 0.64286 | 79 | 51 | 0.64557 | 86 | 57 | 0.66279 | 100 | 62 | 0.62 | 106 | 70 | 0.66038 | 120 | 78 | 0.65 | 123 | 85 | 0.69106 | 126 | 87 | 0.69048 | 143 | 94 | 0.65734 | 200 | 122 | 0.61 | 228 | 153 | 0.67105 | Program | 0.65517 | 0.64286 | 0.64557 | 0.66279 | 0.62 | 0.66038 | 0.65 | 0.69106 | 0.69048 | 0.65734 | 0.61 | 0.67105
Strategic Missile Defense | Major Program |  | Engineering | 57 | 38 | 0.66667 | 69 | 45 | 0.65217 | 78 | 51 | 0.65385 | 85 | 57 | 0.67059 | 95 | 62 | 0.65263 | 101 | 70 | 0.69307 | 114 | 78 | 0.68421 | 117 | 84 | 0.71795 | 118 | 86 | 0.72881 | 125 | 92 | 0.736 | 142 | 108 | 0.76056 | 155 | 127 | 0.81935 | Engineering | 0.66667 | 0.65217 | 0.65385 | 0.67059 | 0.65263 | 0.69307 | 0.68421 | 0.71795 | 0.72881 | 0.736 | 0.76056 | 0.81935 | 0.77197
Strategic Missile Defense | Major Program | AN/TYP-2 TO3 TO6 | Program | 58 | 38 | 0.65517 | 70 | 45 | 0.64286 | 79 | 51 | 0.64557 | 86 | 57 | 0.66279 | 100 | 62 | 0.62 | 106 | 70 | 0.66038 | 120 | 78 | 0.65 | 123 | 85 | 0.69106 | 126 | 87 | 0.69048 | 137 | 92 | 0.67153 | 167 | 96 | 0.57485 | 171 | 103 | 0.60234
|  |  | Engineering | 57 | 38 | 0.66667 | 69 | 45 | 0.65217 | 78 | 51 | 0.65385 | 85 | 57 | 0.67059 | 95 | 62 | 0.65263 | 101 | 70 | 0.69307 | 114 | 78 | 0.68421 | 117 | 84 | 0.71795 | 118 | 86 | 0.72881 | 122 | 91 | 0.7459 | 126 | 95 | 0.75397 | 128 | 102 | 0.79688
|  |  | EPT | 11 | 4 | 0.36364 | 14 | 6 | 0.42857 | 14 | 6 | 0.42857 | 16 | 6 | 0.375 | 19 | 7 | 0.36842 | 19 | 9 | 0.47368 | 22 | 11 | 0.5 | 23 | 12 | 0.52174 | 24 | 13 | 0.54167 | 26 | 14 | 0.53846 | 28 | 14 | 0.5 | 30 | 21 | 0.7
|  |  | ISC | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 4 | 0 | 0 | 4 | 1 | 0.25 | 6 | 1 | 0.16667 | 6 | 1 | 0.16667 | 18 | 1 | 0.055556 | 18 | 1 | 0.055556
|  |  | MPT | 13 | 5 | 0.38462 | 16 | 6 | 0.375 | 17 | 6 | 0.35294 | 17 | 6 | 0.35294 | 17 | 7 | 0.41176 | 17 | 7 | 0.41176 | 24 | 7 | 0.29167 | 24 | 8 | 0.33333 | 24 | 9 | 0.375 | 24 | 9 | 0.375 | 25 | 10 | 0.4 | 25 | 10 | 0.4
|  |  | OPS |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 9 | 0 | 0 | 16 | 0 | 0 | 18 | 0 | 0
|  |  | Quality | [30 empty] | 7 | 0 | 0 | 7 | 0 | 0
|  |  | SDA | 23 | 20 | 0.86957 | 29 | 24 | 0.82759 | 33 | 28 | 0.84848 | 37 | 31 | 0.83784 | 42 | 31 | 0.7381 | 42 | 35 | 0.83333 | 42 | 38 | 0.90476 | 42 | 39 | 0.92857 | 42 | 39 | 0.92857 | 42 | 41 | 0.97619 | 42 | 42 | 1 | 42 | 42 | 1
|  |  | SIT |  |  | #DIV/0! |  |  | #DIV/0! | 4 | 2 | 0.5 | 5 | 4 | 0.8 | 7 | 7 | 1 | 11 | 7 | 0.63636 | 14 | 10 | 0.71429 | 16 | 13 | 0.8125 | 16 | 13 | 0.8125 | 18 | 15 | 0.83333 | 19 | 17 | 0.89474 | 19 | 17 | 0.89474
|  |  | WLE | 10 | 9 | 0.9 | 10 | 9 | 0.9 | 10 | 9 | 0.9 | 10 | 10 | 1 | 10 | 10 | 1 | 12 | 12 | 1 | 12 | 12 | 1 | 12 | 12 | 1 | 12 | 12 | 1 | 12 | 12 | 1 | 12 | 12 | 1 | 12 | 12 | 1
Strategic Missile Defense | Major Program | AN/TYP-2 TO6 | Program | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 6 | 2 | 0.33333 | 33 | 26 | 0.78788 | 57 | 50 | 0.87719
|  |  | Engineering | [27 empty] | 3 | 1 | 0.33333 | 16 | 13 | 0.8125 | 27 | 25 | 0.92593
|  |  | AS | [29 empty] | #DIV/0! | 1 | 0 | 0 | 3 | 0 | 0
|  |  | SDA | [27 empty] | 3 | 1 | 0.33333 | 8 | 6 | 0.75 | 12 | 13 | 1.0833
|  |  | SIT | [29 empty] | #DIV/0! | 2 | 2 | 1 | 8 | 6 | 0.75
|  |  | SPE | [29 empty] | #DIV/0! | 1 | 0 | 0 | 1 | 0 | 0
|  |  | WLE | [29 empty] | #DIV/0! | 5 | 5 | 1 | 6 | 6 | 1
Naval Power | Small Program | Barracuda | Program | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 18 | 10 | 0.55556 | 46 | 36 | 0.78261 | 59 | 46 | 0.77966 | 84 | 66 | 0.78571 | 115 | 99 | 0.86087 | 137 | 123 | 0.89781 | 178 | 140 | 0.78652 | 216 | 170 | 0.78704 | 239 | 170 | 0.7113 | Program |  |  |  | 0.55556 | 0.78261 | 0.77966 | 0.78571 | 0.86087 | 0.89781 | 0.78652 | 0.78704 | 0.7113
|  |  | Engineering | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 16 | 9 | 0.5625 | 43 | 33 | 0.76744 | 56 | 42 | 0.75 | 77 | 61 | 0.79221 | 107 | 92 | 0.85981 | 128 | 115 | 0.89844 | 169 | 131 | 0.77515 | 204 | 161 | 0.78922 | 227 | 161 | 0.70925 | Engineering |  |  |  | 0.5625 | 0.76744 | 0.75 | 0.79221 | 0.85981 | 0.89844 | 0.77515 | 0.78922 | 0.70925 | 0.75787
|  |  | EPT | [9 empty] | 1 | 1 | 1 | 3 | 4 | 1.3333 | 4 | 4 | 1 | 4 | 4 | 1 | 8 | 7 | 0.875 | 13 | 8 | 0.61538 | 22 | 10 | 0.45455 | 36 | 17 | 0.47222 | 42 | 17 | 0.40476
|  |  | ISC | [9 empty] | 2 | 1 | 0.5 | 3 | 3 | 1 | 3 | 4 | 1.3333 | 5 | 4 | 0.8 | 6 | 6 | 1 | 7 | 7 | 1 | 7 | 8 | 1.1429 | 9 | 8 | 0.88889 | 9 | 8 | 0.88889
|  |  | MPT | [9 empty] | 1 | 2 | 2 | 9 | 8 | 0.88889 | 10 | 10 | 1 | 20 | 19 | 0.95 | 29 | 27 | 0.93103 | 38 | 37 | 0.97368 | 55 | 42 | 0.76364 | 69 | 52 | 0.75362 | 79 | 52 | 0.65823
|  |  | OPS | [18 empty] | 2 | 1 | 0.5 | 2 | 1 | 0.5 | 2 | 1 | 0.5 | 2 | 1 | 0.5 | 2 | 1 | 0.5 | 2 | 1 | 0.5
|  |  | PMO | [26 empty] | #DIV/0! |  |  | #DIV/0! | 1 | 0 | 0 | 1 | 0 | 0
|  |  | SDA | [9 empty] | 12 | 5 | 0.41667 | 21 | 18 | 0.85714 | 30 | 24 | 0.8 | 41 | 33 | 0.80488 | 57 | 47 | 0.82456 | 63 | 57 | 0.90476 | 75 | 66 | 0.88 | 81 | 78 | 0.96296 | 86 | 78 | 0.90698
|  |  | SIT | [12 empty] | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 0.5 | 2 | 1 | 0.5 | 3 | 1 | 0.33333
|  |  | SPE | [12 empty] | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 3 | 2 | 0.66667 | 3 | 3 | 1 | 4 | 3 | 0.75 | 5 | 4 | 0.8 | 5 | 4 | 0.8
|  |  | WLE | [9 empty] | 2 | 1 | 0.5 | 7 | 1 | 0.14286 | 9 | 1 | 0.11111 | 9 | 2 | 0.22222 | 9 | 8 | 0.88889 | 10 | 9 | 0.9 | 11 | 9 | 0.81818 | 11 | 9 | 0.81818 | 12 | 9 | 0.75
Air Power | Major Program | FSSMI | Program | 2705 | 2408 | 0.8902 | 2731 | 2448 | 0.89637 | 2742 | 2484 | 0.90591 | 2757 | 2500 | 0.90678 | 2782 | 2530 | 0.90942 | 2802 | 2650 | 0.94575 | 2810 | 2670 | 0.95018 | 2825 | 2741 | 0.97027 | 2835 | 2749 | 0.96966 | 2848 | 2754 | 0.96699 | 2862 | 2778 | 0.97065 | 2870 | 2781 | 0.96899 | Program | 0.8902 | 0.89637 | 0.90591 | 0.90678 | 0.90942 | 0.94575 | 0.95018 | 0.97027 | 0.96966 | 0.96699 | 0.97065 | 0.96899
|  |  | Engineering | 2325 | 2239 | 0.96301 | 2348 | 2263 | 0.9638 | 2353 | 2285 | 0.9711 | 2364 | 2296 | 0.97124 | 2384 | 2314 | 0.97064 | 2398 | 2327 | 0.97039 | 2406 | 2342 | 0.9734 | 2419 | 2370 | 0.97974 | 2425 | 2377 | 0.98021 | 2431 | 2382 | 0.97984 | 2439 | 2395 | 0.98196 | 2441 | 2395 | 0.98116 | Engineering | 0.96301 | 0.9638 | 0.9711 | 0.97124 | 0.97064 | 0.97039 | 0.9734 | 0.97974 | 0.98021 | 0.97984 | 0.98196 | 0.98116 | 0.98099
|  |  | EDD | 533 | 521 | 0.97749 | 534 | 525 | 0.98315 | 534 | 526 | 0.98502 | 535 | 527 | 0.98505 | 538 | 528 | 0.98141 | 542 | 531 | 0.9797 | 546 | 537 | 0.98352 | 553 | 541 | 0.9783 | 556 | 544 | 0.97842 | 560 | 545 | 0.97321 | 563 | 549 | 0.97513 | 563 | 549 | 0.97513
|  |  | FISH |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0! | 2 | 0 | 0 | 2 | 2 | 1 | 2 | 2 | 1 | 2 | 4 | 2 | 4 | 4 | 1 | 5 | 4 | 0.8 | 7 | 4 | 0.57143 | 7 | 4 | 0.57143
|  |  | IIS | 4 | 5 | 1.25 | 6 | 5 | 0.83333 | 6 | 6 | 1 | 6 | 6 | 1 | 6 | 6 | 1 | 6 | 6 | 1 | 6 | 6 | 1 | 6 | 6 | 1 | 6 | 6 | 1 | 6 | 6 | 1 | 6 | 8 | 1.3333 | 6 | 8 | 1.3333
|  |  | ISC | 135 | 59 | 0.43704 | 136 | 59 | 0.43382 | 142 | 64 | 0.4507 | 143 | 65 | 0.45455 | 145 | 69 | 0.47586 | 147 | 125 | 0.85034 | 147 | 129 | 0.87755 | 148 | 134 | 0.90541 | 148 | 135 | 0.91216 | 148 | 135 | 0.91216 | 148 | 138 | 0.93243 | 148 | 138 | 0.93243
|  |  | IT | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | MED | 586 | 564 | 0.96246 | 592 | 573 | 0.96791 | 593 | 577 | 0.97302 | 593 | 580 | 0.97808 | 596 | 581 | 0.97483 | 599 | 583 | 0.97329 | 599 | 583 | 0.97329 | 599 | 590 | 0.98497 | 599 | 591 | 0.98664 | 599 | 592 | 0.98831 | 599 | 596 | 0.99499 | 599 | 596 | 0.99499
|  |  | OPS | 87 | 52 | 0.5977 | 87 | 52 | 0.5977 | 87 | 54 | 0.62069 | 87 | 54 | 0.62069 | 87 | 54 | 0.62069 | 87 | 55 | 0.63218 | 87 | 55 | 0.63218 | 87 | 77 | 0.88506 | 87 | 77 | 0.88506 | 87 | 77 | 0.88506 | 87 | 77 | 0.88506 | 87 | 77 | 0.88506
|  |  | PMO | 45 | 26 | 0.57778 | 45 | 26 | 0.57778 | 45 | 27 | 0.6 | 48 | 31 | 0.64583 | 49 | 37 | 0.7551 | 53 | 43 | 0.81132 | 53 | 44 | 0.83019 | 54 | 44 | 0.81481 | 56 | 44 | 0.78571 | 62 | 44 | 0.70968 | 66 | 50 | 0.75758 | 72 | 53 | 0.73611
|  |  | Quality | 108 | 26 | 0.24074 | 108 | 42 | 0.38889 | 108 | 47 | 0.43519 | 108 | 47 | 0.43519 | 108 | 49 | 0.4537 | 108 | 91 | 0.84259 | 108 | 91 | 0.84259 | 108 | 105 | 0.97222 | 108 | 105 | 0.97222 | 108 | 105 | 0.97222 | 108 | 105 | 0.97222 | 108 | 105 | 0.97222
|  |  | SADID | 300 | 297 | 0.99 | 304 | 298 | 0.98026 | 304 | 303 | 0.99671 | 304 | 305 | 1.0033 | 307 | 309 | 1.0065 | 309 | 309 | 1 | 309 | 309 | 1 | 311 | 311 | 1 | 311 | 311 | 1 | 311 | 311 | 1 | 313 | 313 | 1 | 313 | 313 | 1
|  |  | SED | 518 | 500 | 0.96525 | 521 | 501 | 0.96161 | 521 | 507 | 0.97313 | 524 | 509 | 0.97137 | 528 | 512 | 0.9697 | 529 | 515 | 0.97353 | 530 | 521 | 0.98302 | 531 | 525 | 0.9887 | 533 | 525 | 0.98499 | 533 | 525 | 0.98499 | 535 | 526 | 0.98318 | 535 | 526 | 0.98318
|  |  | SVTAD | 151 | 133 | 0.88079 | 154 | 135 | 0.87662 | 154 | 135 | 0.87662 | 155 | 136 | 0.87742 | 156 | 138 | 0.88462 | 156 | 140 | 0.89744 | 156 | 143 | 0.91667 | 157 | 143 | 0.91083 | 157 | 145 | 0.92357 | 157 | 145 | 0.92357 | 157 | 146 | 0.92994 | 157 | 146 | 0.92994
|  |  | WLED | 237 | 224 | 0.94515 | 243 | 231 | 0.95062 | 247 | 237 | 0.95951 | 253 | 239 | 0.94466 | 259 | 246 | 0.94981 | 263 | 249 | 0.94677 | 266 | 249 | 0.93609 | 268 | 260 | 0.97015 | 269 | 261 | 0.97026 | 271 | 264 | 0.97417 | 272 | 265 | 0.97426 | 274 | 265 | 0.96715
Land Warfare & Air Defense (LW&AD) | Major Program | Patriot Sweden | Program | 215 | 240 | 1.1163 | 244 | 278 | 1.1393 | 273 | 315 | 1.1538 | 302 | 352 | 1.1656 | 336 | 396 | 1.1786 | 352 | 421 | 1.196 | 585 | 594 | 1.0154 | 640 | 642 | 1.0031 | 719 | 687 | 0.95549 | 786 | 742 | 0.94402 | 863 | 786 | 0.91078 | 892 | 803 | 0.90022 | Program | 1.1163 | 1.1393 | 1.1538 | 1.1656 | 1.1786 | 1.196 | 1.0154 | 1.0031 | 0.95549 | 0.94402 | 0.91078 | 0.90022
|  |  | Engineering | 215 | 240 | 1.1163 | 244 | 278 | 1.1393 | 273 | 315 | 1.1538 | 302 | 352 | 1.1656 | 336 | 396 | 1.1786 | 352 | 421 | 1.196 | 585 | 594 | 1.0154 | 640 | 642 | 1.0031 | 719 | 687 | 0.95549 | 786 | 742 | 0.94402 | 863 | 786 | 0.91078 | 892 | 803 | 0.90022 | Engineering | 1.1163 | 1.1393 | 1.1538 | 1.1656 | 1.1786 | 1.196 | 1.0154 | 1.0031 | 0.95549 | 0.94402 | 0.91078 | 0.90022 | 0.91834
|  |  | EPT | 20 | 25 | 1.25 | 20 | 29 | 1.45 | 27 | 30 | 1.1111 | 28 | 32 | 1.1429 | 31 | 36 | 1.1613 | 31 | 40 | 1.2903 | 56 | 56 | 1 | 70 | 61 | 0.87143 | 93 | 76 | 0.8172 | 117 | 95 | 0.81197 | 146 | 114 | 0.78082 | 157 | 119 | 0.75796
|  |  | IOT RIS |  |  | #DIV/0! | [24 empty] | 1 | 0 | 0 | 2 | 0 | 0 | 2 | 1 | 0.5
|  |  | MPT | 66 | 79 | 1.197 | 69 | 85 | 1.2319 | 72 | 93 | 1.2917 | 79 | 102 | 1.2911 | 91 | 116 | 1.2747 | 97 | 120 | 1.2371 | 173 | 176 | 1.0173 | 184 | 182 | 0.98913 | 198 | 189 | 0.95455 | 206 | 200 | 0.97087 | 216 | 202 | 0.93519 | 222 | 205 | 0.92342
|  |  | SDA | 72 | 72 | 1 | 84 | 86 | 1.0238 | 97 | 98 | 1.0103 | 102 | 108 | 1.0588 | 106 | 116 | 1.0943 | 110 | 120 | 1.0909 | 149 | 151 | 1.0134 | 156 | 156 | 1 | 169 | 162 | 0.95858 | 175 | 167 | 0.95429 | 186 | 173 | 0.93011 | 186 | 174 | 0.93548
|  |  | SIT | 13 | 13 | 1 | 15 | 15 | 1 | 15 | 20 | 1.3333 | 19 | 24 | 1.2632 | 22 | 26 | 1.1818 | 23 | 29 | 1.2609 | 56 | 58 | 1.0357 | 65 | 68 | 1.0462 | 74 | 72 | 0.97297 | 84 | 80 | 0.95238 | 98 | 86 | 0.87755 | 104 | 90 | 0.86538
|  |  | SPE | 1 | 3 | 3 | 5 | 5 | 1 | 8 | 7 | 0.875 | 15 | 15 | 1 | 24 | 21 | 0.875 | 25 | 26 | 1.04 | 43 | 42 | 0.97674 | 57 | 61 | 1.0702 | 68 | 69 | 1.0147 | 78 | 78 | 1 | 84 | 84 | 1 | 88 | 86 | 0.97727
|  |  | WLE | 43 | 48 | 1.1163 | 51 | 58 | 1.1373 | 54 | 67 | 1.2407 | 59 | 71 | 1.2034 | 62 | 81 | 1.3065 | 66 | 86 | 1.303 | 108 | 111 | 1.0278 | 108 | 114 | 1.0556 | 117 | 119 | 1.0171 | 125 | 122 | 0.976 | 131 | 127 | 0.96947 | 133 | 128 | 0.96241
Land Warfare & Air Defense (LW&AD) | Major Program | Romania Patriot 3 Lot | Program | 53 | 31 | 0.58491 | 77 | 66 | 0.85714 | 94 | 93 | 0.98936 | 106 | 105 | 0.99057 | 125 | 124 | 0.992 | 136 | 131 | 0.96324 | 153 | 142 | 0.9281 | 171 | 152 | 0.88889 | 182 | 164 | 0.9011 | 199 | 178 | 0.89447 | 226 | 190 | 0.84071 | 237 | 201 | 0.8481 | Program | 0.58491 | 0.85714 | 0.98936 | 0.99057 | 0.992 | 0.96324 | 0.9281 | 0.88889 | 0.9011 | 0.89447 | 0.84071 | 0.8481
|  |  | Engineering | 53 | 31 | 0.58491 | 77 | 66 | 0.85714 | 94 | 93 | 0.98936 | 106 | 105 | 0.99057 | 125 | 124 | 0.992 | 136 | 131 | 0.96324 | 153 | 142 | 0.9281 | 171 | 152 | 0.88889 | 182 | 164 | 0.9011 | 199 | 177 | 0.88945 | 226 | 189 | 0.83628 | 237 | 200 | 0.84388 | Engineering | 0.58491 | 0.85714 | 0.98936 | 0.99057 | 0.992 | 0.96324 | 0.9281 | 0.88889 | 0.9011 | 0.88945 | 0.83628 | 0.84388 | 0.85654
|  |  | EPT | 11 | 6 | 0.54545 | 15 | 10 | 0.66667 | 17 | 17 | 1 | 20 | 18 | 0.9 | 22 | 24 | 1.0909 | 22 | 26 | 1.1818 | 22 | 27 | 1.2273 | 23 | 30 | 1.3043 | 24 | 30 | 1.25 | 28 | 31 | 1.1071 | 32 | 31 | 0.96875 | 34 | 31 | 0.91176
|  |  | IOT RIS |  |  | #DIV/0! |  |  | #DIV/0! | [21 empty] | 0 | 1 |  | 0 | 1 |  | 0 | 1
|  |  | MPT | 12 | 7 | 0.58333 | 23 | 25 | 1.087 | 34 | 41 | 1.2059 | 40 | 48 | 1.2 | 52 | 54 | 1.0385 | 56 | 55 | 0.98214 | 60 | 58 | 0.96667 | 61 | 59 | 0.96721 | 62 | 64 | 1.0323 | 68 | 68 | 1 | 79 | 72 | 0.91139 | 83 | 76 | 0.91566
|  |  | SDA | 23 | 14 | 0.6087 | 28 | 22 | 0.78571 | 29 | 23 | 0.7931 | 31 | 24 | 0.77419 | 32 | 28 | 0.875 | 35 | 29 | 0.82857 | 38 | 30 | 0.78947 | 43 | 32 | 0.74419 | 45 | 34 | 0.75556 | 47 | 36 | 0.76596 | 49 | 37 | 0.7551 | 51 | 37 | 0.72549
|  |  | SIT | 5 | 4 | 0.8 | 8 | 6 | 0.75 | 10 | 6 | 0.6 | 11 | 9 | 0.81818 | 11 | 11 | 1 | 12 | 13 | 1.0833 | 17 | 16 | 0.94118 | 26 | 19 | 0.73077 | 29 | 23 | 0.7931 | 34 | 26 | 0.76471 | 38 | 33 | 0.86842 | 40 | 37 | 0.925
|  |  | SPE |  |  | #DIV/0! |  |  | #DIV/0! | [9 empty] | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 4 | 2 | 0.5 | 4 | 3 | 0.75
|  |  | WLE | 2 | 0 | 0 | 3 | 3 | 1 | 4 | 6 | 1.5 | 4 | 6 | 1.5 | 8 | 7 | 0.875 | 10 | 8 | 0.8 | 15 | 11 | 0.73333 | 17 | 11 | 0.64706 | 21 | 11 | 0.52381 | 21 | 14 | 0.66667 | 24 | 14 | 0.58333 | 25 | 16 | 0.64
Land Warfare & Air Defense (LW&AD) | Watch | LTAMDS UMR | Program | 419 | 314 | 0.7494 | 677 | 476 | 0.7031 | 735 | 561 | 0.76327 | 814 | 673 | 0.82678 | 990 | 814 | 0.82222 | 1052 | 908 | 0.86312 | 1122 | 976 | 0.86988 | 1279 | 1136 | 0.88819 | 1352 | 1227 | 0.90754 | 1406 | 1303 | 0.92674 | 1519 | 1416 | 0.93219 | 1538 | 1433 | 0.93173 | Program | 0.7494 | 0.7031 | 0.76327 | 0.82678 | 0.82222 | 0.86312 | 0.86988 | 0.88819 | 0.90754 | 0.92674 | 0.93219 | 0.93173
|  |  | Engineering | 418 | 314 | 0.7512 | 676 | 475 | 0.70266 | 734 | 560 | 0.76294 | 813 | 672 | 0.82657 | 989 | 813 | 0.82204 | 1051 | 907 | 0.86299 | 1121 | 975 | 0.86976 | 1278 | 1135 | 0.88811 | 1351 | 1226 | 0.90748 | 1405 | 1302 | 0.92669 | 1518 | 1415 | 0.93215 | 1537 | 1432 | 0.93169 | Engineering | 0.7512 | 0.70266 | 0.76294 | 0.82657 | 0.82204 | 0.86299 | 0.86976 | 0.88811 | 0.90748 | 0.92669 | 0.93215 | 0.93169 | 0.93017
|  |  | EDD | 121 | 84 | 0.69421 | 187 | 127 | 0.67914 | 206 | 154 | 0.74757 | 230 | 180 | 0.78261 | 248 | 210 | 0.84677 | 267 | 228 | 0.85393 | 288 | 238 | 0.82639 | 304 | 265 | 0.87171 | 314 | 286 | 0.91083 | 326 | 300 | 0.92025 | 337 | 321 | 0.95252 | 343 | 317 | 0.9242
|  |  | GSC | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | MED | 104 | 79 | 0.75962 | 161 | 116 | 0.7205 | 175 | 132 | 0.75429 | 196 | 163 | 0.83163 | 223 | 185 | 0.8296 | 232 | 197 | 0.84914 | 240 | 199 | 0.82917 | 245 | 228 | 0.93061 | 252 | 236 | 0.93651 | 256 | 239 | 0.93359 | 262 | 247 | 0.94275 | 262 | 250 | 0.9542
|  |  | Quality |  |  |  | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 1 | 0.5 | 2 | 1 | 0.5 | 2 | 1 | 0.5 | 2 | 1 | 0.5 | 2 | 1 | 0.5 | 2 | 1 | 0.5 | 2 | 1 | 0.5 | 2 | 1 | 0.5 | 2 | 1 | 0.5
|  |  | SADID | 90 | 87 | 0.96667 | 144 | 120 | 0.83333 | 155 | 137 | 0.88387 | 177 | 159 | 0.89831 | 231 | 195 | 0.84416 | 246 | 218 | 0.88618 | 259 | 239 | 0.92278 | 307 | 281 | 0.91531 | 329 | 310 | 0.94225 | 341 | 326 | 0.95601 | 380 | 354 | 0.93158 | 382 | 357 | 0.93455
|  |  | SED | 51 | 28 | 0.54902 | 108 | 57 | 0.52778 | 111 | 70 | 0.63063 | 117 | 85 | 0.7265 | 164 | 118 | 0.71951 | 169 | 145 | 0.85799 | 179 | 162 | 0.90503 | 232 | 196 | 0.84483 | 243 | 214 | 0.88066 | 253 | 230 | 0.90909 | 289 | 258 | 0.89273 | 289 | 265 | 0.91696
|  |  | SVTAD | 21 | 10 | 0.47619 | 25 | 13 | 0.52 | 28 | 17 | 0.60714 | 31 | 29 | 0.93548 | 36 | 32 | 0.88889 | 44 | 36 | 0.81818 | 47 | 40 | 0.85106 | 55 | 49 | 0.89091 | 60 | 53 | 0.88333 | 65 | 63 | 0.96923 | 72 | 68 | 0.94444 | 76 | 70 | 0.92105
|  |  | WLED | 31 | 26 | 0.83871 | 49 | 42 | 0.85714 | 57 | 50 | 0.87719 | 60 | 55 | 0.91667 | 85 | 72 | 0.84706 | 91 | 82 | 0.9011 | 106 | 96 | 0.90566 | 133 | 115 | 0.86466 | 151 | 126 | 0.83444 | 162 | 143 | 0.88272 | 176 | 166 | 0.94318 | 183 | 172 | 0.93989
Air Power | Major Program | Qatar ADOC | Program | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
|  | Error Time out | Engineering | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0! | 0 | 0 | #DIV/0!
EDD
GSC
MED
Quality
SADID
SED
SVTAD
WLED
Air Power | Major Program | QEWR | Program | [6 empty] | 1851 | 1735 | 0.93733 | 1858 | 1750 | 0.94187 | 1883 | 1770 | 0.93999 | 1892 | 1782 | 0.94186 | 1911 | 1808 | 0.9461 | 1919 | 1829 | 0.9531 | 1933 | 1914 | 0.99017 | 1937 | 1866 | 0.96335 | 1943 | 1882 | 0.96861 | 1950 | 1900 | 0.97436 | Program |  |  | 0.93733 | 0.94187 | 0.93999 | 0.94186 | 0.9461 | 0.9531 | 0.99017 | 0.96335 | 0.96861 | 0.97436
|  | QEWR IMS in iEPM | Engineering | [6 empty] | 1827 | 1714 | 0.93815 | 1834 | 1729 | 0.94275 | 1859 | 1749 | 0.94083 | 1868 | 1761 | 0.94272 | 1887 | 1787 | 0.94701 | 1895 | 1808 | 0.95409 | 1909 | 1830 | 0.95862 | 1912 | 1845 | 0.96496 | 1918 | 1859 | 0.96924 | 1924 | 1877 | 0.97557 | Engineering |  |  | 0.93815 | 0.94275 | 0.94083 | 0.94272 | 0.94701 | 0.95409 | 0.95862 | 0.96496 | 0.96924 | 0.97557 | 0.96992
|  |  | EPT | [6 empty] | 818 | 755 | 0.92298 | 821 | 765 | 0.93179 | 824 | 774 | 0.93932 | 827 | 779 | 0.94196 | 832 | 791 | 0.95072 | 832 | 799 | 0.96034 | 834 | 805 | 0.96523 | 834 | 809 | 0.97002 | 836 | 814 | 0.97368 | 839 | 819 | 0.97616
|  |  | IOT RIS | [6 empty] | 5 | 3 | 0.6 | 5 | 3 | 0.6 | 5 | 3 | 0.6 | 5 | 3 | 0.6 | 5 | 3 | 0.6 | 5 | 3 | 0.6 | 5 | 3 | 0.6 | 5 | 3 | 0.6 | 5 | 4 | 0.8 | 6 | 4 | 0.66667
|  |  | ISC | [6 empty] | 19 | 18 | 0.94737 | 19 | 18 | 0.94737 | 19 | 18 | 0.94737 | 19 | 18 | 0.94737 | 19 | 18 | 0.94737 | 19 | 18 | 0.94737 | 19 | 81 | 4.2632 | 20 | 18 | 0.9 | 20 | 19 | 0.95 | 20 | 19 | 0.95
|  |  | MPT | [6 empty] | 669 | 660 | 0.98655 | 669 | 660 | 0.98655 | 674 | 660 | 0.97923 | 676 | 660 | 0.97633 | 676 | 661 | 0.97781 | 676 | 662 | 0.97929 | 676 | 668 | 0.98817 | 676 | 669 | 0.98964 | 676 | 669 | 0.98964 | 676 | 669 | 0.98964
|  |  | SDA | [6 empty] | 3 | 3 | 1 | 3 | 3 | 1 | 4 | 4 | 1 | 4 | 4 | 1 | 6 | 5 | 0.83333 | 7 | 6 | 0.85714 | 8 | 6 | 0.75 | 8 | 6 | 0.75 | 8 | 6 | 0.75 | 8 | 6 | 0.75
|  |  | SIT | [6 empty] | 201 | 164 | 0.81592 | 205 | 169 | 0.82439 | 212 | 175 | 0.82547 | 215 | 178 | 0.82791 | 223 | 185 | 0.8296 | 226 | 190 | 0.84071 | 232 | 200 | 0.86207 | 234 | 207 | 0.88462 | 234 | 213 | 0.91026 | 237 | 225 | 0.94937
|  |  | SPE | [6 empty] | 135 | 131 | 0.97037 | 135 | 131 | 0.97037 | 144 | 135 | 0.9375 | 145 | 139 | 0.95862 | 149 | 144 | 0.96644 | 153 | 150 | 0.98039 | 158 | 150 | 0.94937 | 159 | 153 | 0.96226 | 163 | 156 | 0.95706 | 163 | 157 | 0.96319
|  |  | WLE | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[40 empty] | Average | 0.81641 | 0.86302 | 0.91154 | 0.87568 | 0.90345 | 0.9112 | 0.88715 | 0.89882 | 0.90431 | 0.88802 | 0.88288 | 0.88016
[40 empty] | Average | 0.79919 | 0.84776 | 0.89921 | 0.86427 | 0.89212 | 0.90715 | 0.87791 | 0.89364 | 0.90175 | 0.87706 | 0.86 | 0.85796
AN-TYP2 TO3, 6
Barracuda
FSSMI

## RMD CT - BEI CEI
As of: 3/9/22 |  |  |  | Fiscal Month | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 3 Month Avg. | 3 Month Delta |  | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 3 Month Avg. | 3 Month Delta |  | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 |  | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01
Mission Area | PAD | EAC Type | Table Type | Program | 2019-09-01: Program BEI |  |  | Program | Program CEI | [31 empty] | MTD SPI | [19 empty] | ITD SPI
Naval Power | Naval Radars | Watch | BEI Detail | AMDR LRIP | 0.352 | 0.432 | 0.412 | 0.432 | 0.412 | 0.379 | 0.383 | 0.384 | 0.402 | 0.522 | 0.548 | 0.588 | 0.619 | 0.634 | 0.686 | 0.644 | 0.666 | 0.671 | 0.669 | 0.64044 | 0.64994 | 0.635 | 0.68122 | 0.672 | 0.683 | 0.695 | 0.698 | 0.7 | 0.688 | 0.69533 | -0.007 | AMDR LRIP | 0.283 | 0.213 | 0.165 | 0.349 | 0.103 | 0.163 | 0.157 | 0.213 | 0.215 | 0.35 | 0.359 | 0.246 | 0.189 | 0.31 | 0.345 | 0.227 | 0.214 | 0.296 | 0.293 | 0.19632 | 0.14286 | 0.143 | 0.38798 | 0.14286 | 0.222 | 0.243 | 0.16 | 0.125 | 0.171 | 0.152 | -0.072 | AMDR LRIP | [10 empty] | 0.434 | 1.487 | 2.589 | 0.881 | 1.262 | -1.773 | 3.768 | 1.489 | 1.304 | AMDR LRIP | [14 empty] | 0.989 | 0.861 | 0.954 | 0.97 | 0.98
Air Power | Sensors & Systems | Watch | BEI Detail | FSSMI FPIF | 0.87 | 0.861 | 0.856 | 0.848 | 0.845 | 0.842 | 0.839 | 0.837 | 0.834 | 0.833 | 0.831 | 0.829 | 0.828 | 0.827 | 0.826 | 0.827 | 0.825 | 0.821 | 0.821 | 0.82693 | 0.82693 | 0.82693 | 0.82693 | 0.82693 | 0.82693 | 0.82693 | 0.82693 | 0.82693 | 0.82693 | 0.82693 | 0 | FSSMI FPIF | [29 empty] | #DIV/0! | 0 | FSSMI FPIF | 1.173 | 0.871 | 1.707 | 1.078 | 1.225 | 1.663 | 1.383 | 0.698 | 1.4666 | 1.616 | 2.39 | 0.928 | 1.368 | 0.768 | 1.143 |  | 0.612 |  | 1.122 | FSSMI FPIF | 0.954 | 0.954 | 0.959 | 0.96 | 0.962 | 0.966 | 0.969 | 0.967 | 0.97 | 0.974 | 0.986 | 0.986 | 0.988 | 0.987 | 0.987 |  | 0.987 |  | 0.988
Air Power | Sensors & Systems | Watch | BEI Detail | FSSMI FFP | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.8 | 0.8 | 0.81356 | 0.81356 | 0.81356 | 0.81356 | 0.81356 | 0.81356 | 0.81356 | 0.81356 | 0.81356 | 0.81356 | 0.81356 | 0 | FSSMI FFP | [29 empty] | #DIV/0! | 0 | FSSMI FFP | 0.617 | 0.765 | 0.676 | 0.576 | 1.071 | 0.645 | 0.609 | 0.601 | 13.781 | 0.991 | 0.525 | 0.701 | 1.432 | 0.937 | 0.978 |  | 0.892 |  | 0.895 | FSSMI FFP | 0.893 | 0.884 | 0.87 | 0.852 | 0.864 | 0.852 | 0.839 | 0.834 | 0.859 | 0.887 | 0.888 | 0.968 | 0.978 | 0.977 | 0.977 |  | 0.994 |  | 0.895
Air Power | Sensors & Systems | Watch | BEI Detail | FSSMI CP | 0.947 | 0.947 | 0.947 | 0.947 | 0.947 | 0.947 | 0.818 | 0.474 | 0.474 | 0.462 | 0.462 | 0.462 | 0.462 | 0.462 | 0.462 | 0.462 | 0.462 | 0.462 | 0.462 | 0.462 | 0.462 | 0.462 | 0.46154 | 0.46154 | 0.46154 | 0.46154 | 0.46154 | 0.46154 | 0.46154 | 0.46154 | 0 | FSSMI CP | [29 empty] | #DIV/0! | 0 | FSSMI CP | 0.961 | 0.794 | 0.672 | 1.173 | 1.071 | 0.645 | 0.609 | 0.601 | 13.781 | 13.439 | 1 | 58.177 | 0.95 | 2.508 | 0 |  | 0.664 |  | 1.422 | FSSMI CP | 0.996 | 0.994 | 0.982 | 0.99 | 0.997 | 0.994 | 0.989 | 0.995 | 0.859 | 0.995 | 0.975 | 0.996 | 0.995 | 0.998 | 0.111 |  | 0.954 |  | 0.998
Land Warfare & Air Defense (LW&AD) | Lower Tier Air & Missile Defense | Watch | BEI Detail | LTAMDS UMR |  |  |  |  | 0.757 | 0.736 | 0.683 | 0.739 | 0.775 | 0.775 | 0.812 | 0.821 | 0.842 | 0.856 | 0.864 | 0.872 | 0.89 | 0.879 | 0.848 | 0.852 | 0.85688 | 0.867 | 0.87352 | 0.8777 | 0.881 | 0.901 | 0.908 | 0.91 | 0.925 | 0.91433 | 0.024 | LTAMDS UMR | [5 empty] | 0.461 | 0.504 | 0.493 | 0.502 | 0.463 | 1 | 1 | 1 | 1 | 0.472 | 0.517 | 0.449 | 0.371 | 1 | 1 | 0.34498 | 0.46 | 0.34831 | 0.34416 | 0.429 | 0.373 | 0.312 | 0.505 | 0.381 | 0.39933 | 0.008 | LTAMDS UMR | [10 empty] | 0.893 | 0.763 | 1.673 | 0.735 | 0.6 | 0.937 | 0.509 | 0.193 | 1.569 | LTAMDS UMR | [14 empty] | 1.019 | 1.007 | 0.952 | 0.859 | 0.942
Land Warfare & Air Defense (LW&AD) | Lower Tier Air & Missile Defense | Watch | BEI Detail | LTAMDS P3I | 2021-05-01: 1.727; 2021-06-01: 1.039; 2021-07-01: 1.193; 2021-08-01: 0.967; 2021-09-01: 0.688; 2021-10-01: 0.958; 2021-11-01: 1.019; 2021-12-01: 0.971 | 0.995 | -0.958 | LTAMDS P3I | [21 empty] | 0.698 | 0.679 | 0.524 | 0.304 | 0.925 | 0.375 |  |  | 0.375 | -0.925 | LTAMDS P3I | [19 empty] | LTAMDS P3I
Naval Power | Naval Radars | Watch | BEI Detail | EASR Production | 2021-01-01: 0.287; 2021-02-01: 0.306; 2021-03-01: 0.335; 2021-04-01: 0.386; 2021-05-01: 0.35487; 2021-07-01: 0.342; 2021-08-01: 0.37054; 2021-10-01: 0.392; 2021-11-01: 0.397; 2021-12-01: 0.408; 2022-01-01: 0.416 | 0.407 | 0.024 | EASR Production | [17 empty] | 0.204 | 0.287 | 0.343 | 0.10556 |  |  | 0.14557 |  |  | 0.032 | 0.054 | 0.077 | 0.054333 | 0.077 | EASR Production | [10 empty] | 0.61 | 0.24 | 0.279 | -0.078 | 2.534 | 3.226 |  | 0.535 | 0.528 | EASR Production | [14 empty] | 0.799 | 1.069 |  | 1.079 | 1.007
Naval Power | Naval Radars | Watch | BEI Detail | EASR EMD | 0.924 | 0.936 |  | 0.942 | 0.945 | 0.946 | 0.957 | 0.972 | 0.972 | 0.977 | 0.978 | 0.977 | 0.98 | 0.979 | 0.967 | 0.969 | 0.97 |  | 0.975 | 0.973 | 0.96951 | 0.972 | 0.97154 | 0.97358 | 0.975 | 0.976 | 0.976 | 0.978 | 0.978 | 0.97733 | 0.002 | Enterprise Air Surveillance Radar EMD | 0.313 | 0.324 |  |  | 0.273 | 0.136 | 0.327 | 0.533 | 0.2 | 1 | 0.167 |  | 0.143 | 0.368 | 0.417 | 1 | 0.2 |  |  |  | 0.125 | 0.308 |  |  | 0.143 | 0.25 |  | 0.3 | 0.143 | 0.2215 | -0.107 | Enterprise Air Surveillance Radar EMD | [10 empty] | 0 | 0 | 1.404 | 0.986 | 0.342 | 0 |  |  | 0 | Enterprise Air Surveillance Radar EMD | [14 empty] | 0.987 | 0.988 | 0.989 | 0.991 | 0.993
Naval Power | Naval Surface & Undersea Systems | Major Program | BEI Detail | Barracuda | 0.626 | 0.617 | 0.609 | 0.593 | 0.577 | 0.565 | 0.546 | 1 | 0.5 | 0.75 | 0.753 | 0.725 | 0.849 | 0.899 | 0.805 | 0.784 | 0.813 | 0.799 | 0.854 | 0.858 | 0.83789 | 0.85 | 0.82657 | 0.81803 | 0.844 | 0.829 | 0.871 | 0.88 | 0.881 | 0.87733 | 0.052 | Barracuda | 0.269 | 0.214 | 0.036 | 0.083 | 0.026 |  |  | 1 |  | 0.788 | 0.813 | 0.533 | 0.711 | 0.604 | 0.375 | 0.47 | 0.507 | 0.311 | 0.533 | 0.46 | 0.39216 | 0.571 | 0.48571 | 0.6 | 0.673 | 0.585 | 0.689 | 0.552 | 0.512 | 0.58433 | -0.073 | Barracuda | [10 empty] | 0.867 | 0.882 | 0.872 | 0.96 | 1.151 | 0.891 | 0.93 | 1.024 | 1.231 | Barracuda | [14 empty] | 0.985 | 0.981 | 0.98 | 0.981 | 0.988
Naval Power | Sonar Systems | Small Program | BEI Detail | LCS VDS | [10 empty] | 0.709 | 0.658 | 0.75 | 0.739 | 0.71 | 0.651 | 0.678 | 0.629 | 0.624 | 0.53 | 0.53106 | 0.525 | 0.46891 | 0.426 | 0.414 | 0.411 | 0.405 | 0.408 | 0.426 | 0.413 | 0.015 | LCS VDS | [12 empty] | 0.188 | 0.056 | 0.48 | 0.2 | 0.273 | 0.115 | 0.2 |  | 0.028571 | 0.195 |  | 0.044 | 0.186 | 0.153 | 0.135 | 0.284 | 0.21 | 0.20967 | 0.057 | LCS VDS | [14 empty] | -12.396 | 1.772 | 1.706 | 0.157 | 0.305 | LCS VDS | [14 empty] | 0.94 | 1.124 | 1.196 | 1.002 | 0.822
Strategic Missile Defense | Strategic Sensor Systems | Major Program | BEI Detail | KSA THAAD Production Non Reportable | 2020-12-01: 0.658; 2021-01-01: 0.688; 2021-02-01: 0.59; 2021-03-01: 0.489; 2021-04-01: 0.435; 2021-05-01: 0.39851; 2021-06-01: 0.36; 2021-07-01: 0.37474; 2021-08-01: 0.36929; 2021-09-01: 0.363; 2021-10-01: 0.359; 2021-11-01: 0.357; 2021-12-01: 0.353; 2022-01-01: 0.349 | 0.353 | -0.01 | KSA THAAD Production Non Reportable | [16 empty] | 0.398 | [12 empty] | #DIV/0! | 0 | KSA THAAD Production Non Reportable | [14 empty] | 14.775 | 7.232 | 0.786 | 0.548 | 1.213 | KSA THAAD Production Non Reportable | [14 empty] | 1.095 | 1.402 | 1.36 | 1.346 | 1.333
Strategic Missile Defense | Strategic Sensor Systems | Major Program | BEI Detail | KSA THAAD Production Reportable | 2020-12-01: 0.658; 2021-01-01: 0.688; 2021-02-01: 0.59; 2021-03-01: 0.489; 2021-04-01: 0.435; 2021-05-01: 0.39851; 2021-06-01: 0.36; 2021-07-01: 0.37474; 2021-08-01: 0.36929; 2021-09-01: 0.363; 2021-10-01: 0.359; 2021-11-01: 0.357; 2021-12-01: 0.353; 2022-01-01: 0.349 | 0.353 | -0.01 | KSA THAAD Production Reportable | [16 empty] | 0.398 | [12 empty] | #DIV/0! | 0 | KSA THAAD Production Reportable | [14 empty] | 2.362 | 0.993 | 1.086 | 0.903 | 1.447 | KSA THAAD Production Reportable | [14 empty] | 1.334 | 1.258 | 1.236 | 1.181 | 1.224
Strategic Missile Defense | Strategic Sensor Systems | Major Program | BEI Detail | KSA THAAD Long Lead Cost Type | 0.364 | 0.787 | 0.757 | 0.712 | 0.725 | 0.718 | 0.719 | 0.622 | 0.646 | 0.726 | 0.803 | 0.844 | 0.888 | 0.909 | 0.921 | 0.939 | 0.925 | 0.916 | 0.908 | 0.9 | 0.88519 | 0.836 | 0.81579 | 0.81579 | 0.816 | 0.816 | 0.816 | 0.816 | 0.816 | 0.816 | 0 | KSA THAAD Long Lead Cost Type |  |  | 0.297 | 0.331 | 0.27 | 0.363 | 0.373 | 0.302 | 0.315 | 0.481 | 0.398 | 0.405 | 0.527 | 0.296 | 0.438 | 0.429 | 0.028 | [12 empty] | #DIV/0! | 0 | KSA THAAD Long Lead Cost Type | [9 empty] | 1.491 | 1.353 | 0.967 | 0.856 | 1.103 | 0.467 | 1.18 | 0.828 | 0.059 |  | KSA THAAD Long Lead Cost Type | [13 empty] | 0.982 | 0.957 | 0.964 | 0.96 | 0.943
Strategic Missile Defense | Strategic Sensor Systems | Major Program | BEI Detail | KSA THAAD Long Lead Fixed Price | 0.364 | 0.787 | 0.755 | 0.711 | 0.725 | 0.718 | 0.719 | 0.622 | 0.646 | 0.726 | 0.803 | 0.844 | 0.888 | 0.909 | 0.921 | 0.94 | 0.925 | 0.916 | 0.908 | 0.9 | 0.88565 | 0.837 | 0.81569 | 0.81579 | 0.833 | 0.816 | 0.816 | 0.816 | 0.816 | 0.816 | 0 | KSA THAAD Long Lead Fixed Price |  |  | 0.297 | 0.331 | 0.27 | 0.363 | 0.373 | 0.302 | 0.315 | 0.481 | 0.398 | 0.405 | 0.527 | 0.296 | 0.438 | 0.429 | 0.028 | [12 empty] | #DIV/0! | 0 | KSA THAAD Long Lead Fixed Price | [9 empty] | 1.491 | 1.353 | 0.967 | 0.856 | 1.103 | 0.467 | 0.568 | 0.465 | 0.369 | 0.84 | KSA THAAD Long Lead Fixed Price | [13 empty] | 0.982 | 0.957 | 0.922 | 0.891 | 0.864 | 0.939
Air Power | Sensors & Systems | Major Program | BEI Detail | QEWR Reportable CLINs 1001 5001 |  | 0.894 | 0.89 | 0.888 | 0.892 | 0.895 | 0.902 | 0.901 | 0.906 | 0.909 | 0.915 | 0.92 | 0.929 | 0.93 | 0.934 | 0.941 | 0.945 | 0.949 | 0.953 | 0.95 | 0.95414 | 0.961 | 0.96517 | 0.96562 | 0.962 | 0.963 | 0.967 | 0.973 | 0.981 | 0.97367 | 0.018 | QEWR Reportable CLINs 1001 5001 |  |  | 0.315 | 0.331 | 0.268 | 0.326 | 0.43 | 0.366 | 0.418 | 0.377 | 0.38 | 0.355 | 0.468 | 0.446 | 0.423 | 0.16 | 1 | 0.315 | 0.532 | 0.339 | 0.34375 | 0.521 | 0.35 | 0.28125 | 0.321 | 0.509 | 0.486 | 0.469 | 0.558 | 0.50433 | 0.049 | QEWR Reportable CLINs 1001 5001 | [10 empty] | 1.962 | 2.15 | 1.677 | 1.944 | 0.914 | 0.331 | 1.87 | 1.345 | 1.497 | QEWR Reportable CLINs 1001 5001 | [14 empty] | 0.958 | 0.955 | 0.964 | 0.966 | 0.971
Air Power | Sensors & Systems | Major Program | BEI Detail | QEWR Non Reportable CLINs 2001 2002 3001 CFR | 0.925 | 0.944 | 0.942 | 0.947 | 0.948 | 0.953 | 0.94 | 0.946 | 0.935 | 0.948 | 0.94 | 0.93 | 0.942 | 0.938 | 0.951 | 0.958 | 0.954 | 0.946 | 0.955 | 0.962 | 0.96406 | 0.973 | 0.97904 | 0.98121 | 0.986 | 0.982 | 0.982 | 0.97 | 0.986 | 0.97933 | 0.004 | QEWR Non Reportable CLINs 2001 2002 3001 CFR |  | 0.429 | 0.429 | 0.143 | 0.273 | 0.25 | 0.375 | 0.688 | 0.214 | 0.471 | 0.375 | 0.167 | 0.347 | 0.063 | 0.3 | 0.412 | 0.25 | 0.077 | 0.545 | 0.286 | 0.071429 | 0.571 | 0.23529 | 0.33333 | 0.353 | 0.667 | 0.333 |  | 0.333 | 0.333 | -0.334 | QEWR Non Reportable CLINs 2001 2002 3001 CFR | [10 empty] | 0.955 | 0.529 | 4.18 | 1.262 | 0.481 | 0.272 | 0.856 | 0.961 | 1.439 | QEWR Non Reportable CLINs 2001 2002 3001 CFR | [14 empty] | 0.998 | 0.982 | 0.993 | 0.992 | 0.995
Naval Power | Naval Surface & Undersea Systems | Major Program | BEI Detail | MK54 FY16 FY20 Production | 0.81 | 0.823 | 0.803 | 0.84 | 0.839 | 0.835 | 0.848 | 0.821 | 0.828 | 0.823 | 0.821 | 0.827 | 0.83 | 0.809 | 0.823 | 0.827 | 0.803 | 0.836 | 0.817 | 0.813 | 0.7827 | 0.737 | 0.73268 | 0.72371 | 0.726 | 0.734 | 0.738 | 0.726 | 0.685 | 0.71633 | -0.049 | MK54 FY16 FY20 Production | 0.31 | 0.278 |  | 0.385 | 0.356 | 0.296 | 0.253 | 0.133 | 0.692 | 0.647 | 0.385 | 0.512 | 0.143 | 0.063 | 0.276 | 0.171 |  | 0.674 |  | 0.571 |  | 0.4 | 1 | 0.074627 | 0.102 | 0.144 | 0.889 | 0.064 | 0.054 | 0.33567 | -0.09 | MK54 FY16 FY20 Production | [10 empty] | 1.249 | 0.655 | 1.133 | 1.856 | 1.083 | 2.79 | -2.985 | 0.978 | 0.697 | MK54 FY16 FY20 Production | [14 empty] | 0.938 | 1.023 | 0.932 | 0.933 | 0.927
Air Power | Sensors & Systems | Major Program | BEI Detail | SRP FOS2 | [10 empty] | 0.873 | 0.859 | 0.86 | 0.858 | 0.877 | 0.871 | 0.875 | 0.87 | 0.876 | 0.899 | 0.909 | 0.918 | 0.9545 | 0.95243 | 0.97 | 0.975 | 0.977 | 0.98 | 0.984 | 0.98033 | 0.009 | SRP FOS2 | [10 empty] | 1 | 1 | 0.225 | 0.276 | 0.533 | 0.286 | 1 | 1 | 0.353 | 1 | 0.541 | 0.816 | 1 | 0.90476 | 0.763 | 1 | 0.4 | 0.28 | 0.429 | 0.36967 | -0.571 | SRP FOS2 | [14 empty] | 1.094 | 0.991 | 1.068 | 0.995 | 0.939 | SRP FOS2 | [14 empty] | 0.993 | 0.993 | 0.995 | 0.995 | 0.993
Air Power | Sensors & Systems | Small Program | BEI Detail | Qatar ADOC | [10 empty] | 0.97 | 0.97 | 0.967 | 0.97 | 0.97 | 0.969 | 0.974 | 0.974 | 0.966 | 0.966 | 0.96675 | 0.965 | 0.973 | 0.972 | 0.97 | 0.985 | 0.985 | 0.988 | 0.988 | 0.987 | 0.003 | Qatar ADOC | [10 empty] | 0.205 | 0.373 | 0.92 | 0.488 | 0.382 | 0.532 | 0.5 | 0.224 | 0.25 | 0.18 | 0.265 | 0.242 | 0.455 | 0.6 | 0.389 | 0.6 | 0.286 | 0.429 | 0.385 | 0.36667 | -0.215 | Qatar ADOC | [14 empty] | 1.121 | 0.979 | 0.698 | 0.949 | 0.702 | Qatar ADOC | [14 empty] | 0.991 | 0.991 | 0.94 | 0.989 | 0.983
Strategic Missile Defense | Command & Control Solutions | Small Program | BEI Detail | Qatar AOC Upgrade Reportable | 2020-12-01: 0.765; 2021-01-01: 0.525; 2021-02-01: 1.182; 2021-03-01: 0.537; 2021-04-01: 0.588; 2021-05-01: 0.63429; 2021-06-01: 0.749; 2021-07-01: 0.7931; 2021-08-01: 0.77444; 2021-09-01: 0.791; 2021-10-01: 0.836; 2021-11-01: 0.865; 2021-12-01: 0.885; 2022-01-01: 0.908 | 0.886 | 0.072 | Qatar AOC Upgrade Reportable | [16 empty] | 1 | 1 | 0.6 | 0.462 | 0.364 | 0.554 | 0.35714 | 0.27273 | 0.464 | 0.621 | 0.308 | 0.488 | 0.313 | 0.36967 | -0.308 | Qatar AOC Upgrade Reportable | [16 empty] | 0.76 | 0.995 | 1.816 | Qatar AOC Upgrade Reportable | [16 empty] | 0.831 | 0.904 | 1.247
Strategic Missile Defense | Command & Control Solutions | Small Program | BEI Detail | Qatar AOC Upgrade nonReportable | 2020-12-01: 0.765; 2021-01-01: 0.525; 2021-02-01: 0.667; 2021-03-01: 0.537; 2021-04-01: 0.579; 2021-05-01: 0.63429; 2021-06-01: 0.749; 2021-07-01: 0.7931; 2021-08-01: 0.70076; 2021-09-01: 0.791; 2021-10-01: 0.836; 2021-11-01: 0.913; 2021-12-01: 0.885; 2022-01-01: 0.908 | 0.902 | 0.072 | Qatar AOC Upgrade nonReportable | [16 empty] | 1 | 0.316 | 0.397 | 0.436 | 0.355 | 0.554 | 0.35714 |  | 0.421 | 0.421 | 0.308 | 0.629 | 0.313 | 0.41667 | -0.108 | Qatar AOC Upgrade nonReportable | [16 empty] | 0.301 | 3.346 | 1.495 | Qatar AOC Upgrade nonReportable | [16 empty] | 0.399 | 0.767 | 0.865
Land Warfare & Air Defense (LW&AD) | Qatar, Kuwait and Oman Programs | Major Program | BEI Detail | Qatar Depot Operations Cost Type | [10 empty] | 0.935 | 0.991 | 0.988 | 0.997 | 0.971 | 0.971 | 0.97 | 0.975 | 0.975 | 0.98 | 0.98519 | 0.997 | 0.99333 | 0.99335 | 0.998 | 0.993 | 0.998 | 1.015 | 0.996 | 1.003 | 0.003 | Qatar Depot Operations Cost Type | [10 empty] | 0.722 | 0.667 | 0.2 | 1 | 0.083 | 0.182 | 0.961 |  |  |  | 0.333 | 0.5 | 0.95652 | 0.5 | 0.5 | 0.333 | 1 |  | 1 | 1 | 0.667 | Qatar Depot Operations Cost Type | [14 empty] | 1.055 | 0.93 | 0.901 | 1.044 | 0.951 | Qatar Depot Operations Cost Type | [14 empty] | 0.983 | 0.978 | 0.971 | 0.976 | 0.974
Land Warfare & Air Defense (LW&AD) | Qatar, Kuwait and Oman Programs | Small Program | BEI Detail | Qatar Depot Ops FFP | 2020-09-01: 0.988; 2020-10-01: 0.997; 2020-11-01: 0.971; 2020-12-01: 0.971; 2021-01-01: 0.97; 2021-02-01: 0.975; 2021-03-01: 0.975; 2021-04-01: 0.98; 2021-05-01: 0.985; 2021-06-01: 0.997; 2021-07-01: 0.993; 2021-08-01: 0.993; 2021-09-01: 0.998; 2021-10-01: 0.993; 2021-11-01: 0.998; 2022-01-01: 0.996 | 0.997 | 0.003 | Qatar Depot Ops FFP | [12 empty] | 0.2 | 1 | 0.083 | 0.182 | 0.961 |  |  |  | 0.333 | 0.5 | 0.957 | 0.5 | 0.5 | 0.5 | 1 |  | 1 | 1 | 0.5 | Qatar Depot Ops FFP | [19 empty] | Qatar Depot Ops FFP
Land Warfare & Air Defense (LW&AD) | Qatar, Kuwait and Oman Programs | Major Program | BEI Detail | Qatar Patriot Production | 0.86 | 0.859 | 0.86 | 0.861 | 0.858 | 0.855 | 0.856 | 0.852 | 0.845 | 0.851 | 0.85 | 0.85 | 0.851 | 0.963 | 0.853 | 0.854 | 0.86 | 0.86 | 0.862 | 0.862 | 0.862 | 0.862 | 0.86503 | 0.86503 | [5 empty] | #DIV/0! | 0 | Qatar Patriot Production | 0.364 | 0.368 | 0.462 | 0.429 | 0.222 | 0.267 | 0.296 | 0.257 | 0.588 | 0.25 | 0.118 | 0.429 | 0.133 | 0.125 | 0.059 | 0.417 | [6 empty] | 0.34615 | [6 empty] | #DIV/0! | 0 | Qatar Patriot Production | [10 empty] | 0.011 | 5.976 | 0.311 | 2.658 | 11.702 | 16.821 | 8.126 | 66.001 | 2.714 | Qatar Patriot Production | [14 empty] | 0.997 | 0.997 | 0.998 | 1 | 1
Land Warfare & Air Defense (LW&AD) | Qatar, Kuwait and Oman Programs | Major Program | BEI Detail | Qatar Patriot 2 Lot | [29 empty] | #DIV/0! | 0 | Qatar Patriot 2 Lot | [29 empty] | #DIV/0! | 0 | Qatar Patriot 2 Lot | [14 empty] | 0.578 | 0.948 |  | 0.767 |  | Qatar Patriot 2 Lot | [14 empty] | 1 | 0.999 |  | 0.993
Land Warfare & Air Defense (LW&AD) | Qatar, Kuwait and Oman Programs | Major Program | BEI Detail | Qatar NASAMS | [10 empty] | 0.878 | 0.891 | 0.893 | 0.918 | 0.937 | 0.928 | 0.917 | 0.899 | 0.934 | 0.937 | 0.9203 | 0.946 | 0.96152 | 0.94952 | 0.94 | 0.952 | 0.931 | 0.941 | 0.945 | 0.939 | -0.007 | Qatar NASAMS | [10 empty] | 0.522 | 0.362 | 0.284 | 0.296 | 0.413 | 0.44 | 0.257 | 0.255 | 0.147 | 0.143 | 0.073529 | 0.086 | 0.27083 |  | 0.16 | 0.341 |  | 0.111 | 0.143 | 0.127 | -0.198 | Qatar NASAMS | [14 empty] | 0.73 | 3.427 | 0.646 | 0.198 | 0.661 | Qatar NASAMS | [14 empty] | 1.021 | 1.118 | 1.104 | 0.989 | 0.982
Land Warfare & Air Defense (LW&AD) | KSA, UAE, & Bahrain Programs | Major Program | BEI Detail | SNAP | [29 empty] | #DIV/0! | 0 | SNAP | [29 empty] | #DIV/0! | 0 | SNAP | [17 empty] | 0.327 | 1.036 | SNAP | [17 empty] | 1.001 | 1.001
Naval Power | Naval Radars | Major Program | BEI Detail | AEGIS FY18 FY20 Production | [10 empty] | 1 | 0.897 | 0.5 | 1.167 | 1.278 | 0.448 | 0.419 | 0.631 | 0.502 | 0.502 | 0.502 | 0.381 | 0.3475 | 0.574 | 0.754 | 0.843 | 0.833 | 0.846 |  | 0.8395 | -0.843 | AEGIS FY18 FY20 Production | [13 empty] | 0.385 | 1 | [7 empty] | 0.16923 |  |  | 0.523 | 0.077 | 0.069 |  | 0.073 | -0.523 | AEGIS FY18 FY20 Production | [14 empty] | 1.453 | 0.779 | 1.175 | 1.395 |  | AEGIS FY18 FY20 Production | [14 empty] | 1.07 | 1.048 | 1.126 | 1.153
Naval Power | Naval Surface & Undersea Systems | Major Program | BEI Detail | DDG 1002 Ship Set 3 Non Reportable | 0.964 | 0.959 | 0.958 | 0.975 | 0.976 | 0.976 | 0.978 | 0.924 | 0.977 | 0.979 | 0.978 | 0.978 | 0.978 | 0.98 | 0.98 | 0.98 | 0.985 | 0.986 | 0.986 | 0.986 | 0.98703 | 0.988 | 0.988 | 0.988 |  |  |  |  | 0.961 | 0.961 | 0.961 | DDG 1002 Ship Set 3 Non Reportable | 0.472 | [5 empty] | 0.182 |  | 0.667 |  |  |  | 0.5 | 1 | 0.143 | 0.111 | 0.923 | 0.4 |  |  |  | 1 | [7 empty] | #DIV/0! | 0 | DDG 1002 Ship Set 3 Non Reportable | [10 empty] | 0.701 | 1.42 | 1.671 | 2.389 | 3.971 | 2.239 | 4.537 | 3.28 | 1.435 | DDG 1002 Ship Set 3 Non Reportable | [14 empty] | 0.986 | 0.987 | 0.988 | 0.989 | 0.99
Strategic Missile Defense | Strategic Sensor Systems | Small Program | BEI Detail | AN/TPY-2 TO3 | [10 empty] | 0.636 | 0.624 | 0.656 | 0.672 | 0.648 | 0.576 | 0.65 | 0.647 | 0.613 | 0.507 | 0.5 | 0.529 | 0.52381 | 0.51351 | 0.531 | 0.51351 | 0.526 | 0.777 | 0.827 | 0.71 | 0.31349 | AN/TPY-2 TO3 | [10 empty] | 0.231 | 0.261 | 0.316 | 0.1 | 0.2 | 0.102 | 0.469 | 0.069 | 0.111 | 0.156 | 0.042 | 0.196 | 0.11111 | 0.54839 | 0.298 |  |  | 0.357 | 0.875 | 0.616 | 0.875 | AN/TPY-2 TO3 | [14 empty] | 0.22 | 0.068 | 0.408 | 0.611 | 0.679 | AN/TPY-2 TO3 | [14 empty] | 0.811 | 0.728 | 0.765 | 0.75 | 0.744
Strategic Missile Defense | Strategic Sensor Systems | Small Program | BEI Detail | AN/TPY-2 RDC TO6 | 2020-12-01: 0.706; 2021-01-01: 0.673; 2021-02-01: 0.873; 2021-03-01: 0.763; 2021-04-01: 0.789; 2021-05-01: 0.848; 2021-06-01: 0.848; 2021-07-01: 0.80556; 2021-08-01: 0.8267; 2021-09-01: 0.828; 2021-10-01: 0.904; 2021-11-01: 0.885; 2021-12-01: 0.905 | 0.895 | -0.904 | AN/TPY-2 RDC TO6 | [16 empty] | 0.727 | 0.769 | 0.635 | 0.648 | 1 | 0.571 | 0.52727 | 0.46667 | 0.554 | 0.76 | 0.591 | 0.567 |  | 0.579 | -0.76 | AN/TPY-2 RDC TO6 | [16 empty] | 0.931 |  | 0.901 | AN/TPY-2 RDC TO6 | [16 empty] | 0.953 |  | 0.96
Strategic Missile Defense | Strategic Sensor Systems | Major Program | BEI Detail | AN/TPY-2 Radar 13 | 2021-08-01: 0.25; 2021-09-01: 0.235; 2021-12-01: 0.485; 2022-01-01: 0.574 | 0.5295 | 0.574 | AN/TPY-2 Radar 13 | [24 empty] | 0.167 |  |  | 0.125 | 0.368 | 0.2465 | 0.368 | AN/TPY-2 Radar 13
Land Warfare & Air Defense (LW&AD) | Lower Tier Air & Missile Defense | Major Program | BEI Detail | CY21 Patriot ESM | [29 empty] | #DIV/0! | 0 | CY21 Patriot ESM | [29 empty] | #DIV/0! | 0 | CY21 Patriot ESM
Land Warfare & Air Defense (LW&AD) | KSA, UAE, & Bahrain Programs | Major Program | BEI Detail | Bahrain Patriot 2 Lot | [10 empty] | 0.929 | 0.815 | 0.918 | 0.998 | 0.944 | 0.916 | 2 | 0.955 | 0.965 | 0.946 | 0.92777 | 0.944 | 0.93253 | 0.93477 | 0.923 | 0.932 | 0.926 | 1 | 0.94 | 0.95533 | 0.008 | Bahrain Patriot 2 Lot | [10 empty] | 0.674 | 0.962 | 0.632 | 0.62 | 0.509 | 0.54 |  |  | 0.69 | 0.595 | 0.52427 | 0.633 | 0.55172 | 0.5875 | 0.578 | 0.689 | 0.604 |  |  | 0.604 | -0.689 | Bahrain Patriot 2 Lot | [14 empty] | 1.106 | 0.668 | 0.838 | 4.238 | 1.141 | Bahrain Patriot 2 Lot | [14 empty] | 1.118 | 1.05 | 1.03 | 1.087 | 1.094
Land Warfare & Air Defense (LW&AD) | Lower Tier Air & Missile Defense | Major Program | BEI Detail | DSLC FRP | [29 empty] | #DIV/0! | 0 | DSLC FRP | [29 empty] | #DIV/0! | 0 | DSLC FRP | [14 empty] | 0.626 | 0.977 | 0.555 | 0.234 |  | DSLC FRP | [14 empty] | 2.451 | 2.182 | 1.957 | 1.73
Land Warfare & Air Defense (LW&AD) | EUCOM Programs | Major Program | BEI Detail | Poland Patriot Phase 1 | 0.608 | 0.54 | 0.651 | 0.774 | 0.759 | 0.75 | 0.783 | 0.783 | 0.803 | 0.77 | 0.775 | 0.799 | 0.811 | 0.818 | 0.829 | 0.803 | 0.779 | 0.915 | 0.955 | 0.944 | 0.93958 | 0.922 | 0.91738 | 0.9034 | 0.913 | 0.916 | 0.942 | 0.918 | 0.969 | 0.943 | 0.053 | Poland Patriot Phase 1 | 0.149 | 0.227 | 0.429 | 0.356 | 0.209 | 0.346 | 1 | 0.458 | 0.449 | 0.442 | 0.339 | 0.534 | 0.471 | 0.523 | 0.515 | 0.257 |  |  | 0.347 | 0.471 | 0.45882 | 0.444 | 0.25743 | 0.29885 | 0.513 | 0.389 | 0.486 | 0.228 | 0.351 | 0.355 | -0.038 | Poland Patriot Phase 1 | [10 empty] | 0.777 | 0.874 | -0.145 | 0.38 | 0.853 | 0.864 | 0.197 | -0.018 | 0.882 | Poland Patriot Phase 1 | [14 empty] | 1.055 | 1.04 | 0.976 | 1.079 | 1.056
Land Warfare & Air Defense (LW&AD) | EUCOM Programs | Major Program | BEI Detail | Patriot Sweden | 0.795 | 0.846 | 0.902 | 0.929 | 0.866 | 0.828 | 0.82 | 0.81 | 0.813 | 0.813 | 0.805 | 1.016 | 0.99 | 0.973 | 0.953 | 0.931 | 0.917 | 0.9 | 0.904 | 0.844 | 0.89694 | 0.916 | 0.91842 | 0.92091 | 0.935 | 0.935 | 0.934 | 0.93 | 0.938 | 0.934 | 0.003 | Patriot Sweden | 0.462 | 0.4 | 0.5 | 0.593 | 0.444 | 0.27 | 0.618 | 0.529 | 0.516 | 0.628 | 0.439 | 0.891 | 1 | 0.414 | 0.556 | 0.594 | 0.486 | 0.375 | 0.5 | 1 | 0.58333 | 0.624 | 0.63158 | 0.33333 | 0.517 | 0.34 | 0.333 | 0.382 | 0.347 | 0.354 | 0.007 | Patriot Sweden | [10 empty] | 0.534 | -0.591 | 0.681 | 0.588 | 0.912 | 0.579 | 0.74 | 0.404 | 1.09 | Patriot Sweden | [14 empty] | 1.049 | 1.016 | 0.999 | 0.966 | 0.972
Land Warfare & Air Defense (LW&AD) | EUCOM Programs | Major Program | BEI Detail | Romania Patriot 3 Lot | 1 | 1 | 0.609 | 0.732 | 0.77 | 0.674 | 0.874 | 0.974 | 1.017 | 0.928 | 0.943 | 0.853 | 0.859 | 0.867 | 0.857 | 0.832 | 0.87 | 0.885 | 0.886 | 0.886 | 0.99322 | 0.993 | 0.96719 | 0.98645 | 0.977 | 0.958 | 0.934 | 0.916 | 0.923 | 0.92433 | -0.035 | Romania Patriot 3 Lot |  | 0.75 | 0.438 | 0.588 | 0.636 | 0.414 | 0.766 | 0.813 | 0.595 | 0.283 | 0.455 | 0.565 | 0.692 | 0.583 | 0.486 | 0.457 | 0.651 | 0.549 | 0.686 | 0.636 |  | 0.316 | 0.5 | 0.70833 | 0.481 | 0.556 | 0.406 | 0.478 | 0.774 | 0.55267 | 0.218 | Romania Patriot 3 Lot | [10 empty] | 1.381 | 0.423 | 100.614 | 0.546 | 0.689 | 1.358 | 0.321 | 0.528 | 0.691 | Romania Patriot 3 Lot | [14 empty] | 1.147 | 1.17 | 1.073 | 1.022 | 0.968
Land Warfare & Air Defense (LW&AD) | KSA, UAE, & Bahrain Programs | Major Program | BEI Detail | UAE Patriot 100 Lot GEMT Missile | [29 empty] | #DIV/0! | 0 | UAE Patriot 100 Lot GEMT Missile | [29 empty] | #DIV/0! | 0 | UAE Patriot 100 Lot GEMT Missile | [10 empty] | 0.237 | 0.195 | 0.273 | 0.15 | 0.333 | 0.511 | 0.297 |  |  | UAE Patriot 100 Lot GEMT Missile | [14 empty] | 1.013 | 0.976 | 0.941
Land Warfare & Air Defense (LW&AD) | KSA, UAE, & Bahrain Programs | Major Program | BEI Detail | UAE 3 Lot Fire Units | [29 empty] | #DIV/0! | 0 | UAE 3 Lot Fire Units | [29 empty] | #DIV/0! | 0 | UAE 3 Lot Fire Units | [10 empty] | 0.631 | 3.65 | 1.483 | 0.447 | 0.69 | 1.199 | 1.24 |  |  | UAE 3 Lot Fire Units | [14 empty] | 0.959 | 0.97 | 0.974
Land Warfare & Air Defense (LW&AD) | Short & Medium Range Air Defense | Small Program | BEI Detail | Enhanced Sentinel A3 Radars | 2020-12-01: 0.828; 2021-01-01: 0.823; 2021-02-01: 0.812; 2021-03-01: 0.792; 2021-04-01: 0.805; 2021-05-01: 0.802; 2021-06-01: 0.825; 2021-07-01: 0.85; 2021-08-01: 0.847; 2021-09-01: 0.905; 2021-10-01: 0.986; 2021-11-01: 0.986; 2021-12-01: 0.948; 2022-01-01: 0.96 | 0.96467 | -0.026 | Enhanced Sentinel A3 Radars | [16 empty] | 0.235 | 0.19 | 0.182 | 0.25 | 0.182 | 0.25 | 0.643 |  | 0.385 |  |  |  | 0.8 | 0.8 | 0.8 | Enhanced Sentinel A3 Radars | [19 empty] | Enhanced Sentinel A3 Radars
Land Warfare & Air Defense (LW&AD) | Short & Medium Range Air Defense | Small Program | BEI Detail | Sentinel A3 USG 25 | 2020-11-01: 0.912; 2020-12-01: 0.97; 2021-01-01: 1; 2021-02-01: 1; 2021-03-01: 1 | #DIV/0! | 0 | Sentinel A3 USG 25 | [15 empty] | 1 | 1 | 1 | [11 empty] | #DIV/0! | 0 | Sentinel A3 USG 25
Strategic Missile Defense | Strategic Sensor Systems | Major Program | BEI Detail | THAAD UAE Fixed Price | [29 empty] | #DIV/0! | 0 | THAAD UAE Fixed Price | [29 empty] | #DIV/0! | 0 | THAAD UAE Fixed Price | [14 empty] | 1.122 | 7.149 | 0.9 |  |  | THAAD UAE Fixed Price | [14 empty] | 0.993 | 0.994 | 0.994
Strategic Missile Defense | Strategic Sensor Systems | Major Program | BEI Detail | THAAD UAE Cost Type | 2020-08-01: 0.96; 2020-10-01: 0.969; 2020-11-01: 0.958; 2021-01-01: 0.963; 2021-02-01: 0.965; 2021-03-01: 0.895; 2021-04-01: 0.89; 2021-05-01: 0.8981; 2021-06-01: 0.905; 2021-07-01: 0.9121; 2021-08-01: 0.90815; 2021-09-01: 0.915; 2021-10-01: 0.916; 2021-11-01: 0.945; 2021-12-01: 0.949; 2022-01-01: 0.96 | 0.95133 | 0.044 | THAAD UAE Cost Type | [11 empty] | 0.521 | [6 empty] | 0.833 |  |  |  | 0.21429 | 0.15385 | 0.209 | 1 | 0.024 | 0.325 |  | 0.1745 | -1 | THAAD UAE Cost Type | [14 empty] | 0.877 | 0.847 | 0.652 | 3.663 | 0.585 | THAAD UAE Cost Type | [14 empty] | 0.989 | 0.988 | 0.987 | 0.992 | 0.991
Strategic Missile Defense | Command & Control Solutions | Major Program | BEI Detail | TAADS | 2020-09-01: 0.686; 2020-10-01: 1.004; 2020-11-01: 0.691; 2020-12-01: 0.841; 2021-01-01: 0.796; 2021-02-01: 0.752; 2021-03-01: 0.796; 2021-04-01: 0.692; 2021-05-01: 0.74404; 2021-06-01: 0.691; 2021-07-01: 0.96355; 2021-08-01: 0.95434; 2021-09-01: 0.921; 2021-10-01: 0.899; 2021-11-01: 0.901; 2021-12-01: 0.882; 2022-01-01: 1.019 | 0.934 | 0.12 | TAADS | [12 empty] | 0.549 | 0.633 |  | 0.387 | 0.242 | 1 |  | 0.252 | 1 |  | 0.37255 | 1 | 0.436 | 0.333 | 0.406 | 0.415 | 0.626 | 0.48233 | 0.293 | TAADS | [16 empty] | 0.536 | 2.329 |  | TAADS | [16 empty] | 0.938 | 1.079
Strategic Missile Defense | Strategic Engagement Systems | Major Program | BEI Detail | SM3 IIA RDTE | 0.944 | 0.924 | 0.92 | 0.913 | 0.918 | 0.924 | 0.924 | 0.928 | 0.858 | 0.959 | 0.94 | 1.016 | 1.056 | 1.116 | 1.134 | 1.142 | 1.17 | 1.194 | 1.219 | 1.296 | 1.342 | 1.397 | 1.4202 | 1.4391 | 1.412 | 1.432 | 1.42 | 1.428 | 1.374 | 1.4073 | -0.058 | SM3 IIA RDTE | 0.399 | 0.462 | 0.329 | 0.383 | 0.255 | 0.478 | 0.33 | 0.19 | 0.507 | 0.316 | 0.319 | 0.28 | 0.373 | 0.319 | 0.283 | 0.309 | 0.319 | 0.348 | 0.29 | 0.262 | 0.31579 | 0.437 | 0.47119 | 0.28253 | 0.363 | 0.196 | 0.345 | 0.31 | 0.433 | 0.36267 | 0.237 | SM3 IIA RDTE | [10 empty] | 0.793 | 1.569 | 1.509 | 1.278 | 0.749 | 1.04 | 1.679 | 2.01 | 0.849 | SM3 IIA RDTE | [14 empty] | 0.998 | 1.004 | 1.021 | 1.036 | 1.032
Strategic Missile Defense | Strategic Engagement Systems | Major Program | BEI Detail | SM3 IB Multi Year | [29 empty] | #DIV/0! | 0 | SM3 IB Multi Year | [19 empty] | 0.813 |  | 0.455 | 0.21973 | [5 empty] | 0.188 | 0.188 | 0.188 | SM3 IB Multi Year | [19 empty] | SM3 IB Multi Year
Strategic Missile Defense | Strategic Engagement Systems | Small Program | BEI Detail | SM3 1B FY18 | 2020-07-01: 1.149; 2020-08-01: 1.132; 2020-09-01: 0.9; 2020-10-01: 1.037; 2020-11-01: 1.042; 2020-12-01: 0.908; 2021-01-01: 0.96; 2021-02-01: 0.939; 2021-03-01: 0.891; 2021-04-01: 0.9; 2021-05-01: 0.923; 2021-06-01: 0.96; 2021-07-01: 0.9806; 2021-08-01: 0.989; 2021-09-01: 0.991 | #DIV/0! | 0 | SM3 1B FY18 | [10 empty] | 0.35 | 0.649 |  | 0.251 | 0.762 |  | 0.376 | 0.462 |  | 0.145 | 0.568 | 0.696 | 0.8 | 0.425 | 0.4 |  |  |  |  | #DIV/0! | 0 | SM3 1B FY18 | [14 empty] | 0.976 | 0.888 | 0.7 | 0.618 | 0.803 | SM3 1B FY18 | [14 empty] | 1.056 | 1.048 | 1.032 | 1.017 | 1.01
Strategic Missile Defense | Strategic Engagement Systems | Major Program | BEI Detail | SM3 BLK IIA DEV | 0.956 | 0.969 | 0.951 | 0.937 | 0.955 | 0.973 | 0.966 | 0.971 | 0.993 | 0.975 | 0.971 | 0.959 | 0.963 | 0.971 | 0.983 | 0.972 | 0.963 | 0.977 | 0.99 | 0.994 | 0.994 | 0.966 | 0.998 | 0.998 | 0.998 | 0.998 | 0.998 | 0.991 | 0.988 | 0.99233 | -0.01 | SM3 BLK IIA DEV | 0.595 | 0.333 | 0.29 | 0.488 | 0.357 | 0.81 | 0.577 | 0.633 | 0.5 | 0.389 | 0.571 | 0.318 | 0.538 | 0.52 | 0.561 | 0.267 | 0.462 | 0.375 | 0.579 | 0.333 |  |  | 0.5 |  |  |  |  | 0.5 | 0.111 | 0.3055 | 0.111 | SM3 BLK IIA DEV | [10 empty] | 1.097 | 1 | 0.965 | 1.118 | 1.319 | 1.031 | 0.817 | 6.887 | -5.14 | SM3 BLK IIA DEV | [14 empty] | 1 | 1 | 1 | 1 | 1
Strategic Missile Defense | Integrated Missile Defense Solutions | Major Program | BEI Detail | Next Generation Interceptor | 2021-06-01: 0.592; 2021-07-01: 0.612; 2021-08-01: 0.79638; 2021-09-01: 0.877; 2021-10-01: 0.868; 2021-11-01: 0.848; 2021-12-01: 0.895; 2022-01-01: 0.95 | 0.89767 | 0.082 | Next Generation Interceptor | [22 empty] | 0.581 | 0.47727 | 0.685 | 0.627 | 0.592 | 0.6 | 0.743 | 0.645 | 0.116 | Next Generation Interceptor | [19 empty] | Next Generation Interceptor
Naval Power | Naval Shipboard Missiles | Small Program | BEI Detail | SM6 FY19 23 MY Production | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.1111 | 1.109 | 1.6154 | 1.7917 | 1.68 | 1.452 | 0.763 | 0.8 | 0.84 | 0.801 | -0.612 | SM6 FY19 23 MY Production | [21 empty] | 0.143 | 0.125 |  |  | 0.118 |  | 0.079 | 0.306 | 0.1925 | 0.188 | SM6 FY19 23 MY Production | [14 empty] | 1 | 1.444 | 5.225 | 16.272 | 8.95 | SM6 FY19 23 MY Production | [14 empty] | 1 | 1.059 | 2.225 | 5.297 | 6.167
Naval Power | Naval Shipboard Missiles | Small Program | BEI Detail | ESSM EMD Phase | 0.868 | 0.874 | 0.873 | 0.876 | 0.896 | 0.906 | 0.923 | 0.927 | 0.941 | 0.944 | 0.942 | 0.939 | 1.002 | 1.002 | 1.002 | 0.997 | 1 | 1 | 1.002 | 1.003 | 1 | 0.998 | 0.99886 | 1.0046 | 0.994 | 0.994 | 0.994 | 0.992 | 0.991 | 0.99233 | -0.003 | ESSM EMD Phase |  |  | 0.125 | 0.145 | 0.174 | 0.375 | 0.453 | 0.667 | 0.2 | 0.263 |  |  | 1 |  |  | 0.987 | [7 empty] | 0.5 | 0.623 |  |  |  |  | #DIV/0! | 0 | ESSM EMD Phase | [10 empty] | 0 | 0 | -0.017 | 0.445 | 0.56 | -2.449 | 0.456 | 0.781 | 0.916 | ESSM EMD Phase | [14 empty] | 0.998 | 0.998 | 0.998 |  | 0.998
Naval Power | Naval Shipboard Missiles | Major Program | BEI Detail | ESSM Block II LRIP | [29 empty] | #DIV/0! | 0 | ESSM Block II LRIP | [21 empty] | 0.508 | 0.44 | 0.33333 |  |  |  |  | 0.383 | 0.383 | 0.383 | ESSM Block II LRIP | [16 empty] | 1.58 |  |  | ESSM Block II LRIP | [16 empty] | 2.087
Naval Power | Naval Air Missiles | Small Program | BEI Detail | AIM-9X System Improvement Program III | [10 empty] | 0.982 | 0.981 | 0.985 | 0.987 | 0.988 | 0.989 | 0.987 | 0.986 | 0.976 | 0.972 | 0.972 | 0.975 | 0.97319 | 0.97961 | 0.976 | 0.977 | 0.979 | 0.978 | 0.977 | 0.978 | 0 | AIM-9X System Improvement Program III | [10 empty] | 0.382 | 0.509 | 0.548 | 0.554 | 0.489 | 0.492 | 0.4 | 0.441 | 0.387 | 0.594 | 0.5 | 0.409 | 0.33333 | 0.27027 | 0.375 | 0.435 | 0.609 | 0.531 | 0.276 | 0.472 | -0.159 | AIM-9X System Improvement Program III | [14 empty] | 0.913 | 1.749 | 0.873 | 0.801 | 0.701 | AIM-9X System Improvement Program III | [14 empty] | 0.984 | 0.99 | 0.989 | 0.987 | 0.982
Air Power | Tactical Strike | Small Program | BEI Detail | StormBreaker SDB II iECP | 0.916 | 0.926 | 0.917 | 0.9 | 0.904 | 0.904 | 0.893 | 0.889 | 0.893 | 0.896 | 0.899 | 0.909 | 0.913 | 0.899 | 0.901 | 0.901 | 0.899 | 0.894 | 0.885 | 0.856 | 0.855 | 0.865 | 0.86928 | 0.86944 | 0.866 | 0.874 | 0.871 | 0.872 | 0.88 | 0.87433 | 0.006 | StormBreaker SDB II iECP | 0.578 | 0.64 | 0.356 | 0.407 | 0.339 | 0.412 | 0.282 | 0.197 | 0.308 | 0.473 | 0.373 | 0.329 | 0.438 | 0.448 | 0.575 | 0.476 | 0.485 | 0.468 | 0.39 | 0.463 | 0.6 | 0.536 | 0.39759 | 0.48485 | 0.613 | 0.634 | 0.456 | 0.479 | 0.491 | 0.47533 | -0.143 | StormBreaker SDB II iECP | 1.191 | 1.186 | 0.832 | 0.844 | 0.863 | 1.052 | 0.896 | 0.938 | 1.075 | 0.796 | 1.058 | 1.112 | 0.92 | 0.975 | 0.923 | 0.96 | 0.669 | 1.119 |  | StormBreaker SDB II iECP | 0.975 | 0.983 | 0.982 | 0.97 | 0.966 | 0.968 | 0.966 | 0.965 | 0.968 | 0.963 | 0.965 | 0.968 | 0.967 | 0.967 | 0.966 | 0.966 | 0.96 | 0.962
Air Power | Air Dominance | Major Program | BEI Detail | F3R Phase 4b | 0.766 | 0.759 | 0.753 | 0.744 | 0.838 | 0.834 | 0.837 | 0.841 | 0.849 | 0.863 | 0.871 | 0.882 | 1.004 | 0.994 | 0.997 | 0.989 | 0.989 | 0.989 | 0.982 | 0.982 | 0.98642 | 0.991 | [7 empty] | #DIV/0! | 0 | F3R Phase 4b | 1 |  |  |  | 0.06 | 0.132 | 0.328 | 0.487 | 0.37 | 0.576 | 0.375 | 0.378 | 1 | 0.607 | 0.739 | 0.735 | 0.682 | 0.813 | 1 | 1 | 0.75 | 0.857 | [7 empty] | #DIV/0! | 0 | F3R Phase 4b | 1.194 | -3.043 | 1.157 | 0.386 | 0.431 | 0.951 | 1.687 | 32.266 | 29.926 | 9.415 | 259.857 | -4.609 | -0.246 | 0.706 | 0.753 | 0.935 | 0.858 | 1.457 | 0.28 | F3R Phase 4b | 0.87 | 0.899 | 0.9 | 0.893 | 0.888 | 0.889 | 0.892 | 0.896 | 0.903 | 0.913 | 0.918 | 0.921 | 1 | 0.998 | 0.997 | 0.997 | 0.996 | 0.997 | 0.992
Air Power | Air Dominance | Major Program | BEI Detail | F3R Phase 5 | 0.734 | 0.631 | 0.553 | 0.481 | 0.456 | 0.428 | 0.451 | 0.462 | 0.475 | 0.506 | 0.531 | 0.532 | 1 | 1 | 0.983 | 0.983 | 0.967 | 0.945 | 0.943 | 0.885 | 0.89 | 0.908 | 0.89815 | 0.9008 | 0.89 | 0.898 | 0.894 | 0.891 | 0.891 | 0.892 | -0.007 | F3R Phase 5 | 1 | 0.151 |  |  | 0.022 | 0.333 | 0.306 | 0.385 | 0.229 | 0.379 | 0.439 | 0.172 | 0.981 | 0.906 | 0.513 | 0.627 | 0.705 | 0.667 | 0.75 | 0.545 | 0.65957 | 0.774 | 0.52381 | 0.55556 | 0.61 | 0.644 | 0.684 | 0.806 | 0.688 | 0.726 | 0.044 | F3R Phase 5 | 0.667 | 0.58 | 0.581 | 0.554 | 0.546 | 0.64 | 0.632 | 0.69 | 0.64 | 0.731 | 0.654 | 0.695 | -0.108 | 0.896 | 0.677 | 1.099 | 0.751 | 0.647 | 0.61 | F3R Phase 5 | 0.829 | 0.781 | 0.749 | 0.717 | 0.695 | 0.688 | 0.681 | 0.681 | 0.678 | 0.682 | 0.681 | 0.681 | 0.995 | 0.99 | 0.975 | 0.98 | 0.973 | 0.964 | 0.949
Advanced Technology | Advanced Effector Programs | Major Program | BEI Detail | HAWC Phase 2 | 2020-10-01: 0.837; 2020-11-01: 0.794; 2020-12-01: 0.771; 2021-01-01: 0.867; 2021-02-01: 0.893; 2021-03-01: 0.969; 2021-04-01: 0.992; 2021-05-01: 0.941; 2021-06-01: 0.894; 2021-07-01: 0.868; 2021-08-01: 0.871; 2021-09-01: 0.982 | #DIV/0! | 0 | HAWC Phase 2 | [13 empty] | 0.383 | 0.244 | 0.525 | 0.174 | 0.423 | 0.822 | 0.704 | 0.444 | 0.25 | 0.333 | 0.333 | 1 |  |  |  |  | #DIV/0! | 0 | HAWC Phase 2
Land Warfare & Air Defense (LW&AD) | Indopacom Programs | Major Program | BEI Detail | NASAMS Land 19 | [5 empty] | 0.647 | 0.527 | 0.779 | 0.748 | 0.748 | 0.696 | 0.646 | 0.841 | 0.804 | 0.744 | 0.905 | 0.869 | 0.816 | 0.872 | 0.836 | 0.8 | 0.859 | 0.834 | 0.819 | 0.797 | 0.831 | 0.817 | 0.804 | 0.795 | 0.80533 | -0.036 | NASAMS Land 19 | [15 empty] | 0.167 |  |  | 0.209 |  |  | 0.309 | [7 empty] | #DIV/0! | 0 | NASAMS Land 19
Naval Power | Naval Air Missiles | Major Program | BEI Detail | Maritime Strike Tomahawk IP and T | [10 empty] | 0.861 | 0.856 | 0.879 | 0.878 | 0.889 | 0.885 | 0.873 | 0.877 | 0.887 | 0.869 | 0.851 | 0.864 | 0.86071 | 0.85106 | 0.832 | 0.853 | 0.86 | 0.863 | 0.876 | 0.86633 | 0.023 | Maritime Strike Tomahawk IP and T | [10 empty] | 0.41 | 0.617 | 0.69 | 0.563 | 0.5 | 0.674 | 1 | 0.556 | 0.529 | 0.547 | 0.4569 | 0.554 | 0.68966 | 0.53125 | 0.554 | 0.662 | 0.615 | 0.44 | 0.415 | 0.49 | -0.247 | Maritime Strike Tomahawk IP and T | [14 empty] | 1.161 | 1.057 | 0.952 | 1.302 | 1.045 | Maritime Strike Tomahawk IP and T | [14 empty] | 0.939 | 0.949 | 0.947 | 0.964 | 0.969
Air Power | Sensors & Systems | Small Program | BEI Detail-2 | BSU Analysis and Integration | [10 empty] | 0.611 | 0.478 |  | 0.432 | 0.378 | 0.368 | 0.474 | 0.596 | 0.639 | 0.677 | 0.67073 | 0.621 | 0.81731 | 0.81579 | 0.754 | 0.68 | 0.629 | 0.703 | 0.739 | 0.69033 | 0.059 | BSU Analysis and Integration | [15 empty] | 0.083 | 0.5 | 0.667 | 0.2 | 0.444 | 0.45455 | 0.077 | 0.875 | 0.45455 | 0.286 | 0.5 |  | 0.565 | 0.917 | 0.741 | 0.417 | BSU Analysis and Integration | [18 empty] | 1.034 | BSU Analysis and Integration | [18 empty] | 0.96
Air Power | Sensors & Systems | Major Program | BEI Detail-2 | Clear Cod UEWR | [6 empty] | 0.966 | 0.965 | 0.963 | 0.968 | 0.966 | 0.962 | 0.969 | 0.967 | 0.97 | 0.966 | 0.965 | 0.993 | 0.994 | 0.993 | 0.99141 | 0.99 | 0.98792 | 0.98595 | 0.987 | 0.958 | 0.99 | 0.982 | 0.985 | 0.98567 | 0.027 | Clear Cod UEWR | 0.367 | 0.222 | 0.306 | 0.321 | 0.531 | 0.5 | 0.467 | 0.214 | 0.375 | 0.389 | 0.2 |  | 0.222 | 0.25 | 0.179 | 0.157 |  | 0.226 | 0.606 | 0.55 | 0.2 | 0.366 | 0.13333 | 0.13043 | 0.313 | 0.25 | 0.667 |  | 0.25 | 0.4585 | 0 | Clear Cod UEWR | [18 empty] | 1.048 | Clear Cod UEWR | [18 empty] | 0.998
Air Power | Sensors & Systems | Minor Program | BEI Detail-2 | Qatar ADOC FFP | [6 empty] | 0.97 | 0.971 | 0.956 | 0.969 | 0.97 | 0.97 | 0.967 | 0.969 | 0.97 | 0.969 | 0.974 | 0.974 | 0.966 | 0.966 | 0.967 | 0.965 | 0.973 | 0.972 | 0.97 | 0.985 | 0.985 |  |  | 0.985 | -0.985 | Qatar ADOC FFP | 0.449 | 0.476 | 0.351 | 0.308 | 0.417 | 0.31 | 0.157 | 0.362 | 0.368 | 0.4 | 0.205 | 0.73 | 0.92 | 0.463 | 0.371 | 0.532 | 0.5 | 0.224 | 0.25 | 0.18 | 0.265 | 0.242 | 0.455 | 0.6 | 0.389 | 0.6 | 0.286 |  |  | 0.286 | -0.6 | Qatar ADOC FFP | [18 empty] | 0.466 | Qatar ADOC FFP | [18 empty] | 0.938
Air Power | Tactical Strike | Small Program | BEI Detail-2 | HARM REIK NRE | [6 empty] | 1.036 | 1.037 | 1.039 | 1.011 | 1.021 | 1.02 | 1 | 0.974 | 0.982 | 0.885 | 0.885 | 0.954 | 0.968 | 0.981 | 0.92899 | 0.92 | 0.90728 | 0.91391 | 0.921 | 0.927 | 0.934 | 0.934 |  | 0.934 | -0.927 | HARM REIK NRE | 1 | 0.833 | 0.35 | 0.813 |  | 1 | 0.95 | 0.909 | 0.87 | 0.892 | 0.947 | 0.5 | 1 | 0.4 | 0.222 | 0.333 | 0.677 | 1 | 0.4 | 0.6 | 0.28571 | 0.6 |  |  | 0.25 | 0.25 | 0.167 |  |  | 0.167 | -0.25 | HARM REIK NRE | [18 empty] | 1.075 | HARM REIK NRE | [18 empty] | 0.984
Air Power | Sensors & Systems | Small Program | BEI Detail-2 | REX Spares | [6 empty] | 0.837 | 0.788 | 0.726 | 0.728 | 0.702 | 0.704 |  | 0.728 | 0.736 | 0.748 | 0.737 | 0.682 | 0.692 | 0.879 | 0.84564 | 0.895 | 0.8872 | 0.92727 | 0.946 | 0.964 | 0.878 |  |  | 0.878 | -0.964 | REX Spares | [5 empty] | 0.4 |  | 0.097 | 0.4 | 0.6 | 0.429 | 0.25 |  |  | 0.667 | 0.167 | 0.083 |  | 0.278 | 0.048 | 0.3 | 0.897 | 0.54545 | 0.65217 | 0.296 | 1 | 0.375 |  |  | 0.375 | -1 | REX Spares | [18 empty] | 0.442 | REX Spares | [18 empty] | 0.859
Air Power | Air Dominance | Small Program | BEI Detail-2 | Lot 31 Phase 1 | 2020-04-01: 0.966; 2020-05-01: 0.912; 2020-06-01: 0.882; 2020-07-01: 0.895; 2020-08-01: 0.876; 2020-09-01: 0.864; 2020-10-01: 0.845; 2020-11-01: 0.808; 2020-12-01: 0.762; 2021-01-01: 0.761; 2021-02-01: 0.761; 2021-03-01: 0.766; 2021-04-01: 0.766; 2021-05-01: 0.766; 2021-06-01: 0.766; 2021-07-01: 0.766; 2021-08-01: 0.766 | #DIV/0! | 0 | Lot 31 Phase 1 | [8 empty] | 0.462 | 0.75 | 0.333 | 0.429 | 0.571 | 0.273 | 0.105 | 0.188 | 0.417 | 1 | 0.222 | [10 empty] | #DIV/0! | 0 | Lot 31 Phase 1 | [18 empty] | 0.415 | Lot 31 Phase 1 | [18 empty] | 0.808
Air Power | Air Dominance | Small Program | BEI Detail-2 | Lot 31 TE Phase II | 2021-01-01: 1; 2021-02-01: 0.913; 2021-03-01: 0.514; 2021-04-01: 0.434; 2021-05-01: 0.4023; 2021-06-01: 0.4023; 2021-07-01: 0.48689; 2021-08-01: 0.48689; 2021-09-01: 0.806; 2021-10-01: 0.682; 2021-11-01: 0.641; 2021-12-01: 0.576; 2022-01-01: 0.583 | 0.6 | -0.099 | Lot 31 TE Phase II | [17 empty] | 0.75 | 0.326 | 0.293 | 0.28571 | 0.551 | 0.36066 | 1 | 0.455 | 0.186 | 0.111 | 0.069 | 0.257 | 0.14567 | 0.071 | Lot 31 TE Phase II | [18 empty] | 0.214 | Lot 31 TE Phase II | [18 empty] | 0.785
Air Power | Air Dominance | Small Program | BEI Detail-2 | GWTS Replacement | [9 empty] | 1 | 1 | 1 | 1 | 0.924 | 0.991 | 1.093 | 0.981 | 0.908 | 0.904 | 0.904 | 0.87342 | 0.769 | 0.93031 | 0.92977 | 0.841 | 0.798 | 0.787 | 0.823 |  | 0.805 | -0.798 | GWTS Replacement | [10 empty] | 1 | 1 | 0.976 |  | 1 | 0.75 | 0.486 | 0.348 | 0.5 |  | 0.44737 |  | 0.38095 | 0.18519 | 0.368 | 0.25 |  | 0.138 |  | 0.138 | -0.25 | GWTS Replacement | [18 empty] | 0.483 | GWTS Replacement | [18 empty] | 0.855
Air Power | Air Dominance | Small Program | BEI Detail-2 | RFA | [6 empty] | 0.74 | 0.675 | 0.897 | 0.916 | 0.826 | 0.827 | 0.747 | 0.704 | 0.675 | 0.69 | 0.587 | 0.614 | 0.628 | 0.628 | 0.63158 | 0.613 | 0.613 | 0.65891 | 0.642 | 0.806 |  |  |  | #DIV/0! | -0.806 | RFA | [8 empty] | 0.385 | 0.571 |  | 0.2 | 0.053 |  | 0.111 | 0.5 |  | 1 | 1 |  |  |  |  | 0.15789 |  | 0.5 |  |  |  | #DIV/0! | -0.5 | RFA | [18 empty] | 1.164 | RFA | [18 empty] | 0.81
Air Power | Air Dominance | Small Program | BEI Detail-2 | HTS FTE 2018 | 2020-10-01: 0.942; 2020-11-01: 0.942; 2020-12-01: 0.965; 2021-01-01: 0.961; 2021-02-01: 0.97; 2021-03-01: 0.961; 2021-04-01: 0.961; 2021-05-01: 0.97; 2021-06-01: 0.961; 2021-07-01: 0.961; 2021-08-01: 0.97 | #DIV/0! | 0 | HTS FTE 2018 | [13 empty] | 0.333 |  | 0.8 | 0.667 | 0.4 | 0.667 | [10 empty] | #DIV/0! | 0 | HTS FTE 2018 | [19 empty] | HTS FTE 2018
Air Power | Air Dominance | Small Program | BEI Detail-2 | HTS FTE Phase 5 | 2021-11-01: 1.143; 2022-01-01: 0.917 | 1.03 | 0.917 | HTS FTE Phase 5 | [26 empty] | 1 |  | 0.833 | 0.9165 | 0.833 | HTS FTE Phase 5 | [19 empty] | HTS FTE Phase 5
Air Power | Sensors & Systems | Small Program | BEI Detail-2 | AGD Analysis and Integration | [6 empty] | 0.661 | 0.624 | 0.668 | 0.638 | 0.632 | 0.616 | 0.592 | 0.684 | 0.682 | 0.686 | 0.684 | 0.669 | 0.672 | 0.699 | 0.69935 | 0.753 | 0.76768 | 0.76159 | 0.745 | 0.75 | 0.762 | 0.764 | 0.763 | 0.763 | 0.013 | AGD Analysis and Integration | [8 empty] | 0.083 |  | 0.095 | 0.348 | 0.292 | 0.829 | 1 | 0.571 | 0.833 | 0.077 | 0.625 | 0.071 |  | 0.737 | 0.33333 |  | 0.031 | 0.067 | 0.667 | 0.5 |  | 0.5835 | -0.067 | AGD Analysis and Integration | [18 empty] | 0.605 | AGD Analysis and Integration | [18 empty] | 0.873
Air Power | Tactical Strike | Small Program | BEI Detail-2 | EMD F35B Integration | [6 empty] | 0.782 | 0.943 | 0.935 | 0.955 | 0.981 | 0.963 | 0.955 | 0.959 | 0.959 | 0.952 | 0.941 | 0.955 | 0.966 | 0.965 | 0.96684 | 0.96684 | 0.95925 | 0.95509 | 0.908 | 0.903 | 0.911 | 0.901 | 0.912 | 0.908 | 0.009 | EMD F35B Integration |  |  |  | 0.667 | 0.55 | 0.4 | 0.417 | 0.579 | 0.8 | 0.533 | 0.5 | 0.462 | 0.429 | 0.308 | 0.5 | 0.278 | 0.125 | 0.571 | 0.688 | 0.636 | 0.4 |  | 0.55 | 0.57895 | 0.357 | 0.529 | 0.727 | 0.385 | 0.636 | 0.58267 | 0.107 | EMD F35B Integration | [18 empty] | 1.336 | EMD F35B Integration | [18 empty] | 0.982
Air Power | Air Dominance | Small Program | BEI Detail-2 | C 141 | 2021-05-01: 0.918; 2021-06-01: 0.929; 2021-07-01: 0.898; 2021-08-01: 0.902; 2021-09-01: 0.887; 2022-01-01: 0.875 | 0.875 | 0.875 | C 141 | [23 empty] | 0.3 | 0.118 |  |  |  |  | #DIV/0! | 0 | C 141 | [19 empty] | C 141
Air Power | Air Dominance | Small Program | BEI Detail-2 | AMRAAM ER New IOT | 2021-05-01: 0.982; 2021-06-01: 0.977; 2021-07-01: 0.981; 2021-08-01: 0.977; 2021-09-01: 0.976; 2021-10-01: 0.954; 2021-11-01: 0.97; 2021-12-01: 0.951 | 0.9605 | -0.954 | AMRAAM ER New IOT | [20 empty] | 0.698 | 0.711 | 0.556 | 1 | 0.472 |  | 0.313 | 0.474 |  | 0.3935 | 0 | AMRAAM ER New IOT | [19 empty] | AMRAAM ER New IOT
Air Power | Sensors & Systems | Small Program | BEI Detail-2 | ROTHR Shelters Lot1 | 2020-12-01: 0.7; 2021-01-01: 0.675; 2021-03-01: 0.644; 2021-04-01: 0.644; 2021-05-01: 0.644; 2021-06-01: 0.633; 2021-07-01: 0.633; 2021-08-01: 0.633; 2021-09-01: 0.984; 2021-10-01: 1; 2021-11-01: 0.968; 2021-12-01: 0.96 | 0.964 | -1 | ROTHR Shelters Lot1 | [22 empty] | 1 | 1 |  |  | 1 |  |  | 1 | 0 | ROTHR Shelters Lot1 | [18 empty] | 0.496 | ROTHR Shelters Lot1 | [18 empty] | 0.836
Air Power | Sensors & Systems | Small Program | BEI Detail-2 | ROTHR Shelters Lot2 | 2021-08-01: 0.2; 2021-09-01: 0.2; 2021-10-01: 0.2; 2021-11-01: 0.2; 2021-12-01: 0.125 | 0.1625 | -0.2 | ROTHR Shelters Lot2 | [29 empty] | #DIV/0! | 0
Air Power | Sensors & Systems | Small Program | BEI Detail-2 | Cobra Dane TWTR | [6 empty] | 0.875 | 0.877 | 0.847 | 0.842 | 0.836 | 0.823 | 0.817 | 0.828 | 0.824 | 0.86 | 0.879 | 0.922 | 0.922 | 0.984 | 0.98431 | 0.989 | 0.989 | 0.9962 | [5 empty] | #DIV/0! | 0 | Cobra Dane TWTR | [7 empty] | 0.5 | 0.053 | 0.143 | 0.167 | 0.308 | 0.231 | 0.5 |  | 0.526 | 0.5 | 0.7 |  |  |  | 0.667 | [7 empty] | #DIV/0! | 0 | Cobra Dane TWTR | [18 empty] | 0.337 | Cobra Dane TWTR | [18 empty] | 0.944
BEI End
|  |  | BEI Avg | Avg - All | 0.78333 | 0.826 | 0.79881 | 0.81086 | 0.81152 | 0.79542 | 0.80969 | 0.82306 | 0.81606 | 0.83674 | 0.85289 | 0.85158 | 0.87368 | 0.89192 | 0.8817 | 0.84742 | 0.85347 | 0.85423 | 0.83029 | 0.82598 | 0.84595 | 0.83918 | 0.85087 | 0.83661 | 0.84655 | 0.84999 | 0.84439 | 0.8305 | 0.8506 |  |  | Avg - All | 0.50063 | 0.395 | 0.32206 | 0.39216 | 0.28833 | 0.38283 | 0.43135 | 0.45228 | 0.41414 | 0.49389 | 0.44653 | 0.49075 | 0.51568 | 0.4598 | 0.43285 | 0.42709 | 0.52329 | 0.50062 | 0.48388 | 0.46453 | 0.39077 | 0.48731 | 0.48443 | 0.4562 | 0.40491 | 0.48056 | 0.46805 | 0.36422 | 0.44974 |  |  | Avg - All | 0.96717 | 0.19217 | 0.9375 | 0.7685 | 0.86783 | 0.93267 | 0.96933 | 5.9657 | 10.1116 | 3.7462 | 10.8201 | 3.0831 | 4.8915 | 1.0593 | 1.2347 | 1.6465 | 1.1386 | 3.2132 | 1.0157 | Avg - All | 0.9195 | 0.91583 | 0.907 | 0.897 | 0.89533 | 0.89283 | 0.88933 | 0.88967 | 0.87283 | 0.90233 | 0.90217 | 0.92 | 0.98717 | 0.98513 | 1.013 | 1.0427 | 1.0534 | 1.1169 | 1.0971
|  |  | BEI Avg | Avg - Watch | 0.79 | 0.8066 | 0.768 | 0.8052 | 0.79383 | 0.7845 | 0.75617 | 0.7105 | 0.719 | 0.73767 | 0.748 | 0.75567 | 0.76467 | 0.76917 | 0.777 | 0.77183 | 0.70814 | 0.6565 | 0.70143 | 0.7077 | 0.83259 | 0.80221 | 0.77041 | 0.74536 | 0.76129 | 0.753 | 0.7625 | 0.75863 | 0.72986 |  |  | Avg - Watch | 0.298 | 0.2685 | 0.165 | 0.349 | 0.188 | 0.25333 | 0.32933 | 0.413 | 0.30567 | 0.60433 | 0.50867 | 0.623 | 0.444 | 0.55933 | 0.41133 | 0.58133 | 0.28767 | 0.29033 | 0.52667 | 0.51311 | 0.1796 | 0.40225 | 0.47176 | 0.28915 | 0.2745 | 0.44775 | 0.21975 | 0.246 | 0.193 |  |  | Avg - Watch | 0.917 | 0.81 | 1.0183 | 0.94233 | 1.1223 | 0.98433 | 0.867 | 0.63333 | 9.6762 | 5.3487 | 0.836 | 8.8994 | 1.385 | 0.96243 | 0.97986 | 0.5975 | 1.289 | 0.739 | 0.97714 | Avg - Watch | 0.94767 | 0.944 | 0.937 | 0.934 | 0.941 | 0.93733 | 0.93233 | 0.932 | 0.896 | 0.952 | 0.94967 | 0.98333 | 0.987 | 0.98733 | 0.83843 | 0.98125 | 0.97167 | 0.97475 | 0.97186
|  |  | BEI Avg | Avg - Major | 0.76543 | 0.8226 | 0.7942 | 0.80247 | 0.8068 | 0.78581 | 0.80329 | 0.83535 | 0.81188 | 0.83776 | 0.86248 | 0.86883 | 0.8905 | 0.94127 | 0.92219 | 0.87752 | 0.91982 | 0.88639 | 0.88446 | 0.87386 | 0.87384 | 0.85648 | 0.86016 | 0.85174 | 0.85737 | 0.8806 | 0.88208 | 0.86935 | 0.88196 |  |  | Avg - Major | 0.48973 | 0.34855 | 0.344 | 0.36631 | 0.27993 | 0.36771 | 0.44493 | 0.45047 | 0.45 | 0.4598 | 0.4666 | 0.50365 | 0.50968 | 0.46546 | 0.41591 | 0.38346 | 0.52355 | 0.492 | 0.55283 | 0.553 | 0.44672 | 0.52343 | 0.46804 | 0.44312 | 0.4649 | 0.51516 | 0.502 | 0.362 | 0.4353 |  |  | Avg - Major | 0.9305 | -1.2315 | 0.869 | 0.47 | 0.4885 | 0.7955 | 1.1595 | 16.478 | 15.283 | 3.282 | 16.1419 | 0.98541 | 6.8578 | 1.1402 | 1.8672 | 2.0588 | 1.1067 | 3.7098 | 0.78839 | Avg - Major | 0.8495 | 0.84 | 0.8245 | 0.805 | 0.7915 | 0.7885 | 0.7865 | 0.7885 | 0.7905 | 0.7975 | 0.7995 | 0.801 | 0.9975 | 0.988 | 1.0674 | 1.0663 | 1.0797 | 1.0435 | 1.0148
|  |  | BEI Avg | Avg - Small | 0.892 | 0.9 | 0.895 | 0.888 | 0.9 | 0.905 | 0.84337 | 0.85844 | 0.87311 | 0.8812 | 0.87006 | 0.85412 | 0.8835 | 0.85911 | 0.85605 | 0.8282 | 0.8165 | 0.86088 | 0.80142 | 0.79988 | 0.81651 | 0.82552 | 0.86054 | 0.84218 | 0.8538 | 0.84459 | 0.82578 | 0.80875 | 0.85235 |  |  | Avg - Small | 0.789 | 0.7365 | 0.277 | 0.508 | 0.35433 | 0.5174 | 0.5255 | 0.4915 | 0.39567 | 0.52813 | 0.41767 | 0.43215 | 0.51157 | 0.42615 | 0.46971 | 0.45372 | 0.55781 | 0.55081 | 0.42411 | 0.36173 | 0.39494 | 0.47821 | 0.50868 | 0.49688 | 0.37338 | 0.44259 | 0.50331 | 0.39827 | 0.54371 |  |  | Avg - Small | 1.191 | 1.186 | 0.832 | 0.844 | 0.863 | 1.052 | 0.896 | 0.938 | 1.075 | 0.796 | 0.529 | 0.556 | 0.4515 | 0.71 | -0.83537 | 0.67638 | 1.157 | 2.5649 | 1.7268 | Avg - Small | 0.975 | 0.983 | 0.982 | 0.97 | 0.966 | 0.968 | 0.966 | 0.965 | 0.968 | 0.963 | 0.965 | 0.968 | 0.967 | 0.967 | 0.96825 | 0.988 | 1.0262 | 1.4083 | 1.4778
BEI Avg End
|  |  | BEI MA Title | Mission Area | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 |  |  | Mission Area | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 |  |  | Mision Area | 2019-10-20 | 2019-11-20 | 2019-12-20 | 2020-01-20 | 2020-02-20 | 2020-03-20 | 2020-04-20 | 2020-05-20 | 2020-06-20 | 2020-07-20 | 2020-08-20 | 2020-09-20 | 2020-10-20 | 2020-11-20 | 2020-12-20 | 2021-01-20 | 2021-02-20 | 2021-03-20 | 2021-04-20 | Mision Area | 2019-10-20 | 2019-11-20 | 2019-12-20 | 2020-01-20 | 2020-02-20 | 2020-03-20 | 2020-04-20 | 2020-05-20 | 2020-06-20 | 2020-07-20 | 2020-08-20 | 2020-09-20 | 2020-10-20 | 2020-11-20 | 2020-12-20 | 2021-01-20 | 2021-02-20 | 2021-03-20 | 2021-04-20
|  |  | BEI MA | Air Power | 0.85929 | 0.85238 | 0.83937 | 0.8265 | 0.83588 | 0.8325 | 0.81712 | 0.77587 | 0.77787 | 0.78425 | 0.8149 | 0.815 | 0.8762 | 0.8735 | 0.8758 | 0.8758 | 0.8747 | 0.865 | 0.8643 | 0.86025 | 0.86279 | 0.86835 | 0.86013 | 0.86039 | 0.86067 | 0.86434 | 0.86423 | 0.864 | 0.868 |  |  | Air Power | 0.85933 | 0.40667 | 0.36667 | 0.29367 | 0.1924 | 0.2906 | 0.3442 | 0.4246 | 0.3078 | 0.4552 | 0.44957 | 0.39629 | 0.62557 | 0.462 | 0.495 | 0.46114 | 0.66029 | 0.50914 | 0.54571 | 0.54471 | 0.46154 | 0.61671 | 0.49362 | 0.52662 | 0.50817 | 0.67567 | 0.44083 | 0.4926 | 0.48067 |  |  | Air Power | 0.96717 | 0.19217 | 0.9375 | 0.7685 | 0.86783 | 0.93267 | 0.96933 | 5.9657 | 10.1116 | 4.498 | 33.5501 | 7.4604 | 1.2716 | 1.2495 | 0.8084 | 0.79529 | 0.8938 | 1.0676 | 0.98956 | Air Power | 0.9195 | 0.91583 | 0.907 | 0.897 | 0.89533 | 0.89283 | 0.88933 | 0.88967 | 0.87283 | 0.90233 | 0.90217 | 0.92 | 0.98717 | 0.98617 | 0.8953 | 0.98057 | 0.9756 | 0.98071 | 0.97378
|  |  | BEI MA | LW&AD | 0.81575 | 0.81125 | 0.7555 | 0.824 | 0.802 | 0.74833 | 0.75717 | 0.82283 | 0.8335 | 0.81417 | 0.847 | 0.85356 | 0.8981 | 0.9191 | 0.89409 | 0.89842 | 0.98875 | 0.90592 | 0.914 | 0.89745 | 0.97466 | 0.93058 | 0.94158 | 0.92143 | 0.905 | 0.94136 | 0.94482 | 0.9353 | 0.9387 |  |  | LW&AD | 0.325 | 0.43625 | 0.45725 | 0.4915 | 0.37775 | 0.3516 | 0.6368 | 0.51 | 0.53 | 0.4132 | 0.53363 | 0.67625 | 0.51244 | 0.61789 | 0.35289 | 0.43209 | 0.625 | 0.45667 | 0.47013 | 0.585 | 0.35412 | 0.43818 | 0.55832 | 0.47452 | 0.4367 | 0.494 | 0.5645 | 0.3408 | 0.5995 |  |  | LW&AD | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0.63771 | 1.6129 | 14.9843 | 0.78629 | 1.6562 | 2.4349 | 1.3064 | 6.7196 | 1.1928 | LW&AD | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.151 | 1.1252 | 1.0886 | 1.0638 | 0.99878
|  |  | BEI MA | Naval Power | 0.75733 | 0.7735 | 0.731 | 0.77633 | 0.77417 | 0.76783 | 0.7725 | 0.838 | 0.77 | 0.8325 | 0.87018 | 0.85691 | 0.852 | 0.91582 | 0.92073 | 0.834 | 0.79008 | 0.79282 | 0.80225 | 0.79437 | 0.79576 | 0.82127 | 0.81721 | 0.84773 | 0.8878 | 0.83236 | 0.774 | 0.77991 | 0.79264 |  |  | Naval Power | 0.3294 | 0.25725 | 0.10867 | 0.2405 | 0.1864 | 0.2425 | 0.2744 | 0.5092 | 0.3948 | 0.6096 | 0.41933 | 0.4834 | 0.45689 | 0.43367 | 0.44722 | 0.48133 | 0.50243 | 0.37462 | 0.3715 | 0.45189 | 0.25015 | 0.4231 | 0.45386 | 0.29355 | 0.35975 | 0.34589 | 0.40075 | 0.2498 | 0.2547 |  |  | Naval Power | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0.55157 | 0.66914 | 1.133 | 1.0627 | 0.25283 | 0.97708 | 1.6561 | 2.5467 | 1.5556 | Naval Power | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0.96792 | 1.0064 | 1.2009 | 1.3951 | 1.4385
|  |  | BEI MA | SMD | 0.657 | 0.86675 | 0.84575 | 0.81825 | 0.83075 | 0.83325 | 0.832 | 0.78575 | 0.78575 | 0.8465 | 0.88367 | 0.91129 | 0.86243 | 0.94838 | 0.91225 | 0.8225 | 0.80392 | 0.86215 | 0.77192 | 0.76192 | 0.77581 | 0.76993 | 0.79878 | 0.76804 | 0.77767 | 0.81173 | 0.819 | 0.81571 | 0.83369 |  |  | SMD | 0.497 | 0.3975 | 0.30325 | 0.38325 | 0.288 | 0.5035 | 0.41325 | 0.35675 | 0.40925 | 0.41675 | 0.37783 | 0.40557 | 0.47167 | 0.345 | 0.447 | 0.3205 | 0.45392 | 0.54238 | 0.49214 | 0.38967 | 0.52068 | 0.49471 | 0.41013 | 0.4533 | 0.3997 | 0.56543 | 0.36771 | 0.4316 | 0.44111 |  |  | SMD | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.491 | 1.149 | 1.1258 | 1.0465 | 1.1505 | 2.3334 | 2.0996 | 0.77493 | 1.8615 | 0.49891 | SMD | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0.982 | 1.019 | 1.0308 | 0.95479 | 0.98992 | 1.0314
|  |  | BEI MA | RMD | 0.78333 | 0.826 | 0.79881 | 0.81086 | 0.81152 | 0.79542 | 0.79346 | 0.80479 | 0.79113 | 0.81417 | 0.85128 | 0.85505 | 0.87242 | 0.9106 | 0.89788 | 0.85552 | 0.86273 | 0.85836 | 0.83837 | 0.82774 | 0.85207 | 0.84495 | 0.85203 | 0.84418 | 0.85274 | 0.86006 | 0.84846 | 0.84382 | 0.85479 |  |  | RMD | 0.47646 | 0.36838 | 0.31914 | 0.35613 | 0.25317 | 0.34417 | 0.41737 | 0.45505 | 0.41053 | 0.47668 | 0.45181 | 0.49778 | 0.51397 | 0.46958 | 0.42475 | 0.43415 | 0.536 | 0.46877 | 0.48541 | 0.49434 | 0.39678 | 0.47447 | 0.4751 | 0.42366 | 0.43689 | 0.50229 | 0.44624 | 0.36603 | 0.43021 |  |  | RMD | 0.96717 | 0.19217 | 0.9375 | 0.7685 | 0.86783 | 0.93267 | 0.96933 | 5.9657 | 10.1116 | 3.7462 | 10.8201 | 3.0831 | 4.8915 | 1.0593 | 1.2347 | 1.6465 | 1.1386 | 3.2132 | 1.056 | RMD | 0.9195 | 0.91583 | 0.907 | 0.897 | 0.89533 | 0.89283 | 0.88933 | 0.88967 | 0.87283 | 0.90233 | 0.90217 | 0.92 | 0.98717 | 0.98513 | 1.013 | 1.0427 | 1.0534 | 1.1169 | 1.123
|  |  | BEI MA | Plan | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 |  |  | Plan | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 |  |  | Plan | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | Plan | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
BEI MA End
|  | Mission Area | [32 empty] | Mission Area
|  | Visuals | [32 empty] | Visuals
Programs above line
3
25
12%
[15 empty] | gt | 0
[15 empty] | lt | 1
0.038462
1
0.5
2
44
4.545%
4
28
0.14286
1
33
3.03%
|  |  | BEI PAD Title | PAD | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 |  |  | PAD | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01
|  |  | BEI PAD | Sensors & Systems | 0.89975 | 0.9006 | 0.8984 | 0.8974 | 0.8978 | 0.8988 | 0.8665 | 0.824 | 0.8166 | 0.8154 | 0.81269 | 0.79846 | 0.83545 | 0.80385 | 0.80285 | 0.79871 | 0.80571 | 0.81985 | 0.81157 | 0.83725 | 0.83563 | 0.84039 | 0.8592 | 0.81767 | 0.82686 | 0.82457 | 0.81607 | 0.79559 | 0.8528 |  |  | Sensors & Systems | 0.408 | 0.37567 | 0.35025 | 0.27575 | 0.37225 | 0.3572 | 0.35725 | 0.37117 | 0.273 | 0.39667 | 0.33956 | 0.44137 | 0.45312 | 0.41438 | 0.48187 | 0.3426 | 0.574 | 0.39 | 0.40433 | 0.34422 | 0.30509 | 0.5136 | 0.53824 | 0.55072 | 0.349 | 0.577 | 0.5 | 0.4486 | 0.47867
|  |  | BEI PAD | Air Dominance | 0.75 | 0.695 | 0.653 | 0.6125 | 0.647 | 0.631 | 0.676 | 0.736 | 0.78325 | 0.8334 | 0.8246 | 0.8234 | 0.923 | 0.9015 | 0.89933 | 0.91367 | 0.89229 | 0.87143 | 0.814 | 0.79429 | 0.82441 | 0.81292 | 0.81679 | 0.82392 | 0.84033 | 0.8276 | 0.887 | 0.81025 | 0.8165 |  |  | Tactical Strike | 0.789 | 0.7365 | 0.353 | 0.629 | 0.4445 | 0.604 | 0.54967 | 0.56167 | 0.65933 | 0.63267 | 0.60667 | 0.43033 | 0.62233 | 0.38533 | 0.43233 | 0.36233 | 0.429 | 0.67967 | 0.49267 | 0.56633 | 0.42857 | 0.568 | 0.4738 | 0.5319 | 0.40667 | 0.471 | 0.45 | 0.432 | 0.5635
|  |  | BEI PAD | Tactical Strike | 0.916 | 0.926 | 0.917 | 0.9 | 0.904 | 0.904 | 0.90367 | 0.95633 | 0.95567 | 0.954 | 0.967 | 0.964 | 0.956 | 0.944 | 0.94733 | 0.91267 | 0.90833 | 0.93433 | 0.93967 | 0.934 | 0.91695 | 0.91728 | 0.91194 | 0.91281 | 0.89833 | 0.90133 | 0.90533 | 0.90233 | 0.896 |  |  | Air Dominance | 1 | 0.151 | #DIV/0! | #DIV/0! | 0.041 | 0.2325 | 0.317 | 0.436 | 0.3615 | 0.569 | 0.53675 | 0.4358 | 0.7162 | 0.52975 | 0.4936 | 0.6 | 0.5914 | 0.71114 | 0.63786 | 0.61267 | 0.56813 | 0.72325 | 0.45535 | 0.53311 | 0.4046 | 0.395 | 0.527 | 0.37175 | 0.59267
|  |  | BEI PAD | Strategic Strike | [31 empty] | Strategic Strike
|  |  | BEI PAD | Air Power | 0.85929 | 0.85238 | 0.83937 | 0.8265 | 0.83588 | 0.8325 | 0.83775 | 0.82665 | 0.83329 | 0.8435 | 0.83757 | 0.82805 | 0.87753 | 0.84959 | 0.84886 | 0.84357 | 0.84379 | 0.85048 | 0.82829 | 0.83681 | 0.84113 | 0.83975 | 0.85196 | 0.83057 | 0.8397 | 0.83573 | 0.84436 | 0.81553 | 0.84913 |  |  | Air Power | 0.73233 | 0.4585 | 0.35117 | 0.42714 | 0.3075 | 0.4063 | 0.41244 | 0.43491 | 0.38107 | 0.50415 | 0.43894 | 0.43756 | 0.56706 | 0.43933 | 0.47625 | 0.427 | 0.55353 | 0.55405 | 0.50432 | 0.44233 | 0.41044 | 0.57281 | 0.50946 | 0.54229 | 0.37553 | 0.51162 | 0.49738 | 0.41764 | 0.52518
|  |  | BEI PAD | Plan | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 |  |  | Plan | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
BEI PAD End
|  | Air Power | [32 empty] | Air Power
|  | Visuals | [32 empty] | Visuals
All Air Power
9
24
0.375
6
15
0.4
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
SMD
Air
Power
RMD
Naval
Power
SMD
Air
Power
LW&AD
RMD
Naval
Power
Air Dominance
Tactical
Strike
Sensors & Systems
Strategic Strike
Air Power
No programs available in PMX Next Gen Workspace
Tactical Strike
Air Dominance
Sensors &Systems
Air Power
Strategic Strike
No programs available in PMX Next Gen Workspace
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
LW&AD
Note on E10: Enterprise Air Surveillance Radar EMD
Note on E21: Qatar ADOC Contract 2 Cost Type
Note on E32: RDC ANTPY2 T03
Note on E33: RDC TO6
Note on E49: Left out skews the data
Note on E55: Left out skews the data
Note on E61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Australia Land 19 Phase 7B
Note on E62: Maritime Strike Tomahawk IP and T

## SPI vs. BEI
| Fiscal Month | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01
BEI | BEI - FSSMI FPIF | 0.87 | 0.861 | 0.856 | 0.848 | 0.845 | 0.842 | 0.839 | 0.837 | 0.834 | 0.833 | 0.831 | 0.829 | 0.828 | 0.827
BEI | BEI - FSSMI FFP | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857
BEI | BEI - FSSMI CP | 0.947 | 0.947 | 0.947 | 0.947 | 0.947 | 0.947 | 0.818 | 0.474 | 0.474 | 0.462 | 0.462 | 0.462 | 0.462 | 0.462
BEI | BEI - StormBreaker SDB II iECP | 0.916 | 0.926 | 0.917 | 0.9 | 0.904 | 0.904 | 0.893 | 0.889 | 0.893 | 0.896 | 0.899 | 0.909 | 0.913 | 0.899
BEI | BEI - F3R Phase 4b | 0.766 | 0.759 | 0.753 | 0.744 | 0.838 | 0.834 | 0.837 | 0.841 | 0.849 | 0.863 | 0.871 | 0.882 | 1.004 | 0.994
BEI | BEI - F3R Phase 5 | 0.734 | 0.631 | 0.553 | 0.481 | 0.456 | 0.428 | 0.451 | 0.462 | 0.475 | 0.506 | 0.531 | 0.532 | 1 | 1
BEI | BEI - Solid State Module Replacement SSMR |  |  |  |  | 0.255 |  | 1.165 | 0.919 | 0.899 | 0.887 | 0.86 | 0.828 | 0.778 | 0.79
MTD SPI | FSSMI FPIF | 1.173 | 0.871 | 1.707 | 1.078 | 1.225 | 1.663 | 1.383 | 0.698 | 1.4666 | 1.616 | 2.39 | 0.928 | 1.368 | 0.768
MTD SPI | FSSMI FFP | 0.617 | 0.765 | 0.676 | 0.576 | 1.071 | 0.645 | 0.609 | 0.601 | 13.781 | 0.991 | 0.525 | 0.701 | 1.432 | 0.937
MTD SPI | FSSMI CP | 0.961 | 0.794 | 0.672 | 1.173 | 1.071 | 0.645 | 0.609 | 0.601 | 13.781 | 13.439 | 1 | 58.177 | 0.95 | 2.508
MTD SPI | StormBreaker SDB II iECP | 1.191 | 1.186 | 0.832 | 0.844 | 0.863 | 1.052 | 0.896 | 0.938 | 1.075 | 0.796 | 1.058 | 1.112 | 0.92 | 0.975
MTD SPI | F3R Phase 4b | 1.194 | -3.043 | 1.157 | 0.386 | 0.431 | 0.951 | 1.687 | 32.266 | 29.926 | 9.415 | 259.857 | -4.609 | -0.246 | 0.706
MTD SPI | F3R Phase 5 | 0.667 | 0.58 | 0.581 | 0.554 | 0.546 | 0.64 | 0.632 | 0.69 | 0.64 | 0.731 | 0.654 | 0.695 | -0.108 | 0.896
MTD SPI | Solid State Module Replacement SSMR |  |  |  | 1.259 | 0.546 | 0.64 | 0.632 | 0.69 | 0.64 | 1.077 | 0.956 | 0.998 | 0.773 | 0.812
ITD SPI | ITD SPI - FSSMI FPIF | 0.954 | 0.954 | 0.959 | 0.96 | 0.962 | 0.966 | 0.969 | 0.967 | 0.97 | 0.974 | 0.986 | 0.986 | 0.988 | 0.987
ITD SPI | ITD SPI - FSSMI FFP | 0.893 | 0.884 | 0.87 | 0.852 | 0.864 | 0.852 | 0.839 | 0.834 | 0.859 | 0.887 | 0.888 | 0.968 | 0.978 | 0.977
ITD SPI | ITD SPI - FSSMI CP | 0.996 | 0.994 | 0.982 | 0.99 | 0.997 | 0.994 | 0.989 | 0.995 | 0.859 | 0.995 | 0.975 | 0.996 | 0.995 | 0.998
ITD SPI | ITD SPI - StormBreaker SDB II iECP | 0.975 | 0.983 | 0.982 | 0.97 | 0.966 | 0.968 | 0.966 | 0.965 | 0.968 | 0.963 | 0.965 | 0.968 | 0.967 | 0.967
ITD SPI | ITD SPI - F3R Phase 4b | 0.87 | 0.899 | 0.9 | 0.893 | 0.888 | 0.889 | 0.892 | 0.896 | 0.903 | 0.913 | 0.918 | 0.921 | 1 | 0.998
ITD SPI | ITD SPI - F3R Phase 5 | 0.829 | 0.781 | 0.749 | 0.717 | 0.695 | 0.688 | 0.681 | 0.681 | 0.678 | 0.682 | 0.681 | 0.681 | 0.995 | 0.99
ITD SPI | ITD SPI - Solid State Module Replacement SSMR |  |  |  | 0.661 | 0.667 |  | 0.977 | 0.973 | 0.883 | 0.909 | 0.914 | 0.922 | 0.909 | 0.901

## References
https://raytheon.sharepoint.us/sites/RMDEngEACBoard/Lists/2021%20Q1%20EAC%20List/No%20Minors.aspx#InplviewHashdf7f685c-a8bd-49fa-abc3-f908a74b2750=

## Test
|  | As of: 1/19/21 |  | Fiscal Month | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 3 Month Avg. | 3 Month Delta |  | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 3 Month Avg. | 3 Month Delta |  | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 |  | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01
RTX Pilot | Legacy BU | Mission Area | EAC Type |  | 2019-09-01: BEI |  |  |  | CEI | [18 empty] | MTD SPI | [16 empty] | ITD SPI
Yes | IDS | Naval Power | Watch | AMDR LRIP | 0.352 | 0.432 | 0.412 | 0.432 | 0.412 | 0.379 | 0.383 | 0.384 | 0.402 | 0.522 | 0.548 | 0.588 | 0.619 | 0.634 | 0.686 | 0.644 | 0.65467 | 0.01 | AMDR LRIP | 0.283 | 0.213 | 0.165 | 0.349 | 0.103 | 0.163 | 0.157 | 0.213 | 0.215 | 0.35 | 0.359 | 0.246 | 0.189 | 0.31 | 0.345 | 0.227 | 0.294 | -0.083 | AMDR LRIP | [10 empty] | 0.434 | 1.487 | 2.589 | 0.881 | 1.262 | -1.773 | AMDR LRIP | [14 empty] | 0.989 | 0.861
Yes | IDS | Air Power | Watch | FSSMI FPIF | 0.87 | 0.861 | 0.856 | 0.848 | 0.845 | 0.842 | 0.839 | 0.837 | 0.834 | 0.833 | 0.831 | 0.829 | 0.828 | 0.827 | 0.826 | 0.827 |  |  | FSSMI FPIF | [18 empty] | FSSMI FPIF | 1.173 | 0.871 | 1.707 | 1.078 | 1.225 | 1.663 | 1.383 | 0.698 | 1.4666 | 1.616 | 2.39 | 0.928 | 1.368 | 0.768 | 1.143 |  | FSSMI FPIF | 0.954 | 0.954 | 0.959 | 0.96 | 0.962 | 0.966 | 0.969 | 0.967 | 0.97 | 0.974 | 0.986 | 0.986 | 0.988 | 0.987 | 0.987
Yes | IDS | Air Power | Watch | FSSMI FFP | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 | 0.857 |  |  | FSSMI FFP | [18 empty] | FSSMI FFP | 0.617 | 0.765 | 0.676 | 0.576 | 1.071 | 0.645 | 0.609 | 0.601 | 13.781 | 0.991 | 0.525 | 0.701 | 1.432 | 0.937 | 0.978 |  | FSSMI FFP | 0.893 | 0.884 | 0.87 | 0.852 | 0.864 | 0.852 | 0.839 | 0.834 | 0.859 | 0.887 | 0.888 | 0.968 | 0.978 | 0.977 | 0.977
Yes | IDS | Air Power | Watch | FSSMI CP | 0.947 | 0.947 | 0.947 | 0.947 | 0.947 | 0.947 | 0.818 | 0.474 | 0.474 | 0.462 | 0.462 | 0.462 | 0.462 | 0.462 | 0.462 | 0.462 |  |  | FSSMI CP | [18 empty] | FSSMI CP | 0.961 | 0.794 | 0.672 | 1.173 | 1.071 | 0.645 | 0.609 | 0.601 | 13.781 | 13.439 | 1 | 58.177 | 0.95 | 2.508 | 0 |  | FSSMI CP | 0.996 | 0.994 | 0.982 | 0.99 | 0.997 | 0.994 | 0.989 | 0.995 | 0.859 | 0.995 | 0.975 | 0.996 | 0.995 | 0.998 | 0.111
Yes | IDS | Land Warefare & Air Defense (LW&AD) | Watch | LTAMDS UMR |  |  |  |  | 0.757 | 0.736 | 0.683 | 0.739 | 0.775 | 0.775 | 0.812 | 0.821 | 0.842 | 0.856 | 0.864 | 0.872 |  |  | LTAMDS UMR | [5 empty] | 0.461 | 0.504 | 0.493 | 0.502 | 0.463 | 1 | 1 | 1 | 1 | 0.472 | 0.517 |  |  | LTAMDS UMR | [10 empty] | 0.893 | 0.763 | 1.673 | 0.735 | 0.6 | 0.937 | LTAMDS UMR | [14 empty] | 1.019 | 1.007
No | IDS | Naval Power | Watch | EASR Production | [18 empty] | EASR Production | [18 empty] | EASR Production | [10 empty] | 0.61 | 0.24 | 0.279 | -0.078 | 2.534 | 3.226 | EASR Production | [14 empty] | 0.799 | 1.069
No | IDS | Naval Power | Watch | EASR EMD | 0.924 | 0.936 |  | 0.942 | 0.945 | 0.946 | 0.957 | 0.972 | 0.972 | 0.977 | 0.978 | 0.977 | 0.98 | 0.979 | 0.967 | 0.969 |  |  | Enterprise Air Surveillance Radar EMD | 0.313 | 0.324 |  |  | 0.273 | 0.136 | 0.327 | 0.533 | 0.2 | 1 | 0.167 |  | 0.143 | 0.368 | 0.417 | 1 |  |  | Enterprise Air Surveillance Radar EMD | [10 empty] | 0 | 0 | 1.404 | 0.986 | 0.342 | 0 | Enterprise Air Surveillance Radar EMD | [14 empty] | 0.987 | 0.988
Yes | IDS | Naval Power | Small Program | Barracuda | 0.626 | 0.617 | 0.609 | 0.593 | 0.577 | 0.565 | 0.546 | 1 | 0.5 | 0.75 | 0.753 | 0.725 | 0.849 | 0.899 | 0.805 | 0.784 | 0.82933 | -0.115 | Barracuda | 0.269 | 0.214 | 0.036 | 0.083 | 0.026 |  |  | 1 |  | 0.788 | 0.813 | 0.533 | 0.711 | 0.604 | 0.375 | 0.47 |  |  | Barracuda | [10 empty] | 0.867 | 0.882 | 0.872 | 0.96 | 1.151 | 0.891 | Barracuda | [14 empty] | 0.985 | 0.981
Yes | IDS | Naval Power | Small Program | LCS VDS | 2020-07-01: 0.709; 2020-08-01: 0.658; 2020-09-01: 0.75; 2020-10-01: 0.739; 2020-11-01: 0.71; 2020-12-01: 0.651 | 0.7 | -0.088 | LCS VDS | [12 empty] | 0.188 | 0.056 | 0.48 | 0.2 | 0.24533 | 0.144 | LCS VDS | [14 empty] | -12.396 | 1.772 | LCS VDS | [14 empty] | 0.94 | 1.124
Yes | IDS | Strategic Missile Defense | Major Program | KSA THAAD Production Non Reportable | 2020-12-01: 0.658 |  |  | KSA THAAD Production Non Reportable | [18 empty] | KSA THAAD Production Non Reportable | [14 empty] | 14.775 | 7.232 | KSA THAAD Production Non Reportable | [14 empty] | 1.095 | 1.402
Yes | IDS | Strategic Missile Defense | Major Program | KSA THAAD Production Reportable | 2020-12-01: 0.658 |  |  | KSA THAAD Production Reportable | [18 empty] | KSA THAAD Production Reportable | [14 empty] | 2.362 | 0.993 | KSA THAAD Production Reportable | [14 empty] | 1.334 | 1.258
Yes | IDS | Strategic Missile Defense | Major Program | KSA THAAD Long Lead Cost Type | 0.364 | 0.787 | 0.757 | 0.712 | 0.725 | 0.718 | 0.719 | 0.622 | 0.646 | 0.726 | 0.803 | 0.844 | 0.888 | 0.909 | 0.921 | 0.939 |  |  | KSA THAAD Long Lead Cost Type |  |  | 0.297 | 0.331 | 0.27 | 0.363 | 0.373 | 0.302 | 0.315 | 0.481 | 0.398 | 0.405 | 0.527 | 0.296 | 0.438 | 0.429 |  |  | KSA THAAD Long Lead Cost Type | [9 empty] | 1.491 | 1.353 | 0.967 | 0.856 | 1.103 | 0.467 | 1.18 | KSA THAAD Long Lead Cost Type | [13 empty] | 0.982 | 0.957 | 0.964
Yes | IDS | Strategic Missile Defense | Major Program | KSA THAAD Long Lead Fixed Price | 0.364 | 0.787 | 0.755 | 0.711 | 0.725 | 0.718 | 0.719 | 0.622 | 0.646 | 0.726 | 0.803 | 0.844 | 0.888 | 0.909 | 0.921 | 0.94 |  |  | KSA THAAD Long Lead Fixed Price |  |  | 0.297 | 0.331 | 0.27 | 0.363 | 0.373 | 0.302 | 0.315 | 0.481 | 0.398 | 0.405 | 0.527 | 0.296 | 0.438 | 0.429 |  |  | KSA THAAD Long Lead Fixed Price | [9 empty] | 1.491 | 1.353 | 0.967 | 0.856 | 1.103 | 0.467 | 0.568 | KSA THAAD Long Lead Fixed Price | [13 empty] | 0.982 | 0.957 | 0.922
Yes | IDS | Air Power | Major Program | QEWR Reportable CLINs 1001 5001 |  | 0.894 | 0.89 | 0.888 | 0.892 | 0.895 | 0.902 | 0.901 | 0.906 | 0.909 | 0.915 | 0.92 | 0.929 | 0.93 | 0.934 | 0.941 |  |  | QEWR Reportable CLINs 1001 5001 |  |  | 0.315 | 0.331 | 0.268 | 0.326 | 0.43 | 0.366 | 0.418 | 0.377 | 0.38 | 0.355 | 0.468 | 0.446 | 0.423 | 0.16 |  |  | QEWR Reportable CLINs 1001 5001 | [10 empty] | 1.962 | 2.15 | 1.677 | 1.944 | 0.914 | 0.331 | QEWR Reportable CLINs 1001 5001 | [14 empty] | 0.958 | 0.955
Yes | IDS | Air Power | Major Program | QEWR Non Reportable CLINs 2001 2002 3001 CFR | 0.925 | 0.944 | 0.942 | 0.947 | 0.948 | 0.953 | 0.94 | 0.946 | 0.935 | 0.948 | 0.94 | 0.93 | 0.942 | 0.938 | 0.951 | 0.958 |  |  | QEWR Non Reportable CLINs 2001 2002 3001 CFR |  | 0.429 | 0.429 | 0.143 | 0.273 | 0.25 | 0.375 | 0.688 | 0.214 | 0.471 | 0.375 | 0.167 | 0.347 | 0.063 | 0.3 | 0.412 |  |  | QEWR Non Reportable CLINs 2001 2002 3001 CFR | [10 empty] | 0.955 | 0.529 | 4.18 | 1.262 | 0.481 | 0.272 | QEWR Non Reportable CLINs 2001 2002 3001 CFR | [14 empty] | 0.998 | 0.982
No | IDS | Naval Power | Major Program | MK54 FY16 FY20 Production | 0.81 | 0.823 | 0.803 | 0.84 | 0.839 | 0.835 | 0.848 | 0.821 | 0.828 | 0.823 | 0.821 | 0.827 | 0.83 | 0.809 | 0.823 | 0.827 |  |  | MK54 FY16 FY20 Production | 0.31 | 0.278 |  | 0.385 | 0.356 | 0.296 | 0.253 | 0.133 | 0.692 | 0.647 | 0.385 | 0.512 | 0.143 | 0.063 | 0.276 | 0.171 | 0.17 | 0.108 | MK54 FY16 FY20 Production | [10 empty] | 1.249 | 0.655 | 1.133 | 1.856 | 1.083 | 2.79 | MK54 FY16 FY20 Production | [14 empty] | 0.938 | 1.023
No | IDS | Air Power | Major Program | SRP FOS2 | 2020-07-01: 0.873; 2020-08-01: 0.859; 2020-09-01: 0.86; 2020-10-01: 0.858; 2020-11-01: 0.877; 2020-12-01: 0.87 |  |  | SRP FOS2 | [10 empty] | 1 | 1 | 0.225 | 0.276 | 0.533 | 0.286 |  |  | SRP FOS2 | [14 empty] | 1.094 | 0.991 | SRP FOS2 | [14 empty] | 0.993 | 0.993
Yes | IDS | Air Power | Major Program | Qatar ADOC | 2020-07-01: 0.97; 2020-08-01: 0.97; 2020-09-01: 0.967; 2020-10-01: 0.97; 2020-11-01: 0.97; 2020-12-01: 0.969 |  |  | Qatar ADOC | [10 empty] | 0.205 | 0.373 | 0.92 | 0.488 | 0.382 | 0.532 |  |  | Qatar ADOC | [14 empty] | 1.121 | 0.979 | Qatar ADOC | [14 empty] | 0.991 | 0.991
No | IDS | Land Warefare & Air Defense (LW&AD) | Major Program | Qatar Depot Operations Cost Type | 2020-07-01: 0.935; 2020-08-01: 0.991; 2020-09-01: 0.988; 2020-10-01: 0.997; 2020-11-01: 0.971; 2020-12-01: 0.971 |  |  | Qatar Depot Operations Cost Type | [10 empty] | 0.722 | 0.667 | 0.2 | 1 | 0.083 | 0.182 | 0.42167 | -0.818 | Qatar Depot Operations Cost Type | [14 empty] | 1.055 | 0.93 | Qatar Depot Operations Cost Type | [14 empty] | 0.983 | 0.978
No | IDS | Land Warefare & Air Defense (LW&AD) | Major Program | Qatar Patriot Production | 0.86 | 0.859 | 0.86 | 0.861 | 0.858 | 0.855 | 0.856 | 0.852 | 0.845 | 0.851 | 0.85 | 0.85 | 0.851 | 0.963 | 0.853 | 0.854 |  |  | Qatar Patriot Production | 0.364 | 0.368 | 0.462 | 0.429 | 0.222 | 0.267 | 0.296 | 0.257 | 0.588 | 0.25 | 0.118 | 0.429 | 0.133 | 0.125 | 0.059 | 0.417 |  |  | Qatar Patriot Production | [10 empty] | 0.011 | 5.976 | 0.311 | 2.658 | 11.702 | 16.821 | Qatar Patriot Production | [14 empty] | 0.997 | 0.997
No | IDS | Land Warefare & Air Defense (LW&AD) | Major Program | Qatar Patriot 2 Lot | [18 empty] | Qatar Patriot 2 Lot | [18 empty] | Qatar Patriot 2 Lot | [14 empty] | 0.578 | 0.948 | Qatar Patriot 2 Lot | [14 empty] | 1 | 0.999
No | IDS | Land Warefare & Air Defense (LW&AD) | Major Program | Qatar NASAMS | 2020-07-01: 0.878; 2020-08-01: 0.891; 2020-09-01: 0.893; 2020-10-01: 0.918; 2020-11-01: 0.937; 2020-12-01: 0.928 |  |  | Qatar NASAMS | [10 empty] | 0.522 | 0.362 | 0.284 | 0.296 | 0.413 | 0.44 |  |  | Qatar NASAMS | [14 empty] | 0.73 | 3.427 | Qatar NASAMS | [14 empty] | 1.021 | 1.118
No | IDS | Land Warefare & Air Defense (LW&AD) | Major Program | SNAP | [18 empty] | SNAP | [18 empty] | SNAP | [16 empty] | SNAP
No | IDS | Naval Power | Major Program | AEGIS FY18 FY20 Production | 2020-07-01: 1; 2020-08-01: 0.897; 2020-09-01: 0.5; 2020-10-01: 1.167; 2020-11-01: 1.278; 2020-12-01: 0.448 | 0.96433 | -0.719 | AEGIS FY18 FY20 Production | [13 empty] | 0.385 | 1 |  |  |  | AEGIS FY18 FY20 Production | [14 empty] | 1.453 | 0.779 | AEGIS FY18 FY20 Production | [14 empty] | 1.07 | 1.048
Yes | IDS | Naval Power | Major Program | DDG 1002 Ship Set 3 Non Reportable | 0.964 | 0.959 | 0.958 | 0.975 | 0.976 | 0.976 | 0.978 | 0.924 | 0.977 | 0.979 | 0.978 | 0.978 | 0.978 | 0.98 | 0.98 | 0.98 |  |  | DDG 1002 Ship Set 3 Non Reportable | 0.472 | [5 empty] | 0.182 |  | 0.667 |  |  |  | 0.5 | 1 | 0.143 | 0.111 | 0.418 | -0.889 | DDG 1002 Ship Set 3 Non Reportable | [10 empty] | 0.701 | 1.42 | 1.671 | 2.389 | 3.971 | 2.239 | DDG 1002 Ship Set 3 Non Reportable | [14 empty] | 0.986 | 0.987
Yes | IDS | Strategic Missile Defense | Major Program | AN/TYP-2 TO3 | 2020-07-01: 0.636; 2020-08-01: 0.624; 2020-09-01: 0.656; 2020-10-01: 0.672; 2020-11-01: 0.648; 2020-12-01: 0.576 | 0.632 | -0.096 | AN/TYP-2 TO3 | [10 empty] | 0.231 | 0.261 | 0.316 | 0.1 | 0.2 | 0.102 | 0.134 | 0.002 | AN/TYP-2 TO3 | [14 empty] | 0.22 | 0.068 | AN/TYP-2 TO3 | [14 empty] | 0.811 | 0.728
No | IDS | Land Warefare & Air Defense (LW&AD) | Major Program | Bahrain Patriot 2 Lot | 2020-07-01: 0.929; 2020-08-01: 0.815; 2020-09-01: 0.918; 2020-10-01: 0.998; 2020-11-01: 0.944; 2020-12-01: 0.916 |  |  | Bahrain Patriot 2 Lot | [10 empty] | 0.674 | 0.962 | 0.632 | 0.62 | 0.509 | 0.54 |  |  | Bahrain Patriot 2 Lot | [14 empty] | 1.106 | 0.668 | Bahrain Patriot 2 Lot | [14 empty] | 1.118 | 1.05
No | IDS | Land Warefare & Air Defense (LW&AD) | Major Program | DSLC FRP | [18 empty] | DSLC FRP | [18 empty] | DSLC FRP | [14 empty] | 0.626 | 0.977 | DSLC FRP | [14 empty] | 2.451 | 2.182
No | IDS | Land Warefare & Air Defense (LW&AD) | Major Program | Poland Patriot Phase 1 | 0.608 | 0.54 | 0.651 | 0.774 | 0.759 | 0.75 | 0.783 | 0.783 | 0.803 | 0.77 | 0.775 | 0.799 | 0.811 | 0.818 | 0.829 | 0.803 |  |  | Poland Patriot Phase 1 | 0.149 | 0.227 | 0.429 | 0.356 | 0.209 | 0.346 | 1 | 0.458 | 0.449 | 0.442 | 0.339 | 0.534 | 0.471 | 0.523 | 0.515 | 0.257 |  |  | Poland Patriot Phase 1 | [10 empty] | 0.777 | 0.874 | -0.145 | 0.38 | 0.853 | 0.864 | Poland Patriot Phase 1 | [14 empty] | 1.055 | 1.04
Yes | IDS | Land Warefare & Air Defense (LW&AD) | Major Program | Patriot Sweden | 0.795 | 0.846 | 0.902 | 0.929 | 0.866 | 0.828 | 0.82 | 0.81 | 0.813 | 0.813 | 0.805 | 1.016 | 0.99 | 0.973 | 0.953 | 0.931 |  |  | Patriot Sweden | 0.462 | 0.4 | 0.5 | 0.593 | 0.444 | 0.27 | 0.618 | 0.529 | 0.516 | 0.628 | 0.439 | 0.891 | 1 | 0.414 | 0.556 | 0.594 |  |  | Patriot Sweden | [10 empty] | 0.534 | -0.591 | 0.681 | 0.588 | 0.912 | 0.579 | Patriot Sweden | [14 empty] | 1.049 | 1.016
Yes | IDS | Land Warefare & Air Defense (LW&AD) | Major Program | Romania Patriot 3 Lot | 1 | 1 | 0.609 | 0.732 | 0.77 | 0.674 | 0.874 | 0.974 | 1.017 | 0.928 | 0.943 | 0.853 | 0.859 | 0.867 | 0.857 | 0.832 |  |  | Romania Patriot 3 Lot |  | 0.75 | 0.438 | 0.588 | 0.636 | 0.414 | 0.766 | 0.813 | 0.595 | 0.283 | 0.455 | 0.565 | 0.692 | 0.583 | 0.486 | 0.457 |  |  | Romania Patriot 3 Lot | [10 empty] | 1.381 | 0.423 | 100.614 | 0.546 | 0.689 | 1.358 | Romania Patriot 3 Lot | [14 empty] | 1.147 | 1.17
No | IDS | Land Warefare & Air Defense (LW&AD) | Major Program | UAE Patriot 100 Lot GEMT Missile | [18 empty] | UAE Patriot 100 Lot GEMT Missile | [18 empty] | UAE Patriot 100 Lot GEMT Missile | [10 empty] | 0.237 | 0.195 | 0.273 | 0.15 | 0.333 | 0.511 | UAE Patriot 100 Lot GEMT Missile | [14 empty] | 1.013 | 0.976
No | IDS | Land Warefare & Air Defense (LW&AD) | Major Program | UAE 3 Lot Fire Units | [18 empty] | UAE 3 Lot Fire Units | [18 empty] | UAE 3 Lot Fire Units | [10 empty] | 0.631 | 3.65 | 1.483 | 0.447 | 0.69 | 1.199 | UAE 3 Lot Fire Units | [14 empty] | 0.959 | 0.97
No | IDS | Strategic Missile Defense | Major Program | THAAD UAE Fixed Price | [18 empty] | THAAD UAE Fixed Price | [18 empty] | THAAD UAE Fixed Price | [14 empty] | 1.122 | 7.149 | THAAD UAE Fixed Price | [14 empty] | 0.993 | 0.994
No | IDS | Strategic Missile Defense | Major Program | THAAD UAE Cost Type | 2020-08-01: 0.96; 2020-10-01: 0.969; 2020-11-01: 0.958 |  |  | THAAD UAE Cost Type | [11 empty] | 0.521 | [6 empty] | THAAD UAE Cost Type | [14 empty] | 0.877 | 0.847 | THAAD UAE Cost Type | [14 empty] | 0.989 | 0.988
Yes | RMS | Strategic Missile Defense | Major Program | SM3 IIA RDTE | 0.944 | 0.924 | 0.92 | 0.913 | 0.918 | 0.924 | 0.924 | 0.928 | 0.858 | 0.959 | 0.94 | 1.016 | 1.056 | 1.116 | 1.134 | 1.142 |  |  | SM3 IIA RDTE | 0.399 | 0.462 | 0.329 | 0.383 | 0.255 | 0.478 | 0.33 | 0.19 | 0.507 | 0.316 | 0.319 | 0.28 | 0.373 | 0.319 | 0.283 | 0.309 |  |  | SM3 IIA RDTE | [10 empty] | 0.793 | 1.569 | 1.509 | 1.278 | 0.749 | 1.04 | SM3 IIA RDTE | [14 empty] | 0.998 | 1.004
No | RMS | Strategic Missile Defense | Major Program | SM3 1B FY18 | 2020-07-01: 1.149; 2020-08-01: 1.132; 2020-09-01: 0.9; 2020-10-01: 1.037; 2020-11-01: 1.042; 2020-12-01: 0.908 |  |  | SM3 1B FY18 | [10 empty] | 0.35 | 0.649 |  | 0.251 | 0.762 |  |  |  | SM3 1B FY18 | [14 empty] | 0.976 | 0.888 | SM3 1B FY18 | [14 empty] | 1.056 | 1.048
No | RMS | Strategic Missile Defense | Major Program | SM3 BLK IIA DEV | 0.956 | 0.969 | 0.951 | 0.937 | 0.955 | 0.973 | 0.966 | 0.971 | 0.993 | 0.975 | 0.971 | 0.959 | 0.963 | 0.971 | 0.983 | 0.972 |  |  | SM3 BLK IIA DEV | 0.595 | 0.333 | 0.29 | 0.488 | 0.357 | 0.81 | 0.577 | 0.633 | 0.5 | 0.389 | 0.571 | 0.318 | 0.538 | 0.52 | 0.561 | 0.267 |  |  | SM3 BLK IIA DEV | [10 empty] | 1.097 | 1 | 0.965 | 1.118 | 1.319 | 1.031 | SM3 BLK IIA DEV | [14 empty] | 1 | 1
No | RMS | Naval Power | Major Program | SM6 FY19 23 MY Production | [18 empty] | SM6 FY19 23 MY Production | [18 empty] | SM6 FY19 23 MY Production | [14 empty] | 1 | 1.444 | SM6 FY19 23 MY Production | [14 empty] | 1 | 1.059 | bar: 2020-07-01 to 2020-12-01
Yes | RMS | Naval Power | Small Program | ESSM EMD Phase | 0.868 | 0.874 | 0.873 | 0.876 | 0.896 | 0.906 | 0.923 | 0.927 | 0.941 | 0.944 | 0.942 | 0.939 | 1.002 | 1.002 | 1.002 | 0.997 |  |  | ESSM EMD Phase |  |  | 0.125 | 0.145 | 0.174 | 0.375 | 0.453 | 0.667 | 0.2 | 0.263 |  |  | 1 |  |  | 0.987 |  |  | ESSM EMD Phase | [10 empty] | 0 | 0 | -0.017 | 0.445 | 0.56 | -2.449 | ESSM EMD Phase | [14 empty] | 0.998 | 0.998
Yes | RMS | Naval Power | Major Program | AIM-9X System Improvement Program III | 2020-07-01: 0.982; 2020-08-01: 0.981; 2020-09-01: 0.985; 2020-10-01: 0.987; 2020-11-01: 0.988; 2020-12-01: 0.989 |  |  | AIM-9X System Improvement Program III | [10 empty] | 0.382 | 0.509 | 0.548 | 0.554 | 0.489 | 0.492 |  |  | AIM-9X System Improvement Program III | [14 empty] | 0.913 | 1.749 | AIM-9X System Improvement Program III | [14 empty] | 0.984 | 0.99
Yes | RMS | Air Power | Small Program | StormBreaker SDB II iECP | 0.916 | 0.926 | 0.917 | 0.9 | 0.904 | 0.904 | 0.893 | 0.889 | 0.893 | 0.896 | 0.899 | 0.909 | 0.913 | 0.899 | 0.901 | 0.901 |  |  | StormBreaker SDB II iECP | 0.578 | 0.64 | 0.356 | 0.407 | 0.339 | 0.412 | 0.282 | 0.197 | 0.308 | 0.473 | 0.373 | 0.329 | 0.438 | 0.448 | 0.575 | 0.476 |  |  | StormBreaker SDB II iECP | 1.191 | 1.186 | 0.832 | 0.844 | 0.863 | 1.052 | 0.896 | 0.938 | 1.075 | 0.796 | 1.058 | 1.112 | 0.92 | 0.975 | 0.923 | 0.96 | StormBreaker SDB II iECP | 0.975 | 0.983 | 0.982 | 0.97 | 0.966 | 0.968 | 0.966 | 0.965 | 0.968 | 0.963 | 0.965 | 0.968 | 0.967 | 0.967 | 0.966 | 0.966
No | RMS | Air Power | Major Program | F3R Phase 4b | 0.766 | 0.759 | 0.753 | 0.744 | 0.838 | 0.834 | 0.837 | 0.841 | 0.849 | 0.863 | 0.871 | 0.882 | 1.004 | 0.994 | 0.997 | 0.989 |  |  | F3R Phase 4b | 1 |  |  |  | 0.06 | 0.132 | 0.328 | 0.487 | 0.37 | 0.576 | 0.375 | 0.378 | 1 | 0.607 | 0.739 | 0.735 |  |  | F3R Phase 4b | 1.194 | -3.043 | 1.157 | 0.386 | 0.431 | 0.951 | 1.687 | 32.266 | 29.926 | 9.415 | 259.857 | -4.609 | -0.246 | 0.706 | 0.753 | 0.935 | F3R Phase 4b | 0.87 | 0.899 | 0.9 | 0.893 | 0.888 | 0.889 | 0.892 | 0.896 | 0.903 | 0.913 | 0.918 | 0.921 | 1 | 0.998 | 0.997 | 0.997
Yes | RMS | Air Power | Major Program | F3R Phase 5 | 0.734 | 0.631 | 0.553 | 0.481 | 0.456 | 0.428 | 0.451 | 0.462 | 0.475 | 0.506 | 0.531 | 0.532 | 1 | 1 | 0.983 | 0.983 |  |  | F3R Phase 5 | 1 | 0.151 |  |  | 0.022 | 0.333 | 0.306 | 0.385 | 0.229 | 0.379 | 0.439 | 0.172 | 0.981 | 0.906 | 0.513 | 0.627 |  |  | F3R Phase 5 | 0.667 | 0.58 | 0.581 | 0.554 | 0.546 | 0.64 | 0.632 | 0.69 | 0.64 | 0.731 | 0.654 | 0.695 | -0.108 | 0.896 | 0.677 | 1.099 | F3R Phase 5 | 0.829 | 0.781 | 0.749 | 0.717 | 0.695 | 0.688 | 0.681 | 0.681 | 0.678 | 0.682 | 0.681 | 0.681 | 0.995 | 0.99 | 0.975 | 0.98
Yes | RMS | Naval Power | Major Program | Tomahawk MST | 2020-07-01: 0.861; 2020-08-01: 0.856; 2020-09-01: 0.879; 2020-10-01: 0.878; 2020-11-01: 0.889; 2020-12-01: 0.885 |  |  | Tomahawk MST | [10 empty] | 0.41 | 0.617 | 0.69 | 0.563 | 0.5 | 0.674 |  |  | Tomahawk MST | [14 empty] | 1.161 | 1.057 | Tomahawk MST | [14 empty] | 0.939 | 0.949
|  |  |  | Avg - All | 0.78333 | 0.826 | 0.79881 | 0.81086 | 0.81152 | 0.80187 | 0.80504 | 0.80591 | 0.793 | 0.81704 | 0.85571 | 0.86086 | 0.87534 | 0.91061 | 0.90836 | 0.8603 |  |  | Avg - All | 0.47646 | 0.36838 | 0.31914 | 0.35613 | 0.25317 | 0.34417 | 0.41737 | 0.45505 | 0.41053 | 0.47668 | 0.45181 | 0.49778 | 0.52359 | 0.44933 | 0.44217 | 0.43103 |  |  | Avg - All | 0.96717 | 0.19217 | 0.9375 | 0.7685 | 0.86783 | 0.93267 | 0.96933 | 5.9657 | 10.1116 | 3.7462 | 10.8201 | 3.0831 | 4.8915 | 1.0593 | 1.2347 |  | Avg - All | 0.9195 | 0.91583 | 0.907 | 0.897 | 0.89533 | 0.89283 | 0.88933 | 0.88967 | 0.87283 | 0.90233 | 0.90217 | 0.92 | 0.98717 | 0.98513 | 1.013
|  |  |  | Avg - Watch | 0.79 | 0.8066 | 0.768 | 0.8052 | 0.79383 | 0.7845 | 0.75617 | 0.7105 | 0.719 | 0.73767 | 0.748 | 0.75567 | 0.76467 | 0.76917 | 0.777 | 0.77183 |  |  | Avg - Watch | 0.298 | 0.2685 | 0.165 | 0.349 | 0.188 | 0.25333 | 0.32933 | 0.413 | 0.30567 | 0.60433 | 0.50867 | 0.623 | 0.444 | 0.55933 | 0.41133 | 0.58133 |  |  | Avg - Watch | 0.917 | 0.81 | 1.0183 | 0.94233 | 1.1223 | 0.98433 | 0.867 | 0.63333 | 9.6762 | 5.3487 | 0.836 | 8.8994 | 1.385 | 0.96243 | 0.97986 |  | Avg - Watch | 0.94767 | 0.944 | 0.937 | 0.934 | 0.941 | 0.93733 | 0.93233 | 0.932 | 0.896 | 0.952 | 0.94967 | 0.98333 | 0.987 | 0.98733 | 0.83843
|  |  |  | Avg - Major | 0.77615 | 0.83729 | 0.80743 | 0.81743 | 0.82321 | 0.8115 | 0.82979 | 0.81836 | 0.82793 | 0.84114 | 0.88636 | 0.89331 | 0.9014 | 0.94723 | 0.94696 | 0.88396 |  |  | Avg - Major | 0.52789 | 0.37756 | 0.3786 | 0.39618 | 0.28015 | 0.35754 | 0.44336 | 0.42638 | 0.45536 | 0.44 | 0.43123 | 0.4927 | 0.52341 | 0.44558 | 0.44171 | 0.39195 |  |  | Avg - Major | 0.9305 | -1.2315 | 0.869 | 0.47 | 0.4885 | 0.7955 | 1.1595 | 16.478 | 15.283 | 3.282 | 17.0966 | 0.99187 | 7.2319 | 1.1515 | 1.7342 |  | Avg - Major | 0.8495 | 0.84 | 0.8245 | 0.805 | 0.7915 | 0.7885 | 0.7865 | 0.7885 | 0.7905 | 0.7975 | 0.7995 | 0.801 | 0.9975 | 0.988 | 1.0549
|  |  |  | Avg - Small | 0.80333 | 0.80567 | 0.79967 | 0.78967 | 0.79233 | 0.79167 | 0.78733 | 0.93867 | 0.778 | 0.86333 | 0.82575 | 0.80775 | 0.8785 | 0.88475 | 0.8545 | 0.83325 |  |  | Avg - Small | 0.4235 | 0.427 | 0.17233 | 0.21167 | 0.17967 | 0.3935 | 0.3675 | 0.62133 | 0.254 | 0.508 | 0.593 | 0.431 | 0.58425 | 0.36933 | 0.47667 | 0.53325 |  |  | Avg - Small | 1.191 | 1.186 | 0.832 | 0.844 | 0.863 | 1.052 | 0.896 | 0.938 | 1.075 | 0.796 | 0.64167 | 0.66467 | 0.59167 | 0.79333 | -2.4405 |  | Avg - Small | 0.975 | 0.983 | 0.982 | 0.97 | 0.966 | 0.968 | 0.966 | 0.965 | 0.968 | 0.963 | 0.965 | 0.968 | 0.967 | 0.967 | 0.97225
|  |  |  | Mision Area | 2019-10-20 | 2019-11-20 | 2019-12-20 | 2020-01-20 | 2020-02-20 | 2020-03-20 | 2020-04-20 | 2020-05-20 | 2020-06-20 | 2020-07-20 | 2020-08-20 | 2020-09-20 | 2020-10-20 | 2020-11-20 | 2020-12-20 | 2021-01-20 |  |  | Mision Area | 2019-10-20 | 2019-11-20 | 2019-12-20 | 2020-01-20 | 2020-02-20 | 2020-03-20 | 2020-04-20 | 2020-05-20 | 2020-06-20 | 2020-07-20 | 2020-08-20 | 2020-09-20 | 2020-10-20 | 2020-11-20 | 2020-12-20 | 2021-01-20 |  |  | Mision Area | 2019-10-20 | 2019-11-20 | 2019-12-20 | 2020-01-20 | 2020-02-20 | 2020-03-20 | 2020-04-20 | 2020-05-20 | 2020-06-20 | 2020-07-20 | 2020-08-20 | 2020-09-20 | 2020-10-20 | 2020-11-20 | 2020-12-20 |  | Mision Area | 2019-10-20 | 2019-11-20 | 2019-12-20 | 2020-01-20 | 2020-02-20 | 2020-03-20 | 2020-04-20 | 2020-05-20 | 2020-06-20 | 2020-07-20 | 2020-08-20 | 2020-09-20 | 2020-10-20 | 2020-11-20 | 2020-12-20
|  |  |  | SPE | 1.04 | 1.02 | 1.02 | 1.02 | 1.02 | 1.02 | 1.02 | 1.02 | 1.02 | 1.02 | 1.02 | 1.02 | 1.04 | 1.02 | 1.04 | 1.02 |  |  | Air Power | 0.85933 | 0.40667 | 0.36667 | 0.29367 | 0.1924 | 0.2906 | 0.3442 | 0.4246 | 0.3078 | 0.4552 | 0.44957 | 0.39629 | 0.62557 | 0.462 | 0.495 | 0.46114 |  |  | Air Power | 0.96717 | 0.19217 | 0.9375 | 0.7685 | 0.86783 | 0.93267 | 0.96933 | 5.9657 | 10.1116 | 4.498 | 33.5501 | 7.4604 | 1.2716 | 1.2495 | 0.8084 |  | Air Power | 0.9195 | 0.91583 | 0.907 | 0.897 | 0.89533 | 0.89283 | 0.88933 | 0.88967 | 0.87283 | 0.90233 | 0.90217 | 0.92 | 0.98717 | 0.98617 | 0.8953
|  |  |  | SDA | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | LW&AD | 0.325 | 0.43625 | 0.45725 | 0.4915 | 0.37775 | 0.3516 | 0.6368 | 0.51 | 0.53 | 0.4132 | 0.53363 | 0.67625 | 0.5515 | 0.57012 | 0.38662 | 0.4255 |  |  | LW&AD | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0.63771 | 1.6129 | 14.9843 | 0.78629 | 1.6562 |  | LW&AD | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.151
|  |  |  | EE CCA | 1.09 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.15 | 1.09 | 1.15 | 1.09 | 1.15 |  |  | Naval Power | 0.3294 | 0.25725 | 0.10867 | 0.2405 | 0.1864 | 0.2425 | 0.2744 | 0.5092 | 0.3948 | 0.6096 | 0.41933 | 0.4834 | 0.45689 | 0.43367 | 0.44722 | 0.48133 |  |  | Naval Power | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0.55157 | 0.66914 | 1.133 | 1.0627 | 0.25283 |  | Naval Power | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0.96792
|  |  |  | SI&T | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 | 0.36 |  |  | SMD | 0.497 | 0.3975 | 0.30325 | 0.38325 | 0.288 | 0.5035 | 0.41325 | 0.35675 | 0.40925 | 0.41675 | 0.37783 | 0.40557 | 0.4562 | 0.297 | 0.447 | 0.3072 |  |  | SMD | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.491 | 1.149 | 1.1258 | 1.0465 | 1.1505 | 2.3334 |  | SMD | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0.982 | 1.019
|  |  |  | RMD | 0.76 | 0.77 | 0.77 | 0.77 | 0.77 | 0.77 | 0.77 | 0.77 | 0.77 | 0.77 | 0.77 | 0.77 | 0.76 | 0.77 | 0.76 | 0.77 |  |  | RMD | 0.47646 | 0.36838 | 0.31914 | 0.35613 | 0.25317 | 0.34417 | 0.41737 | 0.45505 | 0.41053 | 0.47668 | 0.45181 | 0.49778 | 0.52359 | 0.44933 | 0.44217 | 0.43103 |  |  | RMD | 0.96717 | 0.19217 | 0.9375 | 0.7685 | 0.86783 | 0.93267 | 0.96933 | 5.9657 | 10.1116 | 3.7462 | 10.8201 | 3.0831 | 4.8915 | 1.0593 | 1.2347 |  | RMD | 0.9195 | 0.91583 | 0.907 | 0.897 | 0.89533 | 0.89283 | 0.88933 | 0.88967 | 0.87283 | 0.90233 | 0.90217 | 0.92 | 0.98717 | 0.98513 | 1.013
|  |  |  | Plan | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 |  |  | Plan | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 |  |  | Plan | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 |  | Plan | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
SMD
Air
Power
LW&AD
RMD
Naval
Power
SMD
Air
Power
LW&AD
RMD
Naval
Power

## EAC List
PAD |  | PMX NGW | MA Eng Lead | Misson Area | Maj Proj Desc | Project Definition | Proj Def Description | EAC Classification | 1Q21 EAC Type | 1Q21 Engr EAC Category | Engr EAC Signoff Chair | EAC Bundling | Engr EAC Lead | RMD Engr EAC Template req'd | Final Engr EAC Review Date | Final Engr EAC Review Status
Sensors & Systems | Watch | FSSMI FPIF | Dan Booth | Air Power | AMRAAM | V1002798 | AMRAAM L28-30 PRODUCTION | Small Program | Comprehensive | 3 | Dan Booth | AP.C
Sensors & Systems | Watch | FSSMI FFP | Dan Booth | Air Power | AMRAAM | V1002214 | AMRAAM LOT 26 | Small Program | Comprehensive | 3 | Dan Booth | AP.C
Sensors & Systems | Watch | FSSMI CP | Dan Booth | Air Power | AMRAAM | V1002772 | AMRAAM LOT 27 | Small Program | Comprehensive | 3 | Dan Booth | AP.C
Sensors & Systems | Major Program | QEWR Reportable CLINs 1001 5001 | Dan Booth | Air Power | AMRAAM | V1003555 | AMRAAM LOT 31-32 PRODUCTION | Small Program | Comprehensive | 3 | Dan Booth | AP.C
Sensors & Systems | Major Program | QEWR Non Reportable CLINs 2001 2002 3001 CFR | Dan Booth | Air Power | AMRAAM | V1005727 | AMRAAM PSAS 20 TO#2 | Small Program | Initial | 4 | Craig Dye | AP.D
Sensors & Systems | Major Program | SRP FOS2 | Dan Booth | Air Power | AMRAAM | V1005757 | AMRAAM PSAS 2020 TO#1 NON WTY RPRS | Small Program | Initial | 4 | Craig Dye | AP.D
Sensors & Systems | Major Program | Qatar ADOC | Dan Booth | Air Power | AMRAAM | V1005100 | AMRAAM F3R PHASE 5 | Major Program | Comprehensive | 3 | Dan Booth |  | Stefanie Salini | X | 2021-02-01
Sensors & Systems | Major Program | Qatar AOC Upgrade Reportable | Dan Booth | Air Power | AMRAAM | V1005102 | AMRAAM LOT 33 1. US PROCUREMENT FUNDING | Major Program | Comprehensive | 2 | Pete Bata |  | Dan Booth |  | 2021-02-15
Sensors & Systems | Major Program | Qatar AOC Upgrade nonReportable | Dan Booth | Air Power | AMRAAM | V1005566 | AMRAAM PROD LOT 31 TEST EQUIPMENT II | Small Program | Initial | 3 | Dan Booth
Tactical Strike | Small Program | StormBreaker SDB II iECP | Dan Booth | Air Power | AMRAAM | V1005282 | ENGINEERING AND MANUFACTURING 19' | Small Program | Comprehensive | 4 | Craig Dye
Air Dominance | Major Program | F3R Phase 4b | Dan Booth | Air Power | AMRAAM | V1005653 | GWTS REPLACEMENT | Small Program | Comprehensive | 4 | Craig Dye
Air Dominance | Major Program | F3R Phase 5 | Dan Booth | Air Power | AMRAAM | V1004602 | HWIL UPGRADE | Small Program | Comprehensive | 3 | Dan Booth
Sensors & Systems | Small Program | BSU Analysis and Integration | Dan Booth | Air Power | AMRAAM | V1005281 | SIP4 RISK REDUCTION | Small Program | Comprehensive | 3 | Dan Booth
Sensors & Systems | Major Program | Clear Cod UEWR | Dan Booth | Air Power | AWS: ADV PROGRAMS | V1005844 | HTS CLS FY' 21 | Small Program | Initial | 4 | Craig Dye |  | Michelle Royal |  | 2021-02-15
Sensors & Systems | Minor Program | Qatar ADOC FFP | Dan Booth | Air Power | COMMAND AND CONTROL | 1C003220 | NASAMS ECP | Small Program | Desktop | 3 | Dan Booth |  | Jozef Laski |  | 2021-02-18
Tactical Strike | Small Program | HARM REIK NRE | Dan Booth | Air Power | COMMAND AND CONTROL | 1C002330 | QATAR ADOC CTC 2 CPIF ADOC DEV CL 1001 | Small Program | Comprehensive | 3 | Dan Booth |  | Jozef Laski |  | 2021-02-17
Sensors & Systems | Small Program | REX Spares | Dan Booth | Air Power | COMMAND AND CONTROL | 1C003328 | QATAR AOC COST REIMBURSABLE | Major Program | Initial | 3 | Dan Booth
Air Dominance | Small Program | Lot 31 Phase 1 | Dan Booth | Air Power | GRIFFIN | V1005181 | GRIFFIN CY19 PROD (-1007) QTY 250 | Small Program | Comprehensive | 3 | Josh Clark | AP.E | Benjamin Drake | No | 2021-02-25 | Review Complete
Air Dominance | Small Program | HTS FTE 2018 | Dan Booth | Air Power | GRIFFIN | V1005666 | GRIFFIN CY20 EFW NRE (FFP) | Major Program | Comprehensive | 3 | Josh Clark | AP.E | Benjamin Drake | No | 2021-02-25 | Review Complete
Sensors & Systems | Small Program | AGD Analysis and Integration | Dan Booth | Air Power | HARM | V1005770 | ARM SYSTEMS ENG TASK ORDER (ARMSET) | Small Program | Desktop | 3 | Josh Clark | AP.E | Benjamin Drake | No | 2021-02-25 | Review Complete
Tactical Strike | Small Program | EMD F35B Integration | Dan Booth | Air Power | HARM | V1005333 | HARM CLC FY19 - PRODUCTION 114 | Small Program | Comprehensive | 4 | Josh Clark | AP.E | Benjamin Drake | No | 2021-02-25 | Approved in EDIT+
Sensors & Systems | Small Program | Cobra Dane TWTR | Dan Booth | Air Power | HARM | V1005297 | HARM REIK REFURB-QATAR TAIWAN BAHRAIN | Small Program | Comprehensive | 4 | Josh Clark | AP.E | Benjamin Drake | No | 2021-02-25 | Review Complete
|  |  | Dan Booth | Air Power | IOTS | V5001347 | PAVEWAY P4/EP2 FOR QATAR | Small Program | Comprehensive | 4 | Josh Clark | AP.H | Graeme Shaw | No | 2021-02-25 | Review Complete
|  |  | Dan Booth | Air Power | IOTS | V5001249 | PAVEWAY QTY 7,500 P4S FOR KSA | Small Program | Comprehensive | 4 | Josh Clark | AP.H | Graeme Shaw | No | 2021-02-25 | Review Complete
|  |  | Dan Booth | Air Power | IOTS | V5001087 | RSL P4 QTY 3500 | Small Program | Undef. Desktop | 4 | Josh Clark | AP.H | Graeme Shaw | No | 2021-02-25 | Review Complete
|  |  | Dan Booth | Air Power | Legacy AWS | V1004694 | LOON MOUNTAIN | Small Program | Comprehensive | 3 | Susan Kelly
|  |  | Dan Booth | Air Power | Legacy AWS | V1004686 | LRSO | Watch List Program | Comprehensive | 1 | Danielle Curcio |  | Dan Booth |  | 2021-02-23 | Scheduled
|  |  | Dan Booth | Air Power | Legacy AWS | V1004683 | SKY TAVERN | Small Program | Comprehensive | 3 | Susan Kelly
|  |  | Dan Booth | Air Power | MAVERICK | V1005520 | MAVERICK FMS BUNDLE - 95 QTY | Small Program | Comprehensive | 3 | Josh Clark | AP.E | Benjamin Drake | No | 2021-02-25 | Review Complete
|  |  | Dan Booth | Air Power | MAVERICK | V1005369 | MAVERICK USG LASER 2019 | Small Program | Comprehensive | 4 | Josh Clark | AP.E | Benjamin Drake | No | 2021-02-25 | Approved in EDIT+
|  |  | Dan Booth | Air Power | MAVERICK | V1004508 | MAVERICK PHILIPPINES AGM (QTY 235) | Small Program | Comprehensive | 4 | Josh Clark | AP.E | Benjamin Drake | No | 2021-02-25 | Approved in EDIT+
|  |  | Dan Booth | Air Power | PAVEWAY | V1005496 | P2 SAUDI DFS QTY 25K | Major Program | Comprehensive | 3 | Dan Booth | AP.H | Graeme Shaw | No | 2021-02-25 | Review Complete
|  |  | Dan Booth | Air Power | PAVEWAY | V1004733 | PVWY CTRY X DCS EP2 QTY 4526 | Small Program | Comprehensive | 3 | Dan Booth | AP.H | Graeme Shaw | No | 2021-02-25 | Review Complete
|  |  | Dan Booth | Air Power | PAVEWAY | V1004322 | PVWY CTRY X DCS P2 QTY 8,567 | Small Program | Comprehensive | 3 | Dan Booth | AP.H | Graeme Shaw | No | 2021-02-25 | Review Complete
|  |  | Dan Booth | Air Power | PAVEWAY | V1004495 | PVWY CTRY Y P2 QTY 60K | Small Program | Comprehensive | 3 | Dan Booth | AP.H | Graeme Shaw | No | 2021-02-25 | Review Complete
|  |  | Dan Booth | Air Power | PAVEWAY | V1005485 | P2 GBU-58 FMS AFGHANISTAN/NIGERIA | Small Program | Desktop | 4 | Josh Clark | AP.H | Graeme Shaw | No | 2021-02-25 | Approved in EDIT+
|  |  | Dan Booth | Air Power | PAVEWAY | V1002533 | PVWY EP2 SAUDI FMS QTY 500 FFP | Small Program | Desktop | 4 | Josh Clark | AP.H | Graeme Shaw | No | 2021-02-25 | Approved in EDIT+
|  |  | Dan Booth | Air Power | PAVEWAY | V1004321 | PVWY P2 CTRY X DCS QTY 6744 | Small Program | Comprehensive | 4 | Josh Clark | AP.H | Graeme Shaw | No | 2021-02-25 | Approved in EDIT+
|  |  | Dan Booth | Air Power | PAVEWAY | V1005791 | PAVEWAY HILL AFB FY20 | Small Program | Desktop | 4 | Josh Clark | AP.H | Graeme Shaw | No | 2021-02-25 | Review Complete
|  |  | Dan Booth | Air Power | PERSISTENT AND STRAT | 1C003076 | BSU A&I CPFF ENGINEERING SERVICES | Small Program | Comprehensive | 4 | delegate
|  |  | Dan Booth | Air Power | PERSISTENT AND STRAT | 1C003016 | CLIN 40 FYL ADDITIONAL TRAINING COURSES | Small Program | Comprehensive | 4 | Dan Booth |  | Penny Marion |  | 2021-02-17
|  |  | Dan Booth | Air Power | PERSISTENT AND STRAT | 1P000383 | FSSMI FPIF | Watch List Program | Comprehensive | 1 | Danielle Curcio |  | Caitlyn Parker | X | 2021-02-08 | Scheduled
|  |  | Dan Booth | Air Power | PERSISTENT AND STRAT | 1F004964 | QEWR - CLS SPARES | Small Program | Initial | 3 | Dan Booth
|  |  | Dan Booth | Air Power | PERSISTENT AND STRAT | 1F004610 | QEWR - OBSOLETE SPARES - 4002 | Small Program | Comprehensive | 4 | Dan Booth |  | Linda Fronsdahl |  | 2021-02-11
|  |  | Dan Booth | Air Power | PERSISTENT AND STRAT | 1F003606 | QEWR - RADAR - 1001 | Major Program | Comprehensive | 3 | Dan Booth |  | Linda Fronsdhal |  | 2021-02-15
|  |  | Dan Booth | Air Power | PERSISTENT AND STRAT | 1F003924 | ROTHR SHELTERS | Small Program | Comprehensive | 4 | delegate
|  |  | Dan Booth | Air Power | PERSISTENT AND STRAT | 1A000343 | SRP FOS2 SUSTAINMENT | Major Program | Comprehensive | 3 | Dan Booth |  | Jerry Xu |  | 2021-02-09
|  |  | Dan Booth | Air Power | PERSISTENT AND STRAT | 1P000531 | SSM-R PRODUCTION QUALIFICATION | Small Program | Comprehensive | 4 | Dan Booth
|  |  | Dan Booth | Air Power | STORMBREAKER | V1005055 | SB PI&T EMD F35 | Small Program | Comprehensive | 3 | Dan Booth | AP.B
|  |  | Dan Booth | Air Power | STORMBREAKER | V1005815 | SB PROD CPFF TE | Small Program | Desktop | 4 | Dan Booth | AP.B
|  |  | Dan Booth | Air Power | STORMBREAKER | V1005094 | SB PROD LOT 6 | Major Program | Comprehensive | 3 | Dan Booth | AP.B
|  |  | Dan Booth | Air Power | STORMBREAKER | V1004750 | SB IECP DO2 | Small Program | Comprehensive | 3 | Dan Booth
|  |  | Dan Booth | Air Power | STORMBREAKER | V1003714 | SB PROD LOT 1 | Watch List Program | Comprehensive | 1 | Dan Booth |  | Mark Maley |  | 2021-02-16
|  |  | Dan Booth | Air Power | TACTICAL RADARS AIRP | 1P000438 | 3DELRR EMD - CLIN 1 | Watch List Program | Comprehensive | 1 | Danielle Curcio
Included
Not Included
Note on C8: Qatar ADOC Contract 2 Cost Type

## Sheet2 (hidden)
1 | 0.87
2 | 0.861
3 | 0.856
4 | 0.848
5 | 0.845
6 | 0.842
7 | 0.839
8 | 0.837
9 | 0.834
10 | 0.833
11 | 0.831
12 | 0.829
13 | 0.828
14 | 0.827

## Sheet10 (hidden)
| AMDR LRIP | Barracuda | FSSMI FPIF | Enterprise Air Surveillance Radar EMD | FSSMI FFP | FSSMI CP | KSA THAAD Long Lead Cost Type | KSA THAAD Long Lead Fixed Price | QEWR Reportable CLINs 1001 5001 | QEWR Non Reportable CLINs 2001 2002 3001 CFR | LTAMDS UMR | MK54 FY16 FY20 Production | Qatar Patriot Production | SNAP | Romania Patriot | Korea Config 3 | 1P000392 Kuwait Modernization | Japan PI4 1A000326 | CLS FY18 IDIQ | AEGIS FMS | DDG 1002 Ship Set 3 Non Reportable | AR3 Sentinel Production 12 Radars 2017 | CY19 Patriot Engineering Services | ATSP4 TO 1841 FEAVR | Qatar TA NET FFP | CLS FY19 IDIQ | CLS FY18 IDIQ | Qatar TA NET Cost Type | CCLS IDIQ | Poland Patriot Phase 1 | Patriot Sweden | Japan PI4 ISP | Romania Patriot 3 Lot | SM3 IIA RDTE | SM3 BLK IIA DEV | ESSM EMD Phase | StormBreaker SDB II iECP | PDSS OTB | Tomahawk JMEWS EMD
Q1 | 0.1635 | 0.0595 |  | 0.15925 |  |  | 0.30075 | 0.30075 | 0.32325 | 0.214 | 0.463 | 0.27175 | 0.25175 |  | 0.40275 |  | 0.016 |  | 0.2605 |  |  | 0.1435 |  |  | 0.35 | 0.286 | 0.25 | 0.35 |  | 0.255 | 0.439 |  | 0.438 | 0.289 | 0.339 | 0.15225 | 0.31325 |  | 0.3135
Min | 0.103 | 0.026 |  | 0.1 |  |  | 0.27 | 0.27 | 0.268 | 0.143 | 0.461 | 0.133 | 0.118 |  | 0.363 |  | 0.007 |  | 0.2 |  |  | 0.056 |  |  | 0.25 | 0.143 | 0.2 | 0.25 |  | 0.149 | 0.27 |  | 0.283 | 0.19 | 0.29 | 0.125 | 0.197 |  | 0.196
Median | 0.214 | 0.269 |  | 0.293 |  |  | 0.347 | 0.347 | 0.3605 | 0.375 | 0.502 | 0.333 | 0.33 |  | 0.4345 |  | 0.052 |  | 0.333 |  |  | 0.458 |  |  | 0.417 | 0.429 | 0.327 | 0.417 |  | 0.3925 | 0.5 |  | 0.588 | 0.3295 | 0.494 | 0.2315 | 0.3645 |  | 0.627
Max | 0.359 | 1 |  | 1 |  |  | 0.481 | 0.481 | 0.43 | 0.688 | 1 | 0.692 | 0.588 |  | 0.538 |  | 0.148 |  | 0.375 |  |  | 1 |  |  | 0.821 | 0.462 | 0.525 | 0.821 |  | 1 | 0.628 |  | 0.813 | 0.507 | 0.81 | 0.667 | 0.64 |  | 1
Q3 | 0.3325 | 0.8005 |  | 0.3785 |  |  | 0.39975 | 0.39975 | 0.3895 | 0.429 | 1 | 0.4505 | 0.429 |  | 0.5325 |  | 0.088 |  | 0.3695 |  |  | 0.6275 |  |  | 0.605 | 0.4515 | 0.44625 | 0.605 |  | 0.45575 | 0.593 |  | 0.75 | 0.44625 | 0.5905 | 0.4335 | 0.45775 |  | 0.7845

## Sheet9 (hidden)
| AMDR LRIP | Barracuda | FSSMI FPIF | Enterprise Air Surveillance Radar EMD | FSSMI FFP | FSSMI CP | KSA THAAD Long Lead Cost Type | KSA THAAD Long Lead Fixed Price | QEWR Reportable CLINs 1001 5001 | QEWR Non Reportable CLINs 2001 2002 3001 CFR | LTAMDS UMR | MK54 FY16 FY20 Production | Qatar Patriot Production | SNAP | Romania Patriot | Korea Config 3 | 1P000392 Kuwait Modernization | Japan PI4 1A000326 | CLS FY18 IDIQ | AEGIS FMS | DDG 1002 Ship Set 3 Non Reportable | AR3 Sentinel Production 12 Radars 2017 | CY19 Patriot Engineering Services | ATSP4 TO 1841 FEAVR | Qatar TA NET FFP | CLS FY19 IDIQ | CLS FY18 IDIQ | Qatar TA NET Cost Type | CCLS IDIQ | Poland Patriot Phase 1 | Patriot Sweden | Japan PI4 ISP | Romania Patriot 3 Lot | SM3 IIA RDTE | SM3 BLK IIA DEV | ESSM EMD Phase | StormBreaker SDB II iECP | PDSS OTB | Tomahawk JMEWS EMD
Q1 | 0.38325 | 0.568 | 0.834 | 0.942 | 0.857 | 0.474 | 0.6625 | 0.66225 | 0.892 | 0.93625 | 0.73675 | 0.821 | 0.85025 |  | 0.89125 |  | 0.759 |  | 0.946 | 0.706 | 0.96025 | 0.757 |  |  | 0.89875 | 0.7675 | 0.89325 | 0.89875 |  | 0.67575 | 0.81 |  | 0.7415 | 0.9185 | 0.95525 | 0.87375 | 0.89375 | 0.77 | 0.567
Min | 0.352 | 0.5 | 0.831 | 0.924 | 0.857 | 0.462 | 0.364 | 0.364 | 0.888 | 0.925 | 0.683 | 0.803 | 0.845 |  | 0.868 |  | 0.495 |  | 0.944 | 0.645 | 0.924 | 0.718 |  |  | 0.876 | 0.684 | 0.873 | 0.876 |  | 0.54 | 0.795 |  | 0.609 | 0.858 | 0.937 | 0.868 | 0.889 | 0.766 | 0.532
Median | 0.412 | 0.613 | 0.842 | 0.957 | 0.857 | 0.947 | 0.722 | 0.722 | 0.901 | 0.943 | 0.766 | 0.823 | 0.8555 |  | 0.933 |  | 0.844 |  | 0.95 | 0.724 | 0.976 | 0.826 |  |  | 0.912 | 0.846 | 0.9375 | 0.912 |  | 0.772 | 0.82 |  | 0.901 | 0.924 | 0.9675 | 0.901 | 0.902 | 0.801 | 0.789
Max | 0.595 | 1 | 0.87 | 0.979 | 0.857 | 0.947 | 0.844 | 0.844 | 0.92 | 0.953 | 0.82 | 0.848 | 0.861 |  | 0.982 |  | 0.968 |  | 0.96 | 0.891 | 0.979 | 0.961 |  |  | 0.921 | 1.042 | 0.961 | 0.921 |  | 0.803 | 0.929 |  | 1.017 | 1.037 | 0.993 | 0.944 | 0.926 | 0.989 | 0.974
Q3 | 0.4995 | 0.74375 | 0.856 | 0.977 | 0.857 | 0.947 | 0.7795 | 0.779 | 0.909 | 0.94775 | 0.80275 | 0.839 | 0.85975 |  | 0.96375 |  | 0.909 |  | 0.957 | 0.782 | 0.978 | 0.937 |  |  | 0.91675 | 0.94075 | 0.9495 | 0.91675 |  | 0.783 | 0.866 |  | 0.9935 | 0.943 | 0.9725 | 0.9305 | 0.914 | 0.9505 | 0.953

## Sheet8 (hidden)
| AMDR LRIP | Barracuda | FSSMI FPIF | Enterprise Air Surveillance Radar EMD | FSSMI FFP
Q1 | 0.38325 | 0.568 | 0.834 | 0.942 | 0.857
Min | 0.352 | 0.5 | 0.831 | 0.924 | 0.857
Median | 0.412 | 0.613 | 0.842 | 0.957 | 0.857
Max | 0.595 | 1 | 0.87 | 0.979 | 0.857
Q3 | 0.4995 | 0.74375 | 0.856 | 0.977 | 0.857

## Sheet7 (hidden)
| AMDR LRIP | Barracuda | FSSMI FPIF | Enterprise Air Surveillance Radar EMD
Q1 | 0.38325 | 0.568 | 0.834 | 0.942
Min | 0.352 | 0.5 | 0.831 | 0.924
Median | 0.412 | 0.613 | 0.842 | 0.957
Max | 0.595 | 1 | 0.87 | 0.979
Q3 | 0.4995 | 0.74375 | 0.856 | 0.977

## Sheet6 (hidden)
| AMDR LRIP | Barracuda | FSSMI FPIF
Q1 | 0.38325 | 0.568 | 0.834
Min | 0.352 | 0.5 | 0.831
Median | 0.412 | 0.613 | 0.842
Max | 0.595 | 1 | 0.87
Q3 | 0.4995 | 0.74375 | 0.856

## Sheet5 (hidden)
0.352 | 0.626 | 0.87
0.432 | 0.617 | 0.861
0.412 | 0.609 | 0.856
0.432 | 0.593 | 0.848
0.412 | 0.577 | 0.845
0.379 | 0.565 | 0.842
0.383 | 0.546 | 0.839
0.384 | 1 | 0.837
0.402 | 0.5 | 0.834
0.522 | 0.75 | 0.833
0.548 | 0.753 | 0.831
0.595 | 0.725